## Work List
Exported on: 2026-10-07 17:23:19
Filters applied:
Data source: VBGRAMG
District: KHARGONE
Block: All
Panchayat: NAGZIRI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GOGANWA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1724007026/AV/22012034663207 — PULIYA NIRMAN PARAS KE KHET KE PASS | New | 0 | 0 | 2024-08-16
GOGANWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1724007026/DP/22012034559179 — BOMBOO PLANTATION NAGZIRI | Ongoing | 824805.86 | 0 | 2022-08-22
GOGANWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1724007026/DP/22012034562538 — BAMBOO PLANTAION GERVA BEDI 1 NAGZIRI | Ongoing | 813765.86 | 104700 | 2022-09-01
GOGANWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1724007026/DP/22012034562587 — BAMBOO PLANTION GERVA BEDI NAGZIRI | Ongoing | 813793.41 | 72900 | 2022-09-01
GOGANWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1724007026/DP/22012034562754 — BAMBOO PLANTION GERVA BEDI 3 NAGZIRI | Ongoing | 813665.86 | 57900 | 2022-09-05
GOGANWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1724007026/DP/22012034563788 — BAMBOO PLANTAION GREET KE PASS NAGZIRI | Ongoing | 833343.73 | 0 | 2022-09-12
GOGANWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1724007026/DP/22012034574527 — NAKSHATRA VATIKA BONDARU BABA PPARISAR ME NAGZIRI 2022-2023 | Ongoing | 1411071.93 | 24300 | 2023-05-29
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1724007026/IF/22012035408646 — JGSA2025 CONSTRUCTION OF FORM POND FOR DEPAAK BHAGWAN KE KHET PR NAGZIRI | Ongoing | 147621.16 | 0 | 2025-04-27
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1724007026/IF/22012035497717 — KAPILDHARA KUP SADHANA JAGDISH KE KHET ME NAGZIRI | Approved | 289535.95 | 0 | 2025-04-14
GOGANWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1724007026/IF/22012035564019 — JGSA2025 RECHARGE STRUCTURE FOR KAPILDHARA KUP Kailash rameshwar ke khet meKE KHET ME NAGZIRI | Approved | 0 | 0 | 2025-04-14
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035591920 — EK BAGIYA MAA KE NAAM SANGITA SANJAY MP170022852729 | Ongoing | 279021.3 | 4200 | 2025-08-21
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035592118 — EK BAGIYA MAA KE NAAM MANISHA DEVENDRA MP170040502697 | Ongoing | 279021.3 | 4200 | 2025-08-21
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035593703 — EK BAGIYA MAA KE NAAM MAYA NITESH MP170027354974 | Ongoing | 279021.3 | 0 | 2025-09-02
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035596308 — EK BAGIYA MAA KE NAAM BHAVANA RAJENDRA MP170023614332 | Ongoing | 275021.3 | 4200 | 2025-12-22
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035596332 — EK BAGIYA MAA KE NAAM MANJULA RAMESHWAR MP170034044910 | Closed | 275021.3 | 0 | 2025-09-07
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035596346 — EK BAGIYA MAA KE NAAM PINKI PRABHAKAR MP170031778877 | Ongoing | 279021.3 | 0 | 2025-09-02
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035596349 — EK BAGIYA MAA KE NAAM SONU OMPRAKASH RATHOD MP170040502744 | Ongoing | 280784.1 | 2100 | 2025-09-02
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035604791 — EK BAGIYA MAA KE NAAM AARTI SATISH MP 2400726004 220 A | Ongoing | 275577.25 | 2100 | 2025-09-02
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035632688 — EK bagiya maa ke naam SAPNA RATHOD MP-24-007-026-004/784-A | Closed | 270661.6 | 0 | 2025-11-03
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1724007026/IF/22012035634480 — EK bagiya maa ke naam SARIKA MP-24-007-026-004/174-A | Ongoing | 270661.6 | 4200 | 2025-11-26
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/1139873 — Construction of IAY House -IAY REG. NO. MP3134583 | Approved | 27000 | 0 | 2017-05-16
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/1140453 — Construction of IAY House -IAY REG. NO. MP3193344 | Approved | 27000 | 0 | 2017-05-14
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/1140610 — Construction of IAY House -IAY REG. NO. MP3208081 | Approved | 27000 | 0 | 2017-05-14
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/4554909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113903598 | Completed | 27000 | 1566 | 2026-04-01 | 2026-09-24
GOGANWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/4585241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119540080 | Approved | 27000 | 0 | 2024-09-11
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/5767436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115007978 | Approved | 27000 | 0 | 2025-05-18
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/5767991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126861627 | Physically Completed | 27000 | 8400 | 2025-08-27 | 2026-09-20
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6072292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145271 | Completed | 23490 | 0 | 2026-04-13 | 2026-07-18
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6072298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115148383 | Completed | 23490 | 0 | 2026-04-13 | 2026-07-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6072311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115157098 | Completed | 23490 | 0 | 2026-04-13 | 2026-07-18
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6072312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115157143 | Completed | 23490 | 7854 | 2026-04-13 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6079417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119646922 | Completed | 23490 | 1566 | 2026-04-13 | 2026-08-16
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6079886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119978936 | Completed | 23490 | 1566 | 2026-04-13 | 2026-07-24
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6080742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120894251 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6080753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120899457 | Completed | 23490 | 522 | 2026-04-13 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6089216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126939926 | Completed | 23490 | 0 | 2026-04-13 | 2026-07-18
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6089220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126941957 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6089490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127122736 | Completed | 27000 | 20193 | 2026-06-18 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6090960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128117088 | Completed | 23490 | 8400 | 2026-04-13 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6091384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128573307 | Completed | 27000 | 3915 | 2026-04-13 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6092453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130028887 | Physically Completed | 27000 | 1566 | 2026-04-13 | 2026-09-29
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6110871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117850406 | Completed | 23490 | 0 | 2026-04-13 | 2026-07-18
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6182197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500636 | Ongoing | 27000 | 0 | 2026-06-18
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6186415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115425623 | Ongoing | 27000 | 17013 | 2026-07-20
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6187144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127771602 | Completed | 27000 | 20454 | 2026-06-18 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6187154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115425650 | Completed | 27000 | 20193 | 2026-06-18 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6189630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116927954 | Ongoing | 27000 | 16500 | 2026-06-18
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6194615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128798168 | Completed | 27000 | 20505 | 2026-06-18 | 2026-09-24
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6202853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312926 | Physically Completed | 27000 | 20505 | 2026-06-18 | 2026-09-29
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6203524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312319 | Ongoing | 27000 | 14400 | 2026-07-13
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6206430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120874802 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6213316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113899233 | Approved | 27000 | 0 | 2026-03-19
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6257279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119980614 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6262305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123497952 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6285659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116311931 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6301451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119570406 | Approved | 27000 | 0 | 2026-04-22
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6379546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500598 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6379628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126334304 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130028282 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500453 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392404 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117803743 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127492376 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180071 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126800802 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130028202 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126864885 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128113844 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116191357 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126801815 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130028799 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127599976 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119600373 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128114671 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119978613 | Approved | 27000 | 0 | 2026-03-19
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119979827 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114648291 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128113677 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130028375 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312587 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130055971 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119658097 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312150 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130027428 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127772073 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119579668 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116313011 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130056572 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120900441 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128064080 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127213456 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127771343 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113910592 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119647388 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124134028 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126937853 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127123683 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117862427 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124122767 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127213998 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6392995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312731 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119616478 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119638342 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114168988 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120910818 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126936814 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127770537 | Approved | 27000 | 0 | 2026-03-03
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124114577 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115164707 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393068 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126940914 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113768171 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119653147 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115174356 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115048443 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126865749 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115425600 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120897168 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117871603 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127123219 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312440 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119607994 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124132747 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121718082 | Approved | 27000 | 0 | 2026-03-03
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121718801 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115167344 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117309682 | Approved | 27000 | 0 | 2026-03-03
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117868185 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128113219 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119979039 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/6393414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130029068 | Approved | 27000 | 0 | 2026-02-25
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/861254 — Construction of IAY House -IAY REG. NO. MP1629513 | Approved | 27000 | 0 | 2017-04-07
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/878161 — Construction of IAY House -IAY REG. NO. MP1837742 | Approved | 27000 | 0 | 2017-04-07
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/919392 — Construction of IAY House -IAY REG. NO. MP2411861 | Approved | 27000 | 0 | 2017-04-07
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/919440 — Construction of IAY House -IAY REG. NO. MP2412497 | Approved | 27000 | 0 | 2017-04-07
GOGANWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1724007026/IF/IAY/926644 — Construction of IAY House -IAY REG. NO. MP2536049 | Approved | 27000 | 0 | 2017-04-07
GOGANWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1724007026/RC/22012034644418 — KHET SADAK RAJU RAWAT KE KHET SE BACCHUSINH RAMSINH(CHARI) KE KHET TAK NAGZIRI | Ongoing | 1167384.96 | 0 | 2023-09-05
GOGANWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1724007026/RS/22012034512046 — COMPOST PIT NUG 3 MEHARAJA ROAD NAGZIRI | Ongoing | 216122.54 | 0 | 2021-04-12
GOGANWA | 2024-2025 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for Community | Construction of Embankment | 1724007026/WC/22012035167726 — water pond | New | 0 | 0 | 2024-04-01