## Work List
Exported on: 2026-09-07 13:29:22
Filters applied:
Data source: VBGRAMG
District: RAJGARH
Block: All
Panchayat: BHADAHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Groups / Construction of Irrigation Open Well for Groups | Construction of Well | 1726002011/IC/22012034888050 — Heshi Kapil Dharakup Rasid Khan S/O Babu Khan Bhadahedi | New | 0 | 0 | 2024-10-02
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1726002011/IC/22012034889890 — Construction of Opan Well FOr Communiti Dariyav SIngh Solanki Ke Ghar Ke Pass Bhadahedi | New | 0 | 0 | 2025-04-01
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726002011/IC/22012034892100 — Sarvjanik Payjal Kup Nirman Ramesh Dangi Ke Ghar Ke Pichhe Balda Par Bhadahedi | Approved | 589645.73 | 0 | 2025-04-14
KHILCHIPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002011/IF/22012034665915 — RFR Gadganga Khet Talab Nirman Pawan/Shrinath Jogi Bhadahedi | Ongoing | 337715.44 | 0 | 2022-11-23
KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002011/IF/22012034821084 — CTR_RFR_GADGANGA_KHET TALAB NIRMAN RAMESH/RAMPRATAP VERMA GRAM BHADAHEDI | Ongoing | 338902.57 | 0 | 2023-06-19
KHILCHIPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002011/IF/22012034944571 — CTR_RFR_GADGANGA_KHET TALAB NIRMAN BIRAMSINGH/GYARSIRAM VERMA GRAM BHADAHEDI | Ongoing | 356340.1 | 0 | 2023-06-19
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002011/IF/22012034965129 — CTR_RFR_GADGANGA_KHET TALAB NIRMAN Ramlal/Bherulal Sahu GRAM BHADAHEDI | Ongoing | 356340.1 | 0 | 2025-05-07
KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726002011/IF/22012035276868 — Hiteshi Kapil Dhara Kup Nirman Mangilal Bapulal Dangi Bhadahedi | Approved | 0 | 0 | 2024-10-02
KHILCHIPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002011/IF/22012035314412 — JGSA_Khet Talab_Ramkailsha_Bapulal_GP Bhadahedi | New | 0 | 0 | 2025-01-24
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726002011/IF/22012035326295 — JGSA_Khet Talab Nirman_Ramlal Bherulal Sahu _Gp_ Bhadahedi | New | 0 | 0 | 2025-04-01
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/4977387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129765246 | Ongoing | 27000 | 6000 | 2025-04-30
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/5716757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123251551 | Ongoing | 27000 | 0 | 2025-09-17
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6176358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151343402 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6178053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141289710 | Approved | 27000 | 0 | 2026-03-13
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6178199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126823690 | Ongoing | 27000 | 0 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6179294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151343592 | Ongoing | 27000 | 4200 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6180106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141733792 | Ongoing | 27000 | 12300 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6183762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151343186 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6184705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150032487 | Ongoing | 27000 | 10200 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6185905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123558187 | Ongoing | 27000 | 13500 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6187792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP137815912 | Ongoing | 27000 | 0 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6192694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134008919 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6194400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131812056 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6195611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136694256 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6196502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126811523 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6197421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126072468 | Approved | 27000 | 0 | 2026-03-13
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6199484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129763425 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6199514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126801269 | Approved | 27000 | 0 | 2026-03-13
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6202554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129762875 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6203637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123546425 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6209758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123245587 | Ongoing | 27000 | 17700 | 2026-07-09
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6211133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123236163 | Ongoing | 27000 | 14400 | 2026-07-09
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6211597 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151342556 | Approved | 27000 | 0 | 2026-03-13
KHILCHIPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6213099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136694292 | Approved | 27000 | 0 | 2026-03-13
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6214878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151342739 | Ongoing | 27000 | 6000 | 2026-08-06
KHILCHIPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/6215306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123194145 | Ongoing | 27000 | 10200 | 2026-07-09
KHILCHIPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/835213 — Construction of IAY House -IAY REG. NO. MP1282158 | Approved | 27000 | 0 | 2017-04-12
KHILCHIPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/848103 — Construction of IAY House -IAY REG. NO. MP1466088 | Approved | 27000 | 0 | 2017-04-12
KHILCHIPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/849101 — Construction of IAY House -IAY REG. NO. MP1479499 | Approved | 27000 | 0 | 2017-04-12
KHILCHIPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726002011/IF/IAY/851788 — Construction of IAY House -IAY REG. NO. MP1514326 | Approved | 27000 | 0 | 2017-04-12
KHILCHIPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1726002011/RS/22012035136164 — Ciment Conkrit Nali Nirman Karya Hajarilal Verma Ke Ghar Se Jagdish Verma Ke Ghar Tak Bhadahedi | Approved | 45000 | 0 | 2024-10-02
KHILCHIPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726002011/WC/22012034602410 — RFR Gadganga Parkuleshan Tank Chokidar Ke Khet ke Pas Bhadahedi | Ongoing | 332962.02 | 0 | 2021-03-06
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1726002011/WC/22012035245491 — Construction of Dyke Nirman Bhadahedi Shanti Dham ke Pass Nale P 2024-25 Gram Bhadahedi GP Bhadahedi | Ongoing | 374351.58 | 0 | 2025-05-23
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1726002011/WC/22012035254646 — Construction Of Dyke For communiti Ramesh Dangi Ke Khet Ke Pass Gp Bhadahedi | Ongoing | 374351.58 | 0 | 2025-05-23
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1726002011/WC/22012035254650 — Construction Of Dyke For Communiti Parpadi Ke Pass Gp Bhadahedi | Ongoing | 340683.25 | 0 | 2025-05-23
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1726002011/WC/22012035258071 — Dyke Nirman Khali Fektri Ke Pichhe Gram Bhadahedi | Approved | 0 | 0 | 2025-04-01
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1726002011/WC/22012035258079 — Dyke Nirman Khali Parpadi Ke Pass Gram Bhadahedi | Approved | 0 | 0 | 2025-04-01
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1726002011/WC/22012035259468 — Dyke Nirman Shantidham Ke Pass Gp Bhadahedi | Approved | 0 | 0 | 2025-04-01
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1726002011/WC/22012035272714 — JGSA_Dugwell recharge Pit_Sarvjanik Kup Palkanda Ke Pass _Gp_Bhadahedi | Approved | 0 | 0 | 2025-04-14
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1726002011/WC/22012035272749 — JGSA_Dugwell recharge Pit_Sarvjanik Kup Anganbadi Ke Pass _Gp_Bhadahedi | Approved | 0 | 0 | 2025-04-14
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1726002011/WC/22012035272773 — JGSA_Dugwell recharge Pit_Sarvjanik Kup Kabrusthani Ke Pass _Gp_Bhadahedi | Approved | 0 | 0 | 2025-04-14
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1726002011/WC/22012035272795 — JGSA_Dugwell recharge Pit_Sarvjanik Kup Hanuman Mandir Ke Pass _Gp_Bhadahedi | Approved | 0 | 0 | 2025-04-14
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1726002011/WC/22012035316223 — Construction Of Dyke For communiti Ranglal Ke Khet Ke Pass Gp Bhadahedi | Approved | 0 | 0 | 2025-04-14
KHILCHIPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1726002011/WC/22012035316224 — Construction Of Dyke For communiti Sardar Singh Ke Khet Ke Pass Gp Bhadahedi | Approved | 0 | 0 | 2025-04-14
KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726002011/WH/22012034939970 — NGA_Stop Dam Renovation Puliya Ke Passb Bhadahedi 2024-25_Bhadahedi | Approved | 0 | 0 | 2024-04-14
KHILCHIPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726002011/WH/22012034940020 — NGA_Stop Dam Renovation Taili Ke BheruJi Maharaj Ke Pass Bhadahedi 2024-25_Bhadahedi | Approved | 0 | 0 | 2024-04-14