## Work List
Exported on: 2026-09-11 04:44:58
Filters applied:
Data source: VBGRAMG
District: RAJGARH
Block: All
Panchayat: NARAYANGHATA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726003064/IC/22012034886608 — Sarvjanik Koop Nirman_2024-25-_ Shanti Dham ke Pass Village Jodkiya GP_Narayanghata | Physically Completed | 558651.97 | 0 | 2025-12-28 | 2026-08-31
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726003064/IC/22012034886666 — Sarvjanik Koop Nirman_2024-25-_ Colonay ke Pass Gram Nagayanghata Village GP_Narayanghata | Physically Completed | 558651.97 | 0 | 2025-12-28 | 2026-08-31
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637068 — Ek Bagiya Maa Ke Naam Lakina Bai/Jitendra_003/19-B_GP Narayanghata | Ongoing | 269387.37 | 0 | 2025-11-22
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637081 — Ek Bagiya Maa Ke Naam Ramkala/Umrao Singh_004/199_GP Narayanghata | Ongoing | 269387.37 | 4200 | 2025-12-13
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637106 — Ek Bagiya Maa Ke Naam Maya Bai/Devsingh_003/11A_GP Narayanghata | Ongoing | 269387.37 | 2100 | 2025-11-27
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637109 — Ek Bagiya Maa Ke Naam Iklesh Bai/Banwari_004/119B_GP Narayanghata | Ongoing | 269387.37 | 4200 | 2025-11-27
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637112 — Ek Bagiya Maa Ke Naam_Hokam Bai/Kamal singh_004/159_GP Narayanghata | Ongoing | 269387.37 | 10500 | 2026-03-25
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637114 — Ek Bagiya Maa Ke Naam_Rammurti/Suraj singh_004/92A_GP Narayanghata | Ongoing | 269387.37 | 4200 | 2025-11-22
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637117 — Ek Bagiya Maa Ke Naam Peful Bai/Kanwarlal_004/120_GP Narayanghata | Ongoing | 269387.37 | 6300 | 2025-12-13
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637118 — Ek Bagiya Maa Ke Naam Laad Bai/Devsingh_004/128_GP Narayanghata | Ongoing | 269387.37 | 18900 | 2026-02-12
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637121 — Ek Bagiya Maa Ke Naam Manju Bai/Raghuveer _004/192_GP Narayanghata | Ongoing | 269387.37 | 0 | 2026-02-16
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637124 — Ek Bagiya Maa Ke Naam Santosh Bai/Indar Singh _004/196_GP Narayanghata | Ongoing | 269387.37 | 4200 | 2025-11-22
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637130 — Ek Bagiya Maa Ke Naam Manju Bai/Baje Singh _004/38_GP Narayanghata | Ongoing | 269387.37 | 0 | 2025-11-27
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637364 — Ek Bagiya Maa Ke Naam_Lakhina Bai / Jitendra _003/19-B _GP_Narayanghata _2025-26 | New | 0 | 0 | 2025-10-02
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637366 — Ek Bagiya Maa Ke Naam_Lakhina Bai / Jitendra _003/19-B _GP_Narayanghata _2025-26 | New | 0 | 0 | 2025-10-02
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726003064/IF/22012035637416 — Ek Bagiya Maa Ke Naam Ramkala Bai / Umrav _004/199_GP Narayanghata | New | 0 | 0 | 2025-10-02
RAJGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/2369484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2009580 | Approved | 27000 | 0 | 2020-04-28
RAJGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/2369647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2057787 | Approved | 27000 | 0 | 2020-04-28
RAJGARH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/2375437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2971157 | Approved | 27000 | 0 | 2020-04-28
RAJGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/3786878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125181453 | Approved | 27000 | 0 | 2022-04-30
RAJGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/3844337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125264666 | Approved | 27000 | 0 | 2022-04-30
RAJGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/3881862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147184395 | Ongoing | 27000 | 0 | 2022-05-31
RAJGARH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/3909625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150578730 | Approved | 27000 | 0 | 2022-04-30
RAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/4658369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148486382 | Ongoing | 27000 | 0 | 2024-10-18
RAJGARH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/4665448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149873161 | Ongoing | 27000 | 0 | 2024-11-09
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/5105440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872496 | Ongoing | 27000 | 0 | 2025-04-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6177264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147724606 | Ongoing | 27000 | 0 | 2026-06-16
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6177279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150191963 | Ongoing | 27000 | 12600 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6177448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123614117 | Ongoing | 27000 | 9300 | 2026-05-07
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6177974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125193041 | Ongoing | 27000 | 16800 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6178207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125484517 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6178237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148540310 | Ongoing | 27000 | 8400 | 2026-05-08
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6178314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124471274 | Ongoing | 27000 | 4200 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6178363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121506653 | Ongoing | 27000 | 4200 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6178636 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151719138 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6179110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126267396 | Ongoing | 27000 | 4200 | 2026-06-14
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6179625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147725889 | Ongoing | 27000 | 0 | 2026-06-14
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6179880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125108860 | Ongoing | 27000 | 0 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6179940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149509525 | Ongoing | 27000 | 8400 | 2026-05-07
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6179944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150152048 | Ongoing | 27000 | 0 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6180517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150257642 | Ongoing | 27000 | 0 | 2026-06-06
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6181331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151686234 | Ongoing | 27000 | 8400 | 2026-06-14
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6181977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147724477 | Approved | 27000 | 0 | 2026-02-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6183488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151716320 | Ongoing | 27000 | 15900 | 2026-05-11
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6183724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150177425 | Ongoing | 27000 | 0 | 2026-07-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6184334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123302418 | Ongoing | 27000 | 13800 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6184677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132893217 | Ongoing | 27000 | 0 | 2026-05-24
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6185474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151720846 | Ongoing | 27000 | 18000 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6185587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123295131 | Ongoing | 27000 | 18900 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6185608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151260633 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6185842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125262353 | Approved | 27000 | 0 | 2026-02-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6186465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149502237 | Ongoing | 27000 | 4200 | 2026-04-19
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6186548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148438337 | Ongoing | 27000 | 17700 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6186738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150541072 | Ongoing | 27000 | 12600 | 2026-06-26
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6186861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123306587 | Approved | 27000 | 0 | 2026-02-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6186965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123297059 | Ongoing | 27000 | 15900 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6186992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150150193 | Ongoing | 27000 | 12600 | 2026-06-06
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6187546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149516611 | Ongoing | 27000 | 12600 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6187635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127189214 | Ongoing | 27000 | 1500 | 2026-04-18
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6188944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125242391 | Approved | 27000 | 0 | 2026-02-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6189295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148547556 | Ongoing | 27000 | 8400 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6190050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127187234 | Ongoing | 27000 | 8400 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6190385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872885 | Ongoing | 27000 | 12600 | 2026-06-19
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6190449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148438254 | Ongoing | 27000 | 8400 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6190652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150166516 | Ongoing | 27000 | 8400 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6191104 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125846611 | Ongoing | 27000 | 8400 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6191285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151172368 | Ongoing | 27000 | 8400 | 2026-05-18
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6191441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123301366 | Approved | 27000 | 0 | 2026-02-21
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6193497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150122372 | Ongoing | 27000 | 12300 | 2026-05-24
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6196017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121503479 | Ongoing | 27000 | 8400 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6196456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125201367 | Ongoing | 27000 | 14100 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6196563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125205010 | Ongoing | 27000 | 8700 | 2026-05-24
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6196740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125660876 | Ongoing | 27000 | 8400 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6196945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150066489 | Ongoing | 27000 | 0 | 2026-06-06
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6197685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149534319 | Ongoing | 27000 | 8400 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6197930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150607651 | Ongoing | 27000 | 5100 | 2026-04-19
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6198025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123615899 | Ongoing | 27000 | 8400 | 2026-05-22
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6198122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125477189 | Approved | 27000 | 0 | 2026-02-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6198238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123298537 | Ongoing | 27000 | 18900 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6198666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151719065 | Ongoing | 27000 | 8400 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6198872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125261742 | Ongoing | 27000 | 0 | 2026-07-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6199140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872520 | Ongoing | 27000 | 16800 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6199286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121504511 | Ongoing | 27000 | 8400 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6199460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121431071 | Ongoing | 27000 | 4200 | 2026-07-21
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6200299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125281253 | Ongoing | 27000 | 4200 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6200724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125238248 | Ongoing | 27000 | 4200 | 2026-08-02
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6200838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872903 | Ongoing | 27000 | 8400 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6201844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125114669 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6202297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147724153 | Ongoing | 27000 | 8400 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6202653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125832465 | Ongoing | 27000 | 4200 | 2026-04-19
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6203101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149506347 | Ongoing | 27000 | 900 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6203679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121504498 | Ongoing | 27000 | 0 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6204337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125444655 | Ongoing | 27000 | 8400 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6204737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147724548 | Ongoing | 27000 | 8400 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6205388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126054007 | Ongoing | 27000 | 4200 | 2026-05-24
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6207212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150253608 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6207293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125117639 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6207432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121503519 | Ongoing | 27000 | 4200 | 2026-08-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6207741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147724413 | Ongoing | 27000 | 0 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6207863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872513 | Ongoing | 27000 | 0 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6208049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123306053 | Ongoing | 27000 | 15600 | 2026-06-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6208070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125182179 | Ongoing | 27000 | 8700 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6208098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149048251 | Ongoing | 27000 | 6300 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6208694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148438115 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6209227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134778359 | Ongoing | 27000 | 0 | 2026-04-25
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6209490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123301967 | Ongoing | 27000 | 8400 | 2026-06-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6209510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872668 | Ongoing | 27000 | 16800 | 2026-07-17
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6210464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151646209 | Ongoing | 27000 | 12600 | 2026-05-24
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6211331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121506618 | Ongoing | 27000 | 8400 | 2026-07-13
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6211550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148519039 | Ongoing | 27000 | 8400 | 2026-06-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6211829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150160133 | Ongoing | 27000 | 0 | 2026-06-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6212055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147724356 | Ongoing | 27000 | 8400 | 2026-06-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6212078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151146766 | Ongoing | 27000 | 12600 | 2026-04-25
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6212137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150233500 | Ongoing | 27000 | 8400 | 2026-06-26
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6212274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151479697 | Ongoing | 27000 | 4200 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6212718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126256458 | Ongoing | 27000 | 0 | 2026-04-19
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6213713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150278390 | Ongoing | 27000 | 0 | 2026-05-30
RAJGARH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6213894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125184378 | Approved | 27000 | 0 | 2026-02-05
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6213966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151324518 | Ongoing | 27000 | 4200 | 2026-05-22
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6214272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149530397 | Ongoing | 27000 | 8400 | 2026-05-31
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6214355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872651 | Ongoing | 27000 | 8400 | 2026-05-18
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6214521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149048107 | Ongoing | 27000 | 16800 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6214523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121503536 | Ongoing | 27000 | 4200 | 2026-07-21
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6214667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125831703 | Ongoing | 27000 | 5100 | 2026-04-25
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6214774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150260959 | Ongoing | 27000 | 8400 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6215017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126562257 | Ongoing | 27000 | 4200 | 2026-07-09
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6215283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150130896 | Ongoing | 27000 | 0 | 2026-05-30
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6215346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151703511 | Ongoing | 27000 | 15900 | 2026-04-25
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6215351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151281272 | Ongoing | 27000 | 4200 | 2026-08-03
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6215561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150102562 | Ongoing | 27000 | 16800 | 2026-07-13
RAJGARH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726003064/IF/IAY/6216265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149872715 | Ongoing | 27000 | 4200 | 2026-07-21
RAJGARH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1726003064/WC/22012035205234 — Earthen Bund Percolation Tank Nirman karya Morsingh ke Khet Ke Pass 2024-25 Gram Jodkiya GP Narayan | Approved | 0 | 0 | 2024-06-06
RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1726003064/WC/22012035305530 — JGSA_2025-2026_RECHARGE STRUCTURE SARVJANIK PAYJAL KOOP NIRMAN_Gram NARAYANGHATA_GP NARAYANGHATA | Approved | 23977.32 | 0 | 2025-04-14
RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1726003064/WC/22012035305531 — JGSA_2025-2026_RECHARGE STRUCTURE SARVJANIK PAYJAL KOOP PURJI KE GHAR KE PICHHE_Gram JODKIYA | Approved | 23977.32 | 0 | 2025-04-14
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035326622 — WATER HARVESTING POND_2025-26_JUJHARSINGH KE KHET KE PASS_GR. JODKIYA_GP NARAYANGHATA | Physically Completed | 952501.65 | 0 | 2026-04-07 | 2026-08-31
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035326623 — WATER HARVESTING POND_2025-26_KAILASH KE KHET KE PASS_GR. JODKIYA_GP NARAYANGHATA | Physically Completed | 979137.2 | 0 | 2026-04-08 | 2026-08-31
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035326624 — WATER HARVESTING POND_2025-26_RAMESH GHISAJI KE KHET KE PASS_GR. JODKIYA_GP NARAYANGHATA | Physically Completed | 968043.37 | 0 | 2026-04-08 | 2026-08-31
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035326625 — WATER HARVESTING POND_2025-26_BHANWARLAL TAILAR KE KHET KE PASS_GR. JODKIYA_GP NARAYANGHATA | Physically Completed | 948582.93 | 0 | 2026-04-08 | 2026-08-31
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035326626 — WATER HARVESTING POND_2025-26_DEVSINGH KE KHET KE PASS_GR. JODKIYA_GP NARAYANGHATA | Physically Completed | 977620.96 | 0 | 2026-04-08 | 2026-08-31
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035326627 — WATER HARVESTING POND_2025-26_RAMESH KE KHET KE PASS_GR. JODKIYA_GP NARAYANGHATA | Physically Completed | 934233.96 | 0 | 2026-04-08 | 2026-08-31
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035329027 — WATER HARVESTING POND_2025-26_SHIVNARAYAN KI BALDI KE PASS_GRAM JODKIYA_GP NARAYANGHATA | Physically Completed | 866200.66 | 0 | 2026-04-08 | 2026-08-31
RAJGARH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726003064/WC/22012035329252 — WATER HARVESTING POND_2025-26_BHAGWANSINGH KE KHET KE PASS_GRAM NARAYANGHATA_GP NARAYANGHATA | Approved | 0 | 0 | 2026-01-23
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1726003064/WC/VB/22012035332884 — Gabion Work Stucture Unit-5_2026-27_Dhaniya Wale Nale Per_Gram Narayanghata_GP Narayanghata | Ongoing | 157720.28 | 300 | 2026-08-22
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1726003064/WC/VB/22012035332885 — Loose Bolder Check Dam Unit-5_2026-27_Kundibeh Rasta Nale Per_Gram Narayanghata_GP Narayanghata | Ongoing | 70698.95 | 300 | 2026-08-22
RAJGARH | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1726003064/WC/VB/22012035332886 — Roof Water Harvesting Work_2026-27_Samudayeek Manglik Bhawan_Gram Narayanghata_GP Narayanghata | Ongoing | 30496.65 | 600 | 2026-08-22