## Work List
Exported on: 2026-09-30 12:35:47
Filters applied:
Data source: VBGRAMG
District: RAJGARH
Block: All
Panchayat: KHEJDA MAHARAJA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726004053/IC/22012034893078 — Sarvjanik Koop Nirman_2025-26 Mandir Shri Thakur Ji Maharaj Village Khejda maharaja GP_ Khejda mahar | Ongoing | 605674.69 | 0 | 2026-01-31
BIAORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726004053/IF/22012034423253 — Horticulture Plantation Ramlal s/o Bhanwarji | Ongoing | 117250 | 0 | 2018-09-29
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726004053/IF/22012035285918 — Hiteshi Koop Group Imrat lal s/o Prabhulal Village - Khejdamaharaja GP Khejdamaharaja | Ongoing | 312155.12 | 0 | 2025-02-20
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726004053/IF/22012035285923 — Hiteshi Koop Group Ramlal s/o Kaluram Village- Khejda maharaja GP Khejda maharaja | Physically Completed | 312155.12 | 0 | 2025-02-08 | 2026-09-05
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004053/IF/22012035285934 — Mini Percolation Pond 2024-25_IndarSingh s/o DeviSingh Village- Khejdamaharaja GP Khejdamaharaja | Approved | 0 | 0 | 2024-10-02
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726004053/IF/22012035657381 — Hiteshi Koop Group_2025-26 Prem Singh s/o Bane Singh_Village Khejda maharaja GP_ Khejda maharaja | Approved | 322434.45 | 0 | 2025-10-02
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1726004053/IF/22012035657453 — Hiteshi Koop Group_2025-26 Ramswroop s/o Tulshiram_Village Khejda maharaja GP_ Khejda maharaja | Approved | 322434.45 | 0 | 2025-10-02
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6122822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100084426 | Physically Completed | 27000 | 27000 | 2026-08-01 | 2026-09-24
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6122846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100103698 | Physically Completed | 27000 | 25880 | 2026-07-07 | 2026-09-16
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6126342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115960009 | Physically Completed | 27000 | 27000 | 2026-08-01 | 2026-09-24
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6126679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116415246 | Ongoing | 27000 | 12600 | 2026-08-01
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6126682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116416091 | Ongoing | 27000 | 12600 | 2026-08-01
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6136459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115959710 | Physically Completed | 27000 | 27000 | 2026-08-01 | 2026-09-24
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6136554 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106123513 | Approved | 27000 | 0 | 2026-02-11
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6136646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123431941 | Ongoing | 27000 | 16800 | 2026-07-20
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6136957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123917074 | Physically Completed | 27000 | 27000 | 2026-07-20 | 2026-09-22
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6141294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118530503 | Approved | 27000 | 0 | 2026-02-11
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6145230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118848088 | Physically Completed | 27000 | 27000 | 2026-07-20 | 2026-09-16
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6149821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106123969 | Ongoing | 27000 | 0 | 2026-09-16
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6149822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106125231 | Ongoing | 27000 | 16800 | 2026-07-20
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6149823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106880390 | Physically Completed | 27000 | 27000 | 2026-08-01 | 2026-09-24
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6149824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113496485 | Physically Completed | 27000 | 27000 | 2026-07-20 | 2026-09-16
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6149825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100084395 | Approved | 27000 | 0 | 2026-02-11
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6156322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891219 | Ongoing | 27000 | 12600 | 2026-08-01
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6165709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106890793 | Completed | 27000 | 27000 | 2026-07-20 | 2026-09-16
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6167158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115960626 | Physically Completed | 27000 | 27000 | 2026-07-07 | 2026-09-22
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6168005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115960538 | Physically Completed | 27000 | 27000 | 2026-07-20 | 2026-09-16
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6175393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100103818 | Physically Completed | 27000 | 27000 | 2026-07-20 | 2026-09-22
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004053/IF/IAY/6175394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100103877 | Ongoing | 27000 | 24300 | 2026-07-20
BIAORA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1726004053/RC/VB/22012034854306 — Sugam Samparkta Pariyojna 2026-27 Jhandupura se khejda Maharaja GP Khejdamaharaja | Deleted | 0 | 0 | 2026-06-05
BIAORA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1726004053/WC/VB/22012035332253 — Rooftop rainwater Harvesting _2026-27_ Panchyat Bhawan Village Khejdamaharaja GP Khejdamaharaja | Approved | 0 | 0 | 2026-07-19
BIAORA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1726004053/WC/VB/22012035332254 — Rooftop rainwater Harvesting _2026-27_ Primary School Village Khejdamaharaja GP Khejdamaharaja | Approved | 0 | 0 | 2026-07-17
BIAORA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1726004053/WC/VB/22012035332255 — Rooftop rainwater Harvesting _2026-27_ Aganwadi BhawanVillage Khejdamaharaja GP Khejdamaharaja | Approved | 0 | 0 | 2026-07-17