## Work List
Exported on: 2026-10-22 04:34:40
Filters applied:
Data source: VBGRAMG
District: RAJGARH
Block: All
Panchayat: MAHU
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1726004059/IC/22012034886189 — Sarvjanik Kup Nirman Colonay Pathar Par_2024-25_Gram-Mahu_GP-Mahu | Approved | 558651.97 | 0 | 2024-10-02
BIAORA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726004059/IF/22012034557448 — Hiteshi Kapil Dhara kup Balabagas s/o Roadji | Ongoing | 242453.87 | 0 | 2020-06-03
BIAORA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726004059/IF/22012035081377 — Hiteshi Koop Nirman_Prem Singh s/o Bhagirath_Gram_Mahu_2023-24_GP_Mahu | Ongoing | 282040.21 | 0 | 2023-06-21
BIAORA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1726004059/IF/22012035081384 — Hiteshi Koop Nirman_Pananalal s/o Nandram_Gram_Mahu_2023-24_GP_Mahu | Physically Completed | 282040.21 | 0 | 2023-06-21 | 2026-09-15
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726004059/IF/22012035302734 — Mini Percolation Pond 2024-25 Bharat Singh S/o Man Singh Rajput Village - Mahu GP Mahu | Approved | 0 | 0 | 2025-01-29
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1726004059/IF/22012035302737 — Mini Percolation Pond 2024-25 Mulchand s/o Revaram Village - Mahu GP Mahu | Approved | 0 | 0 | 2025-01-29
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726004059/IF/22012035596977 — Ek Bagiya Maa Ke Naam_Jasodi Bai_001/256_GP_ Mahu_2025-26 | Ongoing | 263510.03 | 32700 | 2025-09-24
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726004059/IF/22012035596995 — Ek Bagiya Maa Ke Naam_Ramkanya Bai Sen_001/596_GP_ Mahu_2025-26 | Ongoing | 263510.03 | 42000 | 2025-09-24
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6128376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126733185 | Physically Completed | 27000 | 25200 | 2026-07-31 | 2026-09-27
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6128379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126734727 | Approved | 27000 | 0 | 2026-02-08
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6131337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148691063 | Approved | 27000 | 0 | 2026-02-10
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6131338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148691099 | Physically Completed | 27000 | 25200 | 2026-07-31 | 2026-09-27
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6138455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123435498 | Physically Completed | 23490 | 0 | 2026-06-16 | 2026-07-24
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6138465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123438997 | Ongoing | 27000 | 0 | 2026-07-30
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6143699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124155986 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6144693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126738182 | Physically Completed | 27000 | 4200 | 2026-06-11 | 2026-09-27
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6151340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126581177 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6159741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123453747 | Physically Completed | 27000 | 24600 | 2026-08-04 | 2026-09-27
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6162807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123453196 | Physically Completed | 23490 | 3000 | 2026-06-11 | 2026-08-16
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6165566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124156525 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6172335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123438445 | Physically Completed | 23490 | 3000 | 2026-06-11 | 2026-08-16
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6175884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124181244 | Ongoing | 27000 | 0 | 2026-10-15
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6182688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124178160 | Ongoing | 27000 | 16800 | 2026-08-01
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6182745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126732175 | Ongoing | 27000 | 16800 | 2026-07-31
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6193443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123437291 | Physically Completed | 23490 | 0 | 2026-05-27 | 2026-07-24
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6311032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123454312 | Ongoing | 27000 | 0 | 2026-10-08
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6313363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148691133 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6313364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148697529 | Ongoing | 27000 | 0 | 2026-10-15
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6315151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151582597 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6315152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151582724 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6316415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126550724 | Approved | 27000 | 0 | 2026-02-10
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6317761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736062 | Approved | 27000 | 0 | 2026-02-09
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6317762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148691022 | Ongoing | 27000 | 0 | 2026-10-15
BIAORA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726004059/IF/IAY/6339356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124179873 | Ongoing | 27000 | 0 | 2026-10-15
BIAORA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1726004059/RC/22012034834482 — Sudur Sadak Nirman Kary_Andheri Bag se Kankad Tak_2024-25_GP_Mahu | Ongoing | 1628690.37 | 0 | 2025-04-02