## Work List
Exported on: 2026-09-26 03:39:38
Filters applied:
Data source: VBGRAMG
District: RAJGARH
Block: All
Panchayat: MANKI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BIAORA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1726004062/AV/22012034466122 — Anganwadi Bhawan Nirman Charkhedi | Physically Completed | 180000 | 0 | 2020-12-26 | 2026-09-02
BIAORA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1726004062/DP/22012034567019 — Plantation_work Shantidham Parisar Charkhedi_ 2022-23_ Gram panchayat _ Manki | Ongoing | 154242.72 | 0 | 2022-09-19
BIAORA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726004062/DP/22012034578845 — Sarvjanik Koop Nirman Gram_Manki 2023-24 GP_Manki | Physically Completed | 648891.55 | 0 | 2023-12-30 | 2026-09-10
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726004062/IC/22012034893189 — Sarvjanik Koop Nirman_2025-26 Hrijan Colony Village Manki GP Manki | Approved | 605674.69 | 0 | 2025-12-21
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1726004062/IC/22012034893351 — Sarvjanik Koop Nirman_2025-26 Hrijan Colony Village Manki GP Manki | New | 0 | 0 | 2026-01-26
BIAORA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726004062/IF/22012034423550 — Horticulture Plantation Mangibai w/o Phool Singh | Ongoing | 117250 | 0 | 2019-01-25
BIAORA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035314119 — JGSA Khet Talab Devi Singh/Biram GP Manki | New | 0 | 0 | 2025-03-27
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480057 — JGSA_2025-26-Khet Talab- Devi Singh/ Ratan singh -GP- Manki | Approved | 200188.89 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480106 — JGSA_2025-26-Khet Talab- Sarjan Singh/ kalu singh -GP- Manki | Approved | 199883.22 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480150 — JGSA_2025-26-Khet Talab- Jagdish / Baje singh -GP- Manki | Approved | 199883.22 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480227 — JGSA_2025-26-Khet Talab-Ram Singh/ Madhu singh -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480282 — JGSA_2025-26-Khet Talab- Daryav Singh/ Lal ji Gram -Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480506 — JGSA_2025-26-Khet Talab- Bane Singh/ Ramlal -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480560 — JGSA_2025-26-Khet Talab- Umrav Singh/ Madho Singh Gram-Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480598 — JGSA_2025-26-Khet Talab- Kamer singh / Dev ji Gram- Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480620 — JGSA_2025-26-Khet Talab- Sarjan Singh/ Ram Singh Gram- Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480639 — JGSA_2025-26-Khet Talab- Devi Singh/ Ramlal Gram - Bhagora -GP- Manki | Approved | 199883.22 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480666 — JGSA_2025-26-Khet Talab- Parvat Singh / Nathu jiGram - Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480732 — JGSA_2025-26-Khet Talab- Narayan Singh/Karan Singh Gram - manki -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480764 — JGSA_2025-26-Khet Talab- Bhagwan Singh/ Madho Singh Gram - Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480784 — JGSA_2025-26-Khet Talab- Jagdish/ Purji Gram - Manki -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480834 — JGSA_2025-26-Khet Talab- Ramesh /Gangaram Gram - Manki -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480846 — JGSA_2025-26-Khet Talab- Narayaysen Gram - Manki -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480868 — JGSA_2025-26-Khet Talab- Laxminarayan/ Ramprasad Gram - Manki -GP- Manki | Approved | 199883.22 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480887 — JGSA_2025-26-Khet Talab- Ramababu/ Hindu Singh Gram - Manki -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480904 — JGSA_2025-26-Khet Talab- dilip / Nannulal Gram - Manki -GP- Manki | Approved | 199883.22 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480921 — JGSA_2025-26-Khet Talab- Pappulal / Chhitalal Gram - Manki -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480939 — JGSA_2025-26-Khet Talab- Hindu Singh/ Biram singh -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035480968 — JGSA_2025-26-Khet Talab- Bhagwan Singh/ Ful Singh Gram-Bhagora -GP- Manki | Approved | 0 | 0 | 2025-04-01
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726004062/IF/22012035613871 — Ek Bagiya Maa Ke Naam_Reena Bai_001/79-B_Village_Charkhedi_GP_Manki_2025-26 | Ongoing | 263510.03 | 36000 | 2025-12-19
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035662166 — Percolation tank Nirman_2025-26 Jujhar Singh s/o Amar Singh Village_Manki GP Manki | Approved | 198914.62 | 0 | 2026-01-26
BIAORA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1726004062/IF/22012035662216 — Percolation tank Nirman_2025-26 Kalu Singh s/o Beeram Singh Village_Manki GP Manki | Approved | 198914.62 | 0 | 2026-01-26
BIAORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004062/IF/IAY/204126 — Construction of IAY House -IAY REG. NO. MP-26-004-062-002/0008 | Approved | 27000 | 0 | 2015-12-18
BIAORA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004062/IF/IAY/3955292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149353644 | Approved | 27000 | 0 | 2022-05-04
BIAORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004062/IF/IAY/75256 — Construction of IAY House -IAY REG. NO. MP-26-004-062-003/009 | Approved | 27000 | 0 | 2015-12-17
BIAORA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1726004062/IF/IAY/79024 — Construction of IAY House -IAY REG. NO. MP-26-004-062-002/9A | Approved | 27000 | 0 | 2015-12-17
BIAORA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1726004062/RC/22012034551827 — Sudur Sadak_2020-21_Bhagora madan lal harijan ke Gher se Samudiyak Bhawan tak | Ongoing | 1491727.67 | 0 | 2020-12-22
BIAORA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1726004062/RC/22012034675062 — CC Rod nirman | New | 0 | 0 | 2024-04-16
BIAORA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1726004062/RC/22012034854154 — Sugam Samparkta Pariyojna 2026-27 Gram Manki se gram Bhagora Gram Panchayat Manki | Approved | 1998521.42 | 0 | 2026-06-05
BIAORA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1726004062/WC/22012035246659 — Earthen Bund Perculation Tank_Borawali Pahadi_2024-25_GP_Manki | Physically Completed | 1894712.51 | 21000 | 2025-02-01 | 2026-09-10
BIAORA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1726004062/WC/22012035292751 — JGSA-2025-26-Dugwell Recharge structure-Sarvjanik kup Bhagora nala samsan ke pass | Approved | 25899.46 | 0 | 2025-04-01
BIAORA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1726004062/WC/VB/22012035334135 — Staggered Countour Trench_2026-27_Baldi par- 1 Village Manki GP Manki | Approved | 201335.8 | 0 | 2026-07-27
BIAORA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1726004062/WC/VB/22012035334136 — Staggered Countour Trench_2026-27_Baldi par- 1 Village Manki GP Manki | Approved | 201335.8 | 0 | 2026-07-27
BIAORA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726004062/WH/22012034941422 — JGSA_Talab Renovation 2024-25_ khoyri wala maal gram bhagora | Approved | 0 | 0 | 2024-06-07
BIAORA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726004062/WH/22012034944874 — Talab Renovation Work_2025-26_Mangilal ke Khet ke Pass_Gram_Bhagora_GP_Manki | Physically Completed | 993051.27 | 8400 | 2025-06-07 | 2026-09-10
BIAORA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1726004062/WH/22012034944875 — Talab Renovation Work_2025-26_Kamal Singh ke khet ke Pass_GP_Manki | Physically Completed | 995179.13 | 10500 | 2025-07-06 | 2026-09-10