## Work List
Exported on: 2026-10-26 23:00:05
Filters applied:
Data source: VBGRAMG
District: RAJGARH
Block: All
Panchayat: SEDABAGH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SARANGPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1726005079/AV/22012034661529 — Shantidham Shamshan Ghat Nirman Gram Sedabagh | New | 0 | 0 | 2024-10-02
SARANGPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1726005079/IF/22012034581279 — Niji khet me Falodyan Devbai W/o Bhawarlal Saidabag | Ongoing | 144900 | 0 | 2020-07-16
SARANGPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/3335088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5005457 | Ongoing | 27000 | 0 | 2022-02-20
SARANGPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/3346036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5029394 | Ongoing | 27000 | 0 | 2023-08-18
SARANGPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/3450351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2420817 | Approved | 27000 | 0 | 2021-12-03
SARANGPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/3450355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2433404 | Approved | 27000 | 0 | 2021-12-03
SARANGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/4582633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119594556 | Ongoing | 27000 | 0 | 2024-12-29
SARANGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/4583955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119284184 | Ongoing | 27000 | 0 | 2024-12-29
SARANGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/4592557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121627584 | Ongoing | 27000 | 0 | 2024-12-29
SARANGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/4597144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122466668 | Ongoing | 27000 | 0 | 2024-12-29
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/4909001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122790702 | Ongoing | 27000 | 0 | 2025-05-17
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/4909684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118799339 | Ongoing | 27000 | 0 | 2025-06-07
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/5160142 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123838554 | Ongoing | 27000 | 0 | 2025-06-22
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/5184538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123853649 | Ongoing | 27000 | 0 | 2025-05-17
SARANGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/5595002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119284356 | Approved | 27000 | 0 | 2024-09-16
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/5721953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121631085 | Approved | 27000 | 0 | 2025-05-12
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6073441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115872636 | Ongoing | 27000 | 10500 | 2026-06-02
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6076671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117813791 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6076726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117837832 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6076745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117844725 | Ongoing | 27000 | 8400 | 2026-07-23
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6077709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118289657 | Ongoing | 27000 | 12600 | 2026-06-24
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6077740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118298527 | Ongoing | 27000 | 10500 | 2026-07-21
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6078163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118516969 | Ongoing | 27000 | 21000 | 2026-07-21
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6078165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118516983 | Ongoing | 27000 | 21000 | 2026-06-24
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6078908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119284506 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6081322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121613189 | Approved | 27000 | 0 | 2026-02-17
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6081421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121662721 | Ongoing | 27000 | 8400 | 2026-07-23
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6081428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121665895 | Ongoing | 27000 | 0 | 2026-07-23
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6081452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121683122 | Ongoing | 27000 | 8400 | 2026-07-23
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6081476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121702654 | Ongoing | 27000 | 8400 | 2026-07-23
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6082247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122464244 | Approved | 27000 | 0 | 2026-02-17
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6082249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122465166 | Approved | 27000 | 0 | 2026-02-17
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6082253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122466149 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6082256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122467458 | Approved | 27000 | 0 | 2026-02-17
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6082762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122790032 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6088255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126556252 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6090760 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127960545 | Ongoing | 27000 | 25200 | 2026-06-24
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6090774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127968631 | Ongoing | 27000 | 21000 | 2026-06-02
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6091365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128558017 | Ongoing | 27000 | 23100 | 2026-06-17
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6091378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128563929 | Ongoing | 27000 | 8400 | 2026-06-24
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6185545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123857195 | Approved | 27000 | 0 | 2026-03-05
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6192185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118296644 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6193279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118291545 | Ongoing | 27000 | 6300 | 2026-08-04
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6196678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123855427 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6333693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117847878 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6333961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120247087 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6334291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123833724 | Approved | 27000 | 0 | 2026-05-20
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6334737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118324104 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6334893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121678983 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6334924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121646103 | Approved | 27000 | 0 | 2026-02-17
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6334960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117854585 | Ongoing | 27000 | 0 | 2026-10-13
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6335149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123834932 | Approved | 27000 | 0 | 2026-05-20
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6335315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123022213 | Approved | 27000 | 0 | 2026-04-25
SARANGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6361072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839380 | Approved | 27000 | 0 | 2026-07-31
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6361344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115872738 | Approved | 27000 | 0 | 2026-02-09
SARANGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/6362999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123836888 | Approved | 27000 | 0 | 2026-02-17
SARANGPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1726005079/IF/IAY/650458 — Construction of IAY House -IAY REG. NO. MP3237644 | Approved | 27000 | 0 | 2017-02-20
SARANGPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1726005079/RC/22012034541062 — Khet Sadak_2020-21_Saidabag_PM Road se Tajkaran ke khet taka | Ongoing | 1036754.93 | 0 | 2021-06-15
SARANGPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1726005079/RC/22012034542321 — 15 Vith CC Road Main Road se Anganwadi Bhwan and School tak and Raisingh ke makan se Pramnarayan ke | Ongoing | 33000 | 0 | 2021-05-23
SARANGPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1726005079/RC/22012034644811 — 15 Vith CC Road Shala Bhawan se Shivnarayan ke makan tak Hajipur | Physically Completed | 81000 | 0 | 2023-07-25 | 2026-09-16
SARANGPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1726005079/RC/VB/22012034854289 — Sugam Samparkta Pariyojna 2026-27 Panchayat Bhawan Saidabag se Hajipur Tak GP Saidabag | Ongoing | 1994603.62 | 13500 | 2026-08-25
SARANGPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1726005079/WC/22012035266000 — JGSA_Dugwell Recharge_2025_Nirmal Neer Kup Goya ke Raste par_GP Saidabag | Approved | 0 | 0 | 2025-04-14