## Work List
Exported on: 2026-09-14 06:03:46
Filters applied:
Data source: VBGRAMG
District: VIDISHA
Block: All
Panchayat: GHOSUATALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SIRONJ | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1727002036/AV/22012034622962 — कब्रिस्‍तान शेड निर्माण ग्राम रजाखेड़ी | Ongoing | 247583.97 | 0 | 2023-10-09
SIRONJ | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1727002036/AV/22012034623436 — शांतिधाम निर्माण ग्राम रजाखेडी | Ongoing | 198566.47 | 0 | 2022-11-21
SIRONJ | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1727002036/AV/22012034623438 — शांतिधाम निर्माण ग्राम रायखेडी | Ongoing | 196953.1 | 0 | 2022-11-21
SIRONJ | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1727002036/AV/22012034667641 — कब्रिस्‍तान शेड निर्माण ग्राम कजरीमडवासा | New | 0 | 0 | 2025-08-15
SIRONJ | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1727002036/IF/22012034500212 — व़क्षारोपण सुरेश/रघुनाथ कजरीमडवासा | Ongoing | 136000 | 0 | 2019-10-14
SIRONJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1727002036/IF/22012034923966 — वृक्षारोपण अर्जुन सिंह कुशवाह / भैयालाल ग्राम कजरी मड़वासा | Ongoing | 136000 | 0 | 2021-12-06
SIRONJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727002036/IF/22012035256628 — वृक्षारोपण निर्माण अनवर खॉ / हमीत खॉ ग्राम कजरीमडवासा | Approved | 0 | 0 | 2024-08-15
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727002036/IF/22012035632913 — एक बगिया मॉ के नाम वृक्षारोपण राजबाई /राजू अहिरवार ग्राम रजाखेडी | Ongoing | 277543.62 | 0 | 2025-10-26
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727002036/IF/22012035632926 — एक बगिया मॉ के नाम वृक्षारोपण रानीबाई / राकेश विश्‍वकर्मा ग्राम घोसुआताल | Ongoing | 277543.62 | 0 | 2025-10-26
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727002036/IF/22012035645020 — एक बगिया मॉ के नाम वृक्षारोपण राजबाई/लालाराम ग्राम रजाखेडी | Ongoing | 277543.62 | 0 | 2025-12-24
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002036/IF/22012035645352 — खेत तालाब निर्माण जीवन/कलुआ ग्राम रजाखेडी | Approved | 199805.15 | 0 | 2025-10-02
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002036/IF/22012035645354 — खेत तालाब निर्माण रामदयाल /कन्‍हैयालाल ग्राम रजाखेडी | Approved | 199805.15 | 0 | 2025-10-02
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002036/IF/22012035645356 — खेत तालाब निर्माण जहीरखॉ/ गप्‍पू खॉ ग्राम रजाखेडी | Approved | 199805.15 | 0 | 2025-10-02
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727002036/IF/22012035645527 — खेत तालाब निर्माण कारणसिंह/ कंदईलाल ग्राम रजाखेडी | Approved | 200406.81 | 0 | 2025-10-02
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727002036/IF/22012035652683 — एक बगिया मॉ के नाम वृक्षारोपण राशिबाई / राकेश बघेल ग्राम रजाखेडी | Ongoing | 277543.62 | 0 | 2026-03-26
SIRONJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/2505336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4414580 | Ongoing | 27000 | 0 | 2020-05-18
SIRONJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/2506334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4427977 | Ongoing | 27000 | 0 | 2020-05-18
SIRONJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/3386294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2296068 | Ongoing | 27000 | 0 | 2021-12-20
SIRONJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/3413464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4738926 | Ongoing | 27000 | 0 | 2021-12-20
SIRONJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/3419023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4915121 | Ongoing | 27000 | 0 | 2021-12-20
SIRONJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/3916339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127811247 | Ongoing | 27000 | 0 | 2022-05-30
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/4974440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123062616 | Ongoing | 27000 | 0 | 2025-04-07
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/5417025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129546871 | Ongoing | 27000 | 0 | 2025-05-12
SIRONJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/5635016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127148422 | Ongoing | 27000 | 0 | 2025-07-24
SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/5914594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127809954 | Ongoing | 27000 | 3600 | 2026-04-23
SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/5923440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125103579 | Ongoing | 27000 | 3600 | 2026-04-23
SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/5924788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122566493 | Ongoing | 27000 | 0 | 2026-05-18
SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/6083289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123220455 | Ongoing | 27000 | 3600 | 2026-05-18
SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/6089644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127184219 | Ongoing | 27000 | 3600 | 2026-04-23
SIRONJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727002036/IF/IAY/6118857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127194133 | Ongoing | 27000 | 3600 | 2026-04-23
SIRONJ | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1727002036/RS/22012034624502 — नाली निर्माण 15वित्‍त रामलाल के घर से ओमकार के घर तक रजाखेडी | Ongoing | 27650 | 0 | 2021-12-04
SIRONJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1727002036/WC/22012035279071 — Dugwell Recharge chhatar singh ke ghar ke pas koop gram kajri madwasa | Approved | 25899.46 | 0 | 2025-04-14
SIRONJ | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1727002036/WC/GIS/32407 — स्‍टाप डेम निर्माण कजरीमडवासा नदी पर ग्राम कजरीमडवासा | Ongoing | 1489419.7 | 0 | 2023-03-07
SIRONJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1727002036/WC/GIS/35346 — निर्मल नीर निर्माण शांतिधाम के पास ग्राम रायखेड़ी | Ongoing | 499957.26 | 0 | 2023-10-09
SIRONJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1727002036/WC/GIS/35347 — निर्मल नीर निर्माण मेन रोड के पास ग्राम रजाखेड़ी | Ongoing | 499473.64 | 0 | 2023-10-09