## Work List
Exported on: 2026-10-24 06:44:48
Filters applied:
Data source: VBGRAMG
District: VIDISHA
Block: All
Panchayat: NEGMA PIPARIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BASODA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1727004040/DP/22012034564028 — VirchaRopan Work Amrat Sarower Talab ke Pass Gram Kathari GP Negmapipariya | Ongoing | 408000 | 0 | 2022-09-12
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1727004040/IF/22012034450747 — दिल्लू हरिजन कूप निर्माण ग्राम नगमा पिपरिया | Ongoing | 200000 | 0 | 2019-12-06
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004040/IF/22012034571313 — भूमि सुधार शंकर अहिरवार नगमा पिपरिया | Ongoing | 70444.57 | 0 | 2020-06-19
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004040/IF/22012034572393 — bhumi sudhar ghuri ahirwar nrgma piperiya | Ongoing | 70444.57 | 0 | 2020-06-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1727004040/IF/22012035206952 — Koop Nirman Vijay Singh Meena ke khet me GP Negmapipariya | Ongoing | 247414.33 | 0 | 2024-06-29
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/4491415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152036289 | Ongoing | 27000 | 0 | 2024-08-11
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/4491417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152036342 | Ongoing | 27000 | 0 | 2024-08-21
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/4704165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121017143 | Ongoing | 27000 | 0 | 2025-01-03
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/4728235 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889294 | Ongoing | 27000 | 1800 | 2024-12-27
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/4762619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121016031 | Approved | 27000 | 0 | 2024-09-22
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/4881285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817645 | Ongoing | 27000 | 0 | 2025-12-07
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5116008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817744 | Physically Completed | 23490 | 0 | 2025-03-04 | 2026-07-12
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5118745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126829566 | Approved | 27000 | 0 | 2025-02-07
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5124239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119745728 | Physically Completed | 23490 | 0 | 2025-02-14 | 2026-07-12
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5124240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119745782 | Approved | 27000 | 0 | 2025-03-11
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5124241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119745872 | Ongoing | 27000 | 0 | 2026-05-09
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5126310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448666 | Ongoing | 27000 | 0 | 2025-12-07
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5126455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123389970 | Approved | 27000 | 0 | 2025-03-17
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5126547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149888983 | Approved | 27000 | 0 | 2025-03-04
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5126548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889008 | Approved | 27000 | 0 | 2025-03-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5126550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889058 | Ongoing | 27000 | 9300 | 2026-09-10
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5129594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121015000 | Approved | 27000 | 0 | 2025-02-20
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5130946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123557466 | Approved | 27000 | 0 | 2025-03-17
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5132132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121015887 | Approved | 27000 | 0 | 2025-02-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5133581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817560 | Ongoing | 27000 | 0 | 2025-12-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5133582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817578 | Ongoing | 27000 | 0 | 2025-12-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5437291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746802 | Approved | 27000 | 0 | 2025-04-02
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5437292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746835 | Ongoing | 27000 | 0 | 2025-12-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5437293 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746864 | Ongoing | 27000 | 0 | 2025-12-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5438176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889502 | Ongoing | 27000 | 8100 | 2025-12-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5438836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121020826 | Approved | 27000 | 0 | 2025-04-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5439102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123421896 | Ongoing | 27000 | 12600 | 2025-08-15
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5439122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123269001 | Physically Completed | 27000 | 0 | 2025-04-02 | 2026-08-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5600779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121017229 | Approved | 27000 | 0 | 2025-04-02
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5600881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119747023 | Physically Completed | 23490 | 0 | 2025-12-07 | 2026-07-12
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5640952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123423195 | Approved | 27000 | 0 | 2025-05-10
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5643917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448601 | Approved | 27000 | 0 | 2025-05-20
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5698739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817758 | Physically Completed | 23490 | 0 | 2025-02-23 | 2026-07-12
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5699242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889327 | Ongoing | 27000 | 9000 | 2025-12-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5699243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889487 | Approved | 27000 | 0 | 2025-04-02
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5699417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123390561 | Ongoing | 27000 | 0 | 2025-08-15
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5699533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121017623 | Ongoing | 27000 | 9900 | 2025-12-07
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/5700466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123389460 | Approved | 27000 | 0 | 2025-03-04
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6128842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123423836 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6128891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448675 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6130005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126845853 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6130212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126856010 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6136944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123395067 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6136945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123395697 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6145657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123387583 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6149209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817441 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6149210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817472 | Approved | 27000 | 0 | 2026-03-13
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6149211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817509 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6149213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817685 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6149214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817696 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6154224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746302 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6160862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126860462 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6166558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127129514 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6169664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130184862 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6169907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889176 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6170458 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889436 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6255331 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448701 | Approved | 27000 | 0 | 2026-04-02
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6255332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448725 | Approved | 27000 | 0 | 2026-03-24
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6256911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746205 | Approved | 27000 | 0 | 2026-02-26
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6256912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746400 | Approved | 27000 | 0 | 2026-04-22
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6286070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448637 | Approved | 27000 | 0 | 2026-04-02
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6298606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817673 | Approved | 27000 | 0 | 2026-04-22
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6323716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889161 | Approved | 27000 | 0 | 2026-05-18
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6331908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126939429 | Approved | 27000 | 0 | 2026-06-24
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6332874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119745968 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6345203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126837319 | Approved | 27000 | 0 | 2026-06-24
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6346453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817725 | Approved | 27000 | 0 | 2026-07-06
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6346660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117448686 | Approved | 27000 | 0 | 2026-07-08
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6346748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889528 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123394577 | Approved | 27000 | 0 | 2026-04-02
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746041 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817659 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889240 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130186288 | Approved | 27000 | 0 | 2026-03-13
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746446 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115817543 | Approved | 27000 | 0 | 2026-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126944349 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130185010 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119746601 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123425696 | Approved | 27000 | 0 | 2026-04-22
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6369958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126951055 | Approved | 27000 | 0 | 2026-03-24
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6377053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123396351 | Approved | 27000 | 0 | 2026-04-02
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6377338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149889194 | Approved | 27000 | 0 | 2026-08-24
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6377999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123426904 | Approved | 27000 | 0 | 2026-08-27
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/6379092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123429279 | Approved | 27000 | 0 | 2026-08-27
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1727004040/IF/IAY/917978 — Construction of IAY House -IAY REG. NO. MP2390726 | Approved | 27000 | 0 | 2018-10-22
BASODA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Raising of Fodder Cultivation for Community | Grass Land Development | 1727004040/LD/22012034530900 — Charagah Nirman Goshala Gram Negmapipariya | Physically Completed | 792213.45 | 0 | 2021-01-06 | 2026-07-14
BASODA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727004040/RC/22012034838887 — CC Road Nirman Gudda ke ghar se Hanuman Mandir ki or GP Negmapipariya | Ongoing | 49000 | 0 | 2025-07-06
BASODA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727004040/RC/22012034838890 — CC Road Nirman Shamshan Ghat ke pass GP NegmaPipariya | Ongoing | 20000 | 0 | 2025-07-06
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727004040/RC/22012034838893 — CC Road Nirman Harisingh ke ghar se Lalaram ke ghar tak GP NegmaPipariya | Approved | 19000 | 0 | 2024-10-02
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1727004040/RC/22012034838896 — CC Road Nirman Lkhatpat se Matabai and Bhola ke ghar se Purani cc tak GP NegmaPipariya | Approved | 12000 | 0 | 2024-10-02
BASODA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1727004040/RC/22012034840873 — Graval Road Nirman NegmaPipariya se Goushala ki or GP Negampipariya | Ongoing | 1417000 | 0 | 2025-05-24
BASODA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1727004040/WC/22012034656721 — Community Form Pond constr. Charagah me Gram Negma CTR | Ongoing | 337715.44 | 0 | 2022-01-12