## Work List
Exported on: 2026-09-06 12:49:51
Filters applied:
Data source: VBGRAMG
District: VIDISHA
Block: All
Panchayat: HAMIDAPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1727004044/DP/22012034484533 — nirmal neer koop gram hamidpur | Ongoing | 541990.78 | 0 | 2020-01-22
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727004044/IF/22012034501420 — koop nirman gyarsa | Ongoing | 234458.57 | 0 | 2020-02-10
BASODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1727004044/IF/22012035364053 — Recharge Fit Surendra k pass gp hamidpur | New | 0 | 0 | 2025-04-18
BASODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1727004044/IF/22012035364506 — Recharge Fit Bheem singh k koop k pass gp hamidpur | Approved | 25899.46 | 0 | 2025-04-18
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004044/IF/22012035387075 — khet talab nirman amit/nandkishor lodhi hamidpur | New | 0 | 0 | 2025-04-14
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727004044/IF/22012035590722 — Ek Bagiya Maa KE Naam Ayodhya Bai | Ongoing | 269386.03 | 14400 | 2025-09-08
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/4753026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667726 | Approved | 27000 | 0 | 2024-09-22
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/4790620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341363 | Physically Completed | 23490 | 0 | 2025-08-13 | 2026-07-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/4973384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667096 | Ongoing | 27000 | 0 | 2026-02-23
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/4973386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667765 | Ongoing | 27000 | 2100 | 2025-08-16
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/4973390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117668060 | Completed | 23490 | 0 | 2025-09-24 | 2026-07-22
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5214548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341427 | Ongoing | 27000 | 0 | 2026-02-22
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5224711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667784 | Approved | 27000 | 0 | 2025-03-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5639135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667713 | Physically Completed | 23490 | 0 | 2025-08-14 | 2026-07-31
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5698034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141340923 | Physically Completed | 23490 | 0 | 2025-08-20 | 2026-07-31
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5698993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667654 | Physically Completed | 27000 | 2100 | 2025-08-13 | 2026-09-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5698994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117668014 | Ongoing | 27000 | 4200 | 2025-08-16
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117873736 | Physically Completed | 27000 | 900 | 2026-02-23 | 2026-09-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341051 | Physically Completed | 27000 | 3600 | 2025-08-07 | 2026-09-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341246 | Physically Completed | 27000 | 4200 | 2025-08-20 | 2026-09-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341263 | Physically Completed | 27000 | 3900 | 2025-08-20 | 2026-09-03
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122431169 | Physically Completed | 23490 | 0 | 2025-08-21 | 2026-07-26
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667818 | Physically Completed | 23490 | 0 | 2025-07-19 | 2026-07-31
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5699882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117878843 | Physically Completed | 23490 | 0 | 2025-08-13 | 2026-07-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5700248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879997 | Physically Completed | 23490 | 0 | 2025-08-20 | 2026-07-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5725306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141340746 | Physically Completed | 23490 | 0 | 2025-09-16 | 2026-07-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5733652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117878886 | Ongoing | 27000 | 4200 | 2025-08-27
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5991460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141340721 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5991461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141340786 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5991932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667067 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5991933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667106 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5991934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667153 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5992096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117878906 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5992097 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117878964 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5993333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879479 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5993334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879515 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5993336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879791 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5993845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122449013 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5994033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879248 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5994034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879277 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5996110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125783137 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879550 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879591 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879921 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117873752 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879003 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879042 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879073 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117879130 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667421 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667846 | Approved | 27000 | 0 | 2026-02-17
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117668076 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117668138 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5997744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117668161 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5998093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667883 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5998094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117667966 | Ongoing | 27000 | 0 | 2026-08-16
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5998368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341137 | Ongoing | 27000 | 4200 | 2026-07-30
BASODA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/5998369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141341278 | Ongoing | 27000 | 0 | 2026-08-20
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004044/IF/IAY/944600 — Construction of IAY House -IAY REG. NO. MP2907663 | Ongoing | 27000 | 0 | 2017-05-19
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004044/RC/22012034825254 — CC Road Nirman Udayram Lodhi ke ghar se Mata Mandir ki or GP Hamidpur | Approved | 24000 | 0 | 2024-06-08
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004044/RC/22012034833959 — CC Road Nirman Ganeshram Sharma ke ghar se Midile School tak GP Hamidpur | Approved | 38000 | 0 | 2024-06-08
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004044/RC/22012034833960 — CC Road Nirman Chakkulal ke ghar se Ghanram ke ghar ki or GP Hamidpur | Approved | 25000 | 0 | 2024-08-16
BASODA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1727004044/WC/22012034658016 — CTR khet Talab Nirmaan gp hamidpur | Ongoing | 337715.44 | 0 | 2022-05-03