## Work List
Exported on: 2026-10-11 20:28:00
Filters applied:
Data source: MGNREGA
District: VIDISHA
Block: All
Panchayat: KAKARAWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BASODA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004051/IF/9993677134 — indira avas bhuri bai /moti singh kakrawada | Completed | 14310 | 14232 | 2015-09-28 | 2017-06-01
BASODA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1727004062/AV/22012034304146 — Anganwaadi Bhavan Nirman GP Kakrawada | Completed | 180000 | 175362 | 2017-05-18 | 2020-10-27
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1727004062/AV/22012034390125 — पंचायत भवन निर्माण ग्राम पंचायत ककरावदा | Completed | 579000 | 548733 | 2018-09-29 | 2026-05-11
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1727004062/AV/22012034390127 — आंगनवाडी भवन निर्माण ग्राम पंचायत ककरावदा 1 | Physically Completed | 180000 | 179232 | 2018-09-29 | 2026-06-27
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1727004062/AV/22012034469117 — shanti daam adiwashi tapra | Completed | 192447.03 | 169769.76 | 2019-12-12 | 2026-05-11
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1727004062/AV/22012034657352 — Puliya Nirman Sathiya wale raste per Nale GP Kakrawada | Completed | 29000 | 26209.26 | 2024-07-02 | 2026-05-11
BASODA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1727004062/DP/18 — व़क्षारोपण नर्सरी में ग्राम पंचायत ककरावदा | Completed | 315000 | 311041.46 | 2009-08-07 | 2011-08-06
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1727004062/DP/22012034482346 — nirmal nir kakrawada | Closed | 0 | 0 | 2019-08-15
BASODA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1727004062/DP/22012034603514 — vasudha vatika bandhan sarvjanik samudayik parisar gram kakrawbda | Closed | 0 | 0 | 2023-06-23
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1727004062/IF/22012034309561 — khet talab lalaram ramnath kakrawda | Closed | 32000 | 0 | 2016-04-02
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1727004062/IF/22012034309571 — khet talab shibbu kallu ahirwar kakkrawda | Closed | 32000 | 0 | 2016-04-02
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1727004062/IF/22012034352274 — braksha ropan gram kakarawada | Completed | 335000 | 29122 | 2017-06-22 | 2019-11-10
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/22012034566774 — samtalikaran RAJAN ke khet me | Completed | 86616.75 | 60420 | 2020-06-11 | 2020-07-31
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/22012034566779 — samtalikaran sunil ke khet me | Completed | 86616.75 | 55860 | 2020-06-11 | 2020-07-31
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/22012034568119 — khet levling naval jalam | Completed | 86616.75 | 66120 | 2020-06-11 | 2020-07-31
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/22012034568122 — khet levlingshibbu/kallu | Completed | 86616.75 | 61560 | 2020-06-11 | 2020-07-31
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/22012034568124 — khet levling lalaram/ramnath | Completed | 86616.75 | 54720 | 2020-06-11 | 2020-07-31
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/22012034574679 — bhumi sudhar ajuddi bai /ratan singh gp kakarawada | Closed | 0 | 0 | 2020-04-05
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004062/IF/22012034656597 — FARM POND | Closed | 0 | 0 | 2021-01-26
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004062/IF/22012034667414 — farm pond alkhananda kakarawada | Completed | 332962.02 | 265743 | 2021-03-24 | 2022-05-19
BASODA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004062/IF/22012034730282 — khet talab nirman jitendra singh kakarawada | Completed | 110516.06 | 72954 | 2021-05-19 | 2026-05-04
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004062/IF/22012034993558 — khet talab ankit ke khet me | Closed | 116607.32 | 0 | 2022-04-14
BASODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727004062/IF/22012035357968 — Dugweel Racharge Rajan/budhha ke kup ke pass gp Kakarawada | Approved | 23995.18 | 0 | 2025-04-14
BASODA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727004062/IF/22012035358059 — Dugweel Racharge Shibbu/kallu ke kup ke pass gp Kakarawada | Approved | 23995.18 | 0 | 2025-04-14
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004062/IF/22012035374984 — Khet talab sodan singh / Bharat Singh kakrawada | Completed | 199203.54 | 159361.92 | 2025-05-22 | 2026-05-11
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1727004062/IF/22012035375023 — Khet talab vijay Singh /parasram kakrawada | Approved | 199203.54 | 0 | 2025-04-14
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1727004062/IF/22012035636314 — Ek Bagiya Maa ke naam Gaytri Devi Raghuwanshi/Karan raghuwanshi | Approved | 0 | 0 | 2025-10-02
BASODA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727004062/IF/92 — कूप निर्माण ि‍शब्‍बू, कल्‍लू, गणेश, हल्‍कू ग्राम प | Completed | 192000 | 133256 | 2009-02-20 | 2012-03-31
BASODA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727004062/IF/94 — कूप निर्माण राजन/बुदधा ग्राम पंचायत ककरावदा | Completed | 192000 | 129031 | 2009-02-23 | 2012-03-31
BASODA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/9993677133 — indira avas bhamri / shriram kakrawada | Completed | 14310 | 13609 | 2015-09-28 | 2017-06-01
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1727004062/IF/9993715393 — med bandhan nirman | Closed | 0 | 0 | 2016-04-14
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727004062/IF/9993719154 — Koop Nirman | Closed | 0 | 0 | 2016-04-14
BASODA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/101746 — Construction of IAY House -IAY REG. NO. MP-27-004-062-001/12018 | Approved | 23490 | 0 | 2015-09-22
BASODA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/101747 — Construction of IAY House -IAY REG. NO. MP-27-004-062-001/12076 | Approved | 23490 | 0 | 2015-09-22
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1042098 — Construction of IAY House -IAY REG. NO. MP3123424 | Completed | 15480 | 15480 | 2017-07-10 | 2017-12-30
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1042138 — Construction of IAY House -IAY REG. NO. MP3127041 | Completed | 15480 | 15480 | 2017-07-10 | 2017-12-30
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1043233 — Construction of IAY House -IAY REG. NO. MP3203957 | Completed | 15480 | 15308 | 2017-07-10 | 2018-06-05
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1103238 — Construction of IAY House -IAY REG. NO. MP3054134 | Completed | 15480 | 15480 | 2017-09-28 | 2018-03-31
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1103240 — Construction of IAY House -IAY REG. NO. MP3058331 | Completed | 15480 | 15480 | 2017-07-10 | 2017-12-30
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1213427 — Construction of IAY House -IAY REG. NO. MP3138825 | Completed | 15480 | 15660 | 2018-07-23 | 2018-11-05
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1214667 — Construction of IAY House -IAY REG. NO. MP3137919 | Completed | 15480 | 15660 | 2018-06-19 | 2018-10-03
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1231285 — Construction of IAY House -IAY REG. NO. MP3128465 | Completed | 15480 | 15660 | 2018-07-23 | 2018-12-19
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1346016 — Construction of IAY House -IAY REG. NO. MP3666695 | Completed | 15480 | 15660 | 2018-07-23 | 2018-11-05
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1387250 — Construction of IAY House -IAY REG. NO. MP1446491 | Completed | 15480 | 15660 | 2018-06-11 | 2019-01-24
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1425570 — Construction of IAY House -IAY REG. NO. MP2953425 | Completed | 15480 | 15660 | 2018-08-20 | 2019-01-01
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1430704 — Construction of IAY House -IAY REG. NO. MP3125094 | Completed | 15480 | 15660 | 2018-06-19 | 2019-01-24
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1432977 — Construction of IAY House -IAY REG. NO. MP3198998 | Completed | 15480 | 15660 | 2018-08-20 | 2018-12-19
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1540532 — Construction of IAY House -IAY REG. NO. MP3941125 | Approved | 23490 | 0 | 2018-03-10
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1542891 — Construction of IAY House -IAY REG. NO. MP3968463 | Completed | 15480 | 15660 | 2018-08-20 | 2019-01-09
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1543352 — Construction of IAY House -IAY REG. NO. MP3978729 | Approved | 23490 | 0 | 2018-03-10
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1773154 — Construction of IAY House -IAY REG. NO. MP2935337 | Completed | 15660 | 15660 | 2018-07-23 | 2018-12-12
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1773168 — Construction of IAY House -IAY REG. NO. MP2942447 | Completed | 15660 | 15660 | 2018-07-23 | 2019-01-09
BASODA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/1773411 — Construction of IAY House -IAY REG. NO. MP3011311 | Completed | 15660 | 15660 | 2018-07-23 | 2018-12-03
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2271107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4361950 | Completed | 15840 | 15840 | 2019-10-16 | 2020-01-12
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2271144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4438304 | Completed | 15840 | 15840 | 2019-10-16 | 2020-01-23
BASODA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2271411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5333098 | Completed | 15840 | 15840 | 2019-10-08 | 2020-01-12
BASODA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2807769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4332078 | Completed | 17100 | 17028 | 2021-04-22 | 2022-08-31
BASODA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2810383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4158833 | Completed | 17100 | 17177 | 2021-06-10 | 2021-11-29
BASODA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2823124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5310848 | Completed | 17100 | 17370 | 2021-04-22 | 2021-11-26
BASODA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/2825190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5426119 | Completed | 17100 | 16984 | 2021-05-13 | 2021-12-11
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/327558 — Construction of IAY House -IAY REG. NO. MP1085724 | Completed | 15030 | 15046 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/339161 — Construction of IAY House -IAY REG. NO. MP1108219 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/339165 — Construction of IAY House -IAY REG. NO. MP1108226 | Completed | 15030 | 15405 | 2017-03-06 | 2017-10-20
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/352969 — Construction of IAY House -IAY REG. NO. MP1134250 | Completed | 15030 | 15516 | 2017-07-10 | 2018-06-05
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/352970 — Construction of IAY House -IAY REG. NO. MP1134252 | Completed | 15030 | 15046 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/354463 — Construction of IAY House -IAY REG. NO. MP1139227 | Completed | 15030 | 15390 | 2017-03-06 | 2017-12-01
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/354476 — Construction of IAY House -IAY REG. NO. MP1139253 | Completed | 15030 | 15390 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/355409 — Construction of IAY House -IAY REG. NO. MP1140909 | Completed | 15030 | 15390 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/355424 — Construction of IAY House -IAY REG. NO. MP1140944 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/355666 — Construction of IAY House -IAY REG. NO. MP1141318 | Completed | 15030 | 15390 | 2017-03-06 | 2017-12-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/355678 — Construction of IAY House -IAY REG. NO. MP1141338 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/358486 — Construction of IAY House -IAY REG. NO. MP1146169 | Completed | 15030 | 15390 | 2017-03-06 | 2017-11-03
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/358510 — Construction of IAY House -IAY REG. NO. MP1146201 | Completed | 15030 | 15150 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/358572 — Construction of IAY House -IAY REG. NO. MP1146272 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/359006 — Construction of IAY House -IAY REG. NO. MP1146985 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/361273 — Construction of IAY House -IAY REG. NO. MP1150901 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/361279 — Construction of IAY House -IAY REG. NO. MP1150908 | Completed | 15030 | 15390 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/361318 — Construction of IAY House -IAY REG. NO. MP1150968 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/365741 — Construction of IAY House -IAY REG. NO. MP1158188 | Completed | 15030 | 15046 | 2017-03-06 | 2018-01-29
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3661940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115903769 | Completed | 18360 | 18360 | 2022-06-01 | 2023-02-03
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3661943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115904446 | Completed | 18360 | 18360 | 2022-06-01 | 2023-02-03
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3661944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115904588 | Completed | 18360 | 18241 | 2022-06-01 | 2023-08-22
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3662178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116202661 | Completed | 18360 | 18360 | 2022-06-01 | 2023-02-03
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3698508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115904797 | Completed | 18360 | 18241 | 2022-06-01 | 2023-08-22
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3702233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105473153 | Completed | 18360 | 18360 | 2022-06-01 | 2022-10-21
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3832021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117672846 | Approved | 23490 | 0 | 2022-04-25
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/387631 — Construction of IAY House -IAY REG. NO. MP1179642 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/387653 — Construction of IAY House -IAY REG. NO. MP1179730 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/387889 — Construction of IAY House -IAY REG. NO. MP1180713 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/387892 — Construction of IAY House -IAY REG. NO. MP1180725 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/387959 — Construction of IAY House -IAY REG. NO. MP1181058 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/387968 — Construction of IAY House -IAY REG. NO. MP1181091 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/389297 — Construction of IAY House -IAY REG. NO. MP1186362 | Completed | 15030 | 15046 | 2017-03-06 | 2018-01-11
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/3972968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115903705 | Completed | 18360 | 18360 | 2022-06-01 | 2023-02-03
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/397787 — Construction of IAY House -IAY REG. NO. MP1206880 | Completed | 15030 | 15480 | 2017-05-11 | 2018-01-11
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/407450 — Construction of IAY House -IAY REG. NO. MP1241634 | Completed | 15030 | 15220 | 2017-05-11 | 2018-12-28
BASODA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4191664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116782092 | Completed | 18360 | 18360 | 2022-06-30 | 2022-09-27
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/437251 — Construction of IAY House -IAY REG. NO. MP1446904 | Completed | 15030 | 15480 | 2017-04-09 | 2017-12-10
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4458345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151834648 | Completed | 19890 | 19845 | 2024-03-01 | 2026-02-04
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4458814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936392 | Ongoing | 19890 | 19656 | 2024-03-01
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4458819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936541 | Ongoing | 19890 | 19296 | 2024-03-01
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4461049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151930795 | Ongoing | 19890 | 18558 | 2024-03-01
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4461111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013678 | Completed | 19890 | 19773 | 2024-03-01 | 2024-11-19
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4461112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013684 | Completed | 19890 | 19818 | 2024-03-01 | 2026-02-04
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4461113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013690 | Completed | 19890 | 19863 | 2024-03-01 | 2026-02-04
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4461114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013691 | Ongoing | 19890 | 19404 | 2024-03-01
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4468893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012537 | Ongoing | 19890 | 19458 | 2024-05-29
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4468894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152012585 | Ongoing | 19890 | 19551 | 2024-03-01
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4468902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013681 | Ongoing | 19890 | 19560 | 2024-03-01
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4468903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013687 | Completed | 19890 | 19773 | 2024-05-04 | 2026-02-04
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4468904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013689 | Ongoing | 19890 | 19683 | 2024-04-03
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4468961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152019755 | Ongoing | 19890 | 19422 | 2024-04-03
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4469135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151930672 | Ongoing | 19890 | 17130 | 2024-03-01
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4469136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151930729 | Ongoing | 19890 | 19677 | 2024-03-01
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4469309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936243 | Completed | 19890 | 19731 | 2024-03-01 | 2026-02-04
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4469310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936289 | Completed | 19890 | 19794 | 2024-03-01 | 2024-11-19
BASODA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4469311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936451 | Ongoing | 19890 | 19254 | 2024-03-01
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4470282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936485 | Ongoing | 19890 | 19458 | 2024-04-03
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4471858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936352 | Ongoing | 19890 | 18720 | 2024-04-03
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4485418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151936589 | Ongoing | 19890 | 19440 | 2024-04-03
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4560969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114993531 | Completed | 21870 | 21870 | 2025-01-14 | 2025-03-24
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4564877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115969264 | Completed | 23490 | 21717 | 2025-01-14 | 2026-01-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4576576 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734083 | Completed | 23490 | 21708 | 2025-01-14 | 2026-01-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4640122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131587079 | Completed | 23490 | 21708 | 2025-01-30 | 2025-08-21
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/465050 — Construction of IAY House -IAY REG. NO. MP1760562 | Completed | 15030 | 15480 | 2017-09-28 | 2017-12-29
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/467093 — Construction of IAY House -IAY REG. NO. MP1784925 | Completed | 15030 | 15480 | 2017-05-22 | 2018-01-11
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4693907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116434330 | Ongoing | 23490 | 17010 | 2025-02-05
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/469884 — Construction of IAY House -IAY REG. NO. MP1826786 | Completed | 15030 | 15480 | 2017-05-11 | 2018-01-11
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4705830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123048841 | Completed | 23490 | 21717 | 2025-01-29 | 2026-01-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4786625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131226584 | Completed | 21870 | 21870 | 2024-12-31 | 2025-03-24
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4808159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152013692 | Completed | 23490 | 21708 | 2025-03-06 | 2026-01-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4815354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066001 | Completed | 23490 | 21834 | 2025-02-20 | 2026-01-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4815355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066002 | Ongoing | 23490 | 13608 | 2025-02-20
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4815420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066447 | Ongoing | 23490 | 21672 | 2025-02-06
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4815432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066643 | Physically Completed | 23490 | 21438 | 2025-02-05 | 2026-05-17
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4815433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152066644 | Completed | 23490 | 21834 | 2025-02-05 | 2026-01-19
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4815493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP152067438 | Ongoing | 23490 | 10206 | 2025-02-20
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4935093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102320572 | Completed | 23490 | 23490 | 2025-05-01 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4937251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105473097 | Completed | 23490 | 23490 | 2025-04-10 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4946095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115903827 | Completed | 23490 | 23490 | 2025-07-09 | 2025-09-18
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4947353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116434294 | Approved | 23490 | 0 | 2025-02-07
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4947354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116434388 | Completed | 23490 | 23229 | 2025-08-03 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4948324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115969296 | Completed | 23490 | 23490 | 2025-04-16 | 2025-08-15
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4948325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115969317 | Ongoing | 23490 | 20097 | 2025-07-09
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4948714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116782053 | Completed | 23490 | 23490 | 2025-07-16 | 2025-09-09
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4949341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117671653 | Completed | 23490 | 23490 | 2025-04-01 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4949452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734016 | Completed | 23490 | 23229 | 2025-06-03 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4949453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117734149 | Completed | 23490 | 23490 | 2025-05-17 | 2025-09-09
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4951975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118625371 | Completed | 23490 | 23490 | 2025-04-25 | 2025-08-15
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4951977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118627916 | Completed | 23490 | 23490 | 2025-07-24 | 2025-09-29
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4951978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118628128 | Completed | 23490 | 23490 | 2025-04-25 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4951980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118628902 | Completed | 23490 | 23490 | 2025-06-03 | 2025-08-28
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4954047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120696783 | Ongoing | 23490 | 22707 | 2025-08-01
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4958179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123050509 | Completed | 23490 | 23229 | 2025-11-01 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/4958863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123633568 | Ongoing | 23490 | 21924 | 2025-06-03
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/496530 — Construction of IAY House -IAY REG. NO. MP2213444 | Completed | 15030 | 15480 | 2017-05-22 | 2018-01-11
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/499025 — Construction of IAY House -IAY REG. NO. MP2240515 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-11
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/500395 — Construction of IAY House -IAY REG. NO. MP2256447 | Completed | 15030 | 15480 | 2017-05-11 | 2018-01-11
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/501847 — Construction of IAY House -IAY REG. NO. MP2276445 | Completed | 15030 | 15402 | 2017-03-06 | 2018-06-05
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/504450 — Construction of IAY House -IAY REG. NO. MP2313996 | Completed | 15030 | 15390 | 2017-03-06 | 2018-02-16
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/506384 — Construction of IAY House -IAY REG. NO. MP2340039 | Completed | 15030 | 15480 | 2017-05-23 | 2017-12-29
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5123228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131577271 | Completed | 23490 | 23490 | 2025-07-25 | 2025-10-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5125378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131231118 | Completed | 23490 | 23229 | 2025-09-05 | 2026-01-19
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/535417 — Construction of IAY House -IAY REG. NO. MP2940630 | Completed | 15030 | 14889 | 2017-03-06 | 2018-01-30
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/535421 — Construction of IAY House -IAY REG. NO. MP2940669 | Completed | 15030 | 15046 | 2017-03-06 | 2017-11-02
BASODA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/537693 — Construction of IAY House -IAY REG. NO. MP3005762 | Completed | 15030 | 15390 | 2017-03-06 | 2018-01-11
BASODA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5439431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120696483 | Approved | 23490 | 0 | 2025-02-08
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5600280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116434366 | Completed | 23490 | 23490 | 2025-05-17 | 2025-08-15
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5640920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123634914 | Completed | 23490 | 23490 | 2025-08-03 | 2025-10-30
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5642184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118628662 | Completed | 23490 | 23490 | 2025-07-17 | 2025-08-25
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5753503 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131231779 | Completed | 23490 | 23490 | 2025-08-29 | 2025-12-01
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5753555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131575010 | Completed | 23490 | 23229 | 2025-08-29 | 2026-01-19
BASODA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/5774118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116202668 | Completed | 23490 | 23490 | 2025-08-29 | 2025-11-20
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/614282 — Construction of IAY House -IAY REG. NO. MP1851913 | Completed | 15030 | 14448 | 2017-04-09 | 2018-01-30
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/636823 — Construction of IAY House -IAY REG. NO. MP1824920 | Completed | 15030 | 15480 | 2017-07-10 | 2017-12-29
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/908571 — Construction of IAY House -IAY REG. NO. MP2256491 | Completed | 15480 | 14964 | 2017-07-10 | 2018-03-12
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/945965 — Construction of IAY House -IAY REG. NO. MP2940635 | Completed | 15480 | 15480 | 2017-09-28 | 2018-03-12
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/946057 — Construction of IAY House -IAY REG. NO. MP2942520 | Completed | 15480 | 15480 | 2017-09-28 | 2018-03-12
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/947007 — Construction of IAY House -IAY REG. NO. MP2966719 | Completed | 15480 | 14792 | 2017-09-28 | 2018-01-30
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/947016 — Construction of IAY House -IAY REG. NO. MP2967061 | Completed | 15480 | 15414 | 2017-09-28 | 2019-03-17
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/948180 — Construction of IAY House -IAY REG. NO. MP2999652 | Completed | 15480 | 15480 | 2017-07-10 | 2018-01-11
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/950381 — Construction of IAY House -IAY REG. NO. MP3053976 | Completed | 15480 | 15564 | 2017-05-23 | 2018-10-23
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/950387 — Construction of IAY House -IAY REG. NO. MP3054090 | Completed | 15480 | 15480 | 2017-07-10 | 2018-01-11
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/950534 — Construction of IAY House -IAY REG. NO. MP3057766 | Completed | 15480 | 15492 | 2017-09-28 | 2018-06-05
BASODA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727004062/IF/IAY/953051 — Construction of IAY House -IAY REG. NO. MP3123256 | Completed | 15480 | 15516 | 2017-09-28 | 2018-09-18
BASODA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1727004062/LD/17 — खेल मैदान क्रीडांगन ग्राम पंचायत ककरावदा | Completed | 458000 | 191173.5 | 2011-12-08 | 2013-07-31
BASODA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1727004062/LD/22012034228860 — shanti dham | Completed | 764000 | 517832 | 2015-10-26 | 2017-05-15
BASODA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/144 — सीसी रोड ग्राम पंचायत ककरावदा | Completed | 34737 | 38487 | 2009-12-18 | 2009-10-02
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034185635 — सी सी रोड पंचपरमेश्‍वर पंचायत ककरावदा | Completed | 137000 | 133450 | 2013-10-11 | 2014-03-31
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034200958 — c c road | Completed | 130018 | 123366 | 2014-01-27 | 2014-07-10
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034209997 — cc road fifth installment panchayat kakravda | Completed | 137000 | 135043 | 2014-03-02 | 2015-02-28
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1727004062/RC/22012034211503 — grabal road | Completed | 1482245 | 584 | 2014-03-05 | 2015-03-02
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1727004062/RC/22012034211519 — sudoor gram sadk sampark yojna | Completed | 1482245 | 584 | 2014-03-05 | 2015-03-02
BASODA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034266788 — cc road pp | Completed | 110804 | 105430 | 2015-06-30 | 2016-07-28
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034302030 — cc road | Deleted | 0 | 0 | 2016-04-14
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034305424 — cc road nirman | Deleted | 0 | 0 | 2016-04-14
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034314156 — c.c. raod nirmad gram panchyat kakroda | Completed | 74000 | 71051 | 2016-10-15 | 2017-06-01
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Culvert / Construction of Culvert / cross drainage structues for Community | Culvert | 1727004062/RC/22012034314538 — puliya nirman panchayat kakrawda | Completed | 877000 | 842004.6 | 2016-12-15 | 2017-07-01
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1727004062/RC/22012034318942 — graval road men road se kharapri ki or kakrawda | Deleted | 1096648 | 0 | 2016-12-28
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034325262 — cc road nirman | Closed | 0 | 0 | 2017-01-27
BASODA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034325353 — cc road | Closed | 0 | 0 | 2017-01-26
BASODA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034371074 — सीसी रोड ग्राम पंचायत ककरावदा | Closed | 0 | 0 | 2017-10-02
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034395293 — सी.सी. रोड ई कक्ष से बाबू लाल के घर तक | Completed | 34909 | 35736 | 2018-09-29 | 2019-09-13
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034395304 — सी.सी. रोड गुड्डू के घर से माताबाई तक | Completed | 50558 | 52620 | 2018-09-29 | 2019-09-13
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034395498 — सी सी रोड रमेश के घर से भून्धा के घर तक | Completed | 19661 | 19920 | 2018-10-01 | 2020-02-25
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034396908 — cc road | Physically Completed | 96701 | 96164 | 2018-10-05 | 2019-11-10
BASODA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034442762 — cc road nrman | Closed | 0 | 0 | 2019-01-26
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034471659 — CC Road Moolchand ke ghar se Govt. Koop tak | Completed | 38000 | 36784 | 2019-08-03 | 2019-11-10
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034474063 — CC Road Mullo Bai ke Ghar se Somat Ke School ki or | Completed | 47000 | 47344 | 2019-08-25 | 2020-02-20
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034479175 — c c road nirman Mandir se baba sahab tak | Completed | 14000 | 13728 | 2019-11-07 | 2020-02-20
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034479176 — c c road nirman lalaram ke ghar se veer singh ke ghar tak | Completed | 8000 | 7392 | 2019-11-07 | 2020-02-20
BASODA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034479177 — c c road nirman ganpat ke ghar se mansingh ke ghar tak | Completed | 21000 | 20520 | 2020-08-19 | 2021-01-17
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034503436 — c c road nirman main road se govt. handpump ki or | Completed | 17000 | 17952 | 2019-11-28 | 2020-07-10
BASODA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034536980 — CC Road Nirman Munshiji ke ghar se Mukkadam sahab ke ghar ki or kakrawada | Completed | 64000 | 63840 | 2020-09-12 | 2020-12-10
BASODA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1727004062/RC/22012034541743 — Sudur Khet Sadak Nirman gram Kakrawada Mukhya Sadak se Kharpari Ki or Gp Kakarawada | Physically Completed | 1471875.11 | 545113 | 2020-11-24 | 2026-06-29
BASODA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034562137 — cc road nirman dhansingh ke ghar se prakash chidar ke ghar ki aor kakrawada | Completed | 25425 | 26616 | 2021-03-25 | 2026-05-11
BASODA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034614788 — cc road nirman karya veer singh sen ke ghar se guddu ke ghar tak kakravda | Ongoing | 30700 | 1224 | 2022-05-24
BASODA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034642035 — c c road nirman brajlal patwa ke ghar se aman ke ghar tak | Completed | 61000 | 59007 | 2023-09-12 | 2026-04-28
BASODA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034652345 — CC ROAD PANCHYAT BHAVAN PRANGAN KAKRAWADA | Completed | 32000 | 30277 | 2023-09-24 | 2026-05-11
BASODA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034668082 — Cc road nirman adiwashi tapara rati ram ke ghar se shamshan ghat ki puliya ki or | Completed | 97000 | 68510 | 2023-12-14 | 2026-05-04
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034824302 — CC ROAD ADIWASI TAPRA SHAMSHAN GHAT | Completed | 18000 | 10151.82 | 2025-01-21 | 2026-05-11
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034824305 — CC ROAD SHAMSHAN GHAT KAKRAWADA | Completed | 12000 | 7799.82 | 2025-01-26 | 2026-05-11
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/22012034833083 — CC ROAD NIRMAN HANUMAN MANDIR SE NAVAL PANDA KE GHAR KI OR | Approved | 21000 | 0 | 2024-11-15
BASODA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1727004062/RC/28 — गे्रवल रोड ककरावदा ग्राम ककरावदा | Completed | 495420 | 181815.87 | 2008-09-13 | 2013-10-31
BASODA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/286 — पंचपरमेश्‍वर सीसी रोड ग्राम पंचायत ककरावदा | Completed | 140000 | 75867.8 | 2012-02-20 | 2012-05-30
BASODA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004062/RC/468 — 1727004062/RC/468 | Completed | 0 | 155609 | 2012-12-01 | 2013-03-31
BASODA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034186065 — sochalaya nirman (gulab ) | Deleted | 4400 | 0 | 2012-08-15
BASODA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034186067 — sochalaya nirman (kallu) | Deleted | 4400 | 0 | 2012-08-15
BASODA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034186068 — sochalaya nirman (kashi ram ) | Deleted | 4400 | 0 | 2012-08-15
BASODA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034186069 — sochalaya nirman (suresh) | Deleted | 4400 | 0 | 2012-08-15
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189107 — maryada abhiyan baldev/munna kakrawda | Deleted | 4400 | 0 | 2013-04-14
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189115 — maryada abhiyan vinod/toran singh kakrawada | Completed | 4400 | 4400 | 2014-02-01 | 2015-03-03
BASODA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189118 — maryada abhiyan radheshayam/seetaram kakrawada | Completed | 4400 | 4620 | 2014-05-01 | 2015-03-03
BASODA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189121 — maryada abhiyan akhlesh /rajaram kakarawada | Completed | 4400 | 4620 | 2014-05-01 | 2015-03-03
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189122 — maryada abhiyan rambabu/ramprasad kakrawada | Deleted | 4400 | 0 | 2013-04-14
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189125 — maryada abhiyan ramraj/datar singh kakarawada | Deleted | 4400 | 0 | 2013-04-14
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1727004062/RS/22012034189127 — maryada abhiyan neelam/veer singh kakarawada | Deleted | 4400 | 0 | 2013-04-14
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1727004062/RS/22012034443307 — nadep nirman gram kakrawada | Closed | 12284.01 | 0 | 2019-06-25
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1727004062/RS/22012034443308 — nadep nirman garam kakrawada gp kakrawda | Closed | 0 | 0 | 2019-06-25
BASODA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1727004062/RS/22012034443309 — nadep nirman garam kakrawada gp kakrawda | Closed | 12284.01 | 0 | 2019-06-25
BASODA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1727004062/RS/22012034501993 — Construction of Community Sanitary Complex GP Kakrawda | Completed | 44000 | 40404 | 2020-11-29 | 2023-12-15
BASODA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1727004062/RS/22012034656576 — nali nirman karya braj lal patwa ke ghar se aman malviya ke ghar tak | Completed | 28000 | 27965 | 2022-05-24 | 2026-04-28
BASODA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1727004062/RS/22012034658366 — nali ke upar farsikaran karya main road kakrawada | Ongoing | 26154 | 1224 | 2022-05-27
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1727004062/RS/22012035126666 — Nali Nirman Hanuman Mandir se CSC Tak GP Kakrawada | Completed | 33000 | 16459.78 | 2025-03-03 | 2026-04-28
BASODA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1727004062/RS/22012035126669 — Nali Nirman Men Road se Shivraj Adiwasi ke ghar tak GP Kakrawada | Completed | 34000 | 29599.19 | 2024-08-26 | 2026-05-11
BASODA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1727004062/WC/22012034558211 — nala gehrikaran gram kakrawada | Completed | 259913.25 | 185820 | 2020-07-09 | 2021-02-18
BASODA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1727004062/WC/22012034635547 — Talab renovations kakarawada | Closed | 0 | 0 | 2021-01-26
BASODA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1727004062/WC/22012034635557 — talab nirman kakarawada | Closed | 0 | 0 | 2021-01-26
BASODA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1727004062/WC/22012034658869 — Ctr Water harvesting panchayat bhabhan mai gp Kakarawada | Closed | 0 | 0 | 2021-04-14
BASODA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1727004062/WC/22012034658871 — Ctr Water harvesting panchayat bhabhan mai gp Kakarawada | Physically Completed | 38179.65 | 1158 | 2021-07-08 | 2026-06-30
BASODA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1727004062/WC/22012034658879 — Ctr Water harvesting Aganbadi 1 mai gp kakarawada | Closed | 0 | 0 | 2021-04-14
BASODA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1727004062/WC/22012034765455 — Rooftop rainwater harvesting aganwadi bhwan kakrawada | Physically Completed | 22229.14 | 1158 | 2021-07-08 | 2026-06-30
BASODA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1727004062/WC/22012034765456 — Rooftop rainwater harvesting aganwadi bhwan kakrawada | Closed | 0 | 0 | 2021-04-14
BASODA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1727004062/WC/22012034942626 — Wast Weir Nirman Gram Kakrawda | Ongoing | 315991.58 | 21828 | 2022-04-12
BASODA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1727004062/WC/25 — सोख्‍ता गडडा ककरावदा | Completed | 8100 | 3425 | 2008-05-21 | 2008-01-10
BASODA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1727004062/WC/79 — स्‍टाप डेम ग्राम पंचायत ककरावदा | Completed | 499000 | 495705 | 2009-01-19 | 2013-02-06
BASODA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1727004062/WC/9993669514 — cheak dam | Closed | 0 | 0 | 2016-04-14
BASODA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1727004062/WH/19954864 — talab gharikaran | Deleted | 0 | 0 | 2016-04-14
BASODA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1727004062/WH/19961184 — Talab Gharikaran GP Kakrawda | Completed | 232000 | 210890.72 | 2017-05-24 | 2017-07-15
BASODA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1727004063/RC/22012034185641 — सी सी रोड पंचपरमेश्‍वर पंचायत स्‍यारी | Deleted | 162338 | 0 | 2013-04-14