## Work List
Exported on: 2026-09-10 21:13:23
Filters applied:
Data source: VBGRAMG
District: VIDISHA
Block: All
Panchayat: PADARIYA JAGIR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
NATERAN | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1727005069/DP/22012034591900 — VASUDHA VANDAN AMRIT VATIKA HIGH SCHOOL KE PASS GP PADARIYA JAGIR | Ongoing | 55847.4 | 0 | 2023-08-19
NATERAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727005069/IF/22012034992785 — hiteshi koop gopal bai/gulabsingh | Ongoing | 257014.43 | 0 | 2022-05-27
NATERAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1727005069/IF/22012034992791 — hiteshi koop suratsingh/banfoola | Ongoing | 257014.43 | 0 | 2022-11-15
NATERAN | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1727005069/IF/22012035330285 — JGSA Recharge Structure Gulab bai sambal singh yadav | New | 0 | 0 | 2025-04-01
NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727005069/IF/22012035623748 — EK BAGIYA MAA KE NAAM RINKI PAVAN 192522822 GP PADARIYAJAGEER | Ongoing | 269386.03 | 0 | 2025-10-24
NATERAN | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1727005069/IF/22012035633553 — EK BAGIYA MAA KE NAAM FULBA BAI 159473181 PADARIYAJAGEER | Ongoing | 269387.37 | 0 | 2025-10-25
NATERAN | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/3660411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124163431 | Physically Completed | 23490 | 0 | 2022-06-26 | 2026-07-31
NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/4941822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114104207 | Ongoing | 27000 | 0 | 2025-03-28
NATERAN | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/4941922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114146966 | Ongoing | 27000 | 0 | 2025-03-28
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5954542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115250953 | Ongoing | 27000 | 8400 | 2026-05-03
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5954867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114975657 | Ongoing | 27000 | 12300 | 2026-04-15
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5959698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114172858 | Ongoing | 27000 | 12300 | 2026-05-10
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5960492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114977573 | Ongoing | 27000 | 12300 | 2026-04-15
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5960913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114146667 | Ongoing | 27000 | 12300 | 2026-04-15
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5961180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115257669 | Ongoing | 27000 | 12300 | 2026-04-15
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5961564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115034091 | Ongoing | 27000 | 12300 | 2026-04-15
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5966556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114181349 | Ongoing | 27000 | 12300 | 2026-05-03
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/5966563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114974852 | Ongoing | 27000 | 12300 | 2026-04-15
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/6131456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114976929 | Ongoing | 27000 | 12300 | 2026-07-04
NATERAN | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1727005069/IF/IAY/6349814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114974702 | Approved | 27000 | 0 | 2026-07-07
NATERAN | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1727005069/WC/22012034983887 — Water harvesting pond seetaram ke khet ke paas padariya jagir | Ongoing | 356340.1 | 0 | 2022-05-27
NATERAN | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1727005069/WC/22012035215364 — STOP DEM CUM PULIYA NIRMAN PADARIYA JAGIR BABURAM KE KHET KE PASS | Ongoing | 2116000 | 0 | 2024-07-10