## Work List
Exported on: 2026-09-13 21:48:57
Filters applied:
Data source: VBGRAMG
District: BHOPAL
Block: All
Panchayat: KURANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002018/DP/22012034580314 — सामुदायिक व़क्षारोपण कार्य शमशान घाट के पास, कुराना | Ongoing | 91574.4 | 0 | 2023-08-26
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1728002018/DP/22012034614681 — सामुदायिक कूप निर्माण कुराना | New | 0 | 0 | 2024-04-14
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002018/IF/22012035268593 — कपिलधारा कूप निर्माण कार्य राधेश्‍याम / जगन्‍नाथ, ग्राम पंचायत कुराना | Approved | 355189.39 | 0 | 2024-10-02
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1728002018/IF/22012035270888 — कपिलधारा कूप निर्माण कार्य राकेश / जगन्‍नाथ मेहरा, ग्राम पंचायत कुराना | Ongoing | 355189.39 | 0 | 2024-12-14
PHANDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1728002018/IF/22012035384902 — डगवेल रिर्चाज निर्माण नंदकिशोर / मोहन लाल के कूप के पास, ग्राम पंचायत कुराना | Ongoing | 25899.46 | 0 | 2025-04-23
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1728002018/IF/22012035622039 — एक बगिया मॉं के नाम उषा बाई / नंदकिशोर, MP28002018001/525 B, कुराना | Approved | 192688.19 | 0 | 2025-04-14
PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/113878 — Construction of IAY House -IAY REG. NO. MP-28-002-018-001/03 | Approved | 27000 | 0 | 2016-01-16
PHANDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/3909680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148555162 | Approved | 27000 | 0 | 2022-04-27
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4556486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113688114 | Approved | 27000 | 0 | 2024-09-11
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4646815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140032672 | Ongoing | 27000 | 0 | 2024-11-02
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4648236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140710484 | Ongoing | 27000 | 0 | 2024-11-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4688466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106765921 | Ongoing | 27000 | 0 | 2025-08-23
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4698943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119575009 | Ongoing | 27000 | 0 | 2024-11-02
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4758465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119574546 | Physically Completed | 27000 | 0 | 2026-05-02 | 2026-09-06
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4935330 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105335775 | Ongoing | 27000 | 0 | 2025-04-05
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4936999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100962294 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4938667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106748590 | Ongoing | 27000 | 0 | 2025-05-31
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4938849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106850925 | Physically Completed | 27000 | 2100 | 2025-09-27 | 2026-09-06
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4938854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106852235 | Physically Completed | 23490 | 3600 | 2025-07-12 | 2026-08-16
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4938861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106853994 | Ongoing | 27000 | 0 | 2026-09-05
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4939356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113450028 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4940141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105855577 | Physically Completed | 23490 | 1800 | 2026-05-30 | 2026-08-16
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4940218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107073561 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4940746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113686740 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4941926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114147249 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4941940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114150174 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4941958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114154505 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4942707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115033237 | Ongoing | 27000 | 0 | 2025-04-12
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4946649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114825645 | Ongoing | 27000 | 1500 | 2026-08-15
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4948877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114172922 | Physically Completed | 23490 | 0 | 2025-04-05 | 2026-08-23
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4979377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140032466 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4979379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140032597 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4979462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140710382 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4979466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140711411 | Ongoing | 27000 | 0 | 2025-05-03
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4979467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140711714 | Ongoing | 27000 | 1800 | 2026-08-15
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4981734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146187441 | Physically Completed | 23490 | 0 | 2026-05-02 | 2026-08-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/4982967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148191371 | Ongoing | 27000 | 0 | 2025-05-03
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5103873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149166511 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5107541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150918986 | Ongoing | 27000 | 0 | 2025-09-06
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5386646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146128329 | Ongoing | 27000 | 0 | 2026-05-02
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5386657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140709223 | Physically Completed | 27000 | 0 | 2025-09-27 | 2026-09-06
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5388652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150032056 | Physically Completed | 23490 | 0 | 2026-06-13 | 2026-08-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5390666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121679336 | Ongoing | 27000 | 0 | 2025-06-14
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5393955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148578568 | Ongoing | 27000 | 0 | 2026-09-05
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5398381 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114161277 | Ongoing | 27000 | 0 | 2026-09-05
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5402029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115032948 | Ongoing | 27000 | 1800 | 2026-08-15
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5406396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105360013 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5407999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124002091 | Physically Completed | 27000 | 0 | 2026-05-02 | 2026-09-06
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5409745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140710274 | Approved | 27000 | 0 | 2025-03-05
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5409748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140711521 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5530848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106457030 | Ongoing | 27000 | 0 | 2026-09-05
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5723708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106849053 | Approved | 27000 | 0 | 2025-02-12
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/5747478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114157989 | Ongoing | 27000 | 7200 | 2026-08-15
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/6061000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103132420 | Approved | 27000 | 0 | 2024-09-11
PHANDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002018/IF/IAY/85036 — Construction of IAY House -IAY REG. NO. MP-28-002-018-001/39 | Approved | 27000 | 0 | 2016-01-11
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002018/RC/22012034830649 — सी सी रोड निर्माण मनरेगा +15 वां वित्त सविता जैन के घर से नाला तक शांतिनगर बस्‍ती, कुराना | Ongoing | 45000 | 0 | 2024-11-23
PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002018/RS/22012035138810 — आरसीसी नाली निर्माण कार्य मनरेगा +पीएमएजीवाय, किशन लाल से भारती अहिरवार के घर तक, कुराना | Approved | 50000 | 0 | 2025-04-14
PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002018/RS/22012035138811 — आरसीसी नाली निर्माण कार्य मनरेगा +पीएमएजीवाय,गुडडा अहिरवार से राधेश्‍याम के घर तक, कुराना | Approved | 100000 | 0 | 2025-04-14
PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002018/RS/22012035138812 — आरसीसी नाली निर्माण कार्य मनरेगा +पीएमएजीवाय, भंवर लाल मेहरा से शिव राय के घर तक, कुराना | Approved | 30000 | 0 | 2025-04-14
PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002018/RS/22012035138813 — नाली निर्माण कार्य मनरेगा +पीएमएजीवाय, गुडडा अहिरवार से अर्जुन मेहरा के घर तक, कुराना | Approved | 50000 | 0 | 2025-04-14
PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002018/RS/22012035138814 — नाली निर्माण कार्य मनरेगा +पीएमएजीवाय, सुमेर अहिरवार से राधेश्‍याम के घर तक, कुराना | Approved | 50000 | 0 | 2025-04-14
PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002018/WC/22012035230871 — नाला ट्रेंचिंग एवं पिंचिग कार्य चंदर सिंह मेवाडा के खेत के पास, ग्राम पंचायत कुराना | Ongoing | 834895.72 | 0 | 2024-12-14
PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002018/WC/22012035230873 — नाला ट्रेंचिंग एवं पिंचिग कार्य रमेश मेवाडा के खेत के पास, ग्राम पंचायत कुराना | Ongoing | 834895.72 | 0 | 2024-12-07