## Work List
Exported on: 2026-09-11 02:52:58
Filters applied:
Data source: MGNREGA
District: BHOPAL
Block: All
Panchayat: PADARIYA SANKAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PHANDA | 2023-2024 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1728002089/AV/22012034631749 — सेग्रीगेशन शेड निर्माण कार्य मनरेगा+15 वॉं वित्‍त, हरिपुरा ग्राम पंचायत पडरियासांकल | Completed | 20000 | 17680 | 2023-05-27 | 2024-10-09
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1728002089/AV/22012034632925 — आंगनबाडी भवन निर्माण मय वाउंड्रीवॉल, मनरेगा + महिला बाल विकास, पडरियासांकल | Completed | 500000 | 69168 | 2023-05-27 | 2026-05-05
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1728002089/AV/22012034648617 — Gram Panchayat Seva Kendra | Ongoing | 1100000 | 189932.22 | 2024-01-27
PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002089/DP/22012034569732 — मॉं की बगिया निर्माण कार्य (संख्‍या 10), पडरियासांकल | Closed | 45114.42 | 0 | 2022-08-16
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002089/DP/22012034580860 — व़क्षारोपण कार्य गौशाला के पास, समरधा, पडरियासांकल | Ongoing | 427106.07 | 209262.4 | 2023-08-05
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002089/IF/22012035357815 — खेत तालाब निर्माण कार्य शांता बाई / हरकिशन, ग्राम पंचायत पडरियासांकल | Physically Completed | 147621.16 | 134781 | 2025-04-23 | 2026-06-15
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002089/IF/22012035470464 — खेत तालाब निर्माण कार्य मोहर सिंह / कमल सिंह, समरधा, पड़रियासांकल | Physically Completed | 450885.64 | 238338 | 2025-05-05 | 2026-06-15
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002089/IF/22012035470484 — खेत तालाब निर्माण कार्य रंजीत / सत्यनारायण, समरधा, पड़रियासांकल | Physically Completed | 450885.64 | 194229 | 2025-05-10 | 2026-06-15
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002089/IF/22012035470497 — खेत तालाब निर्माण कार्य दौलतराम / बाबू लाल, समरधा, पड़रियासांकल | Physically Completed | 450885.64 | 202059 | 2025-05-05 | 2026-06-15
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1728002089/LD/22012034589330 — चारागाह विकास कार्य समरधा, पडरियासांकल | Ongoing | 904330.73 | 242216 | 2023-05-27
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1728002089/RC/22012034638681 — सुदूर सडक निर्माण मनरेगा +जनभागीदारी मेन रोड से खेडापति मंदिर की ओर, पडरियासांकल | Physically Completed | 1097000 | 951277.74 | 2023-06-10 | 2026-06-19
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002089/RC/22012034680958 — सी सी रोड निर्माण कार्य ग्राम पंचायत पडरियासांकल | New | 0 | 0 | 2024-04-14
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002089/WC/22012035044651 — सामुदायिक पोण्‍ड निर्माण कार्य ग्राम समरधा, पडरियासांकल | Ongoing | 362452.46 | 46410 | 2023-06-03
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002089/WC/22012035120185 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य (संख्‍या 5) पडरियासांकल | Completed | 86218.22 | 47697 | 2023-10-07 | 2025-04-25
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone boulder Gully Plugs for Comm / Construction of Stone boulder Gully Plugs for Community | Boulder Check/Gully Plug | 1728002089/WC/22012035120191 — गली प्‍लग / बोल्‍डर चेक निर्माण्‍ा कार्य (संख्‍या 5) समरधा, पडरियासांकल | Completed | 86218.22 | 50369.82 | 2023-10-07 | 2025-04-25