## Work List
Exported on: 2026-10-04 02:51:29
Filters applied:
Data source: VBGRAMG
District: BHOPAL
Block: All
Panchayat: PIPALIYABAJ KHAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1728002091/AV/22012034648634 — Gram Panchayat Seva Kendra | Ongoing | 1100000 | 0 | 2024-03-08
PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1728002091/DP/22012034624706 — सामुदायिक वृक्षारोपण कार्य ग्राम पंचायत पिपलियाबाजखॉं | Approved | 259479.75 | 0 | 2024-06-08
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1728002091/RC/22012034680960 — सी सी रोड निर्माण कार्य ग्राम पंचायत पिपलियाबाजखाॅं | New | 0 | 0 | 2024-04-14
PHANDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1728002091/RS/22012035138016 — ग्रेवाटर ट्रीटमेंट नाली निर्माण कार्य मनरेगा+ 15 वां वित्त रामगढ मोहल्‍ला, पिपलियाबाजखॉं | Ongoing | 71000 | 2100 | 2025-06-20
PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002091/WC/VB/22012035332531 — रेन वाटर हार्वेस्टिंग कार्य शाला भवन ग्राम पंचायत पिपलियाबाजखाॅं | Deleted | 0 | 0 | 2026-04-24
PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002091/WC/VB/22012035332833 — रेन वाटर हार्वेस्टिंग कार्य सामुदायिक शेड ग्राम पंचायत पिपलियाबाजखॉं | Deleted | 0 | 0 | 2026-04-24