## Work List
Exported on: 2026-10-24 03:04:47
Filters applied:
Data source: MGNREGA + VBGRAMG
District: BHOPAL
Block: All
Panchayat: GURADIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat Building for Community | Constr of GP Bhawan | 1728002099/AV/22012034648688 — Gram Panchayat Seva Kendra | Ongoing | 1100000 | 3094 | 2024-03-11
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1728002099/DP/22012034582721 — व़क्षारोपण कार्य अम़त सरोवर के पास, मनीखेडीकोट, गुराडिया | Ongoing | 134212.69 | 67626 | 2023-08-02
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1728002099/DP/22012034604886 — व़क्षारोपण कार्य शमशान घाट परिसर, गुराडिया | Closed | 0 | 0 | 2023-04-14
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728002099/IF/22012035103221 — कपिलधारा कूप निर्माण कार्य सतीश / बालाराम, मनीखेडीकोट, गुराडिया | Ongoing | 386307.96 | 20412 | 2025-02-12
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1728002099/IF/22012035396516 — खेत तालाब निर्माण कार्य दिलीप / रघुवर सिंह, मनीखेडीकोट, गुराडिया | Physically Completed | 377169.74 | 250789.11 | 2025-04-26 | 2026-06-05
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728002099/IF/22012035480847 — खेत तालाब निर्माण कार्य राजमल / भंवर जी, गु‍राडिया | Ongoing | 147621.16 | 4959 | 2025-05-14
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728002099/IF/22012035515657 — खेत तालाब निर्माण कार्य कमल / रमेश, मनीखेडीकोट, गुराडिया | Approved | 0 | 0 | 2025-04-14
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1728002099/IF/22012035567521 — खेत तालाब निर्माण कार्य तखत सिंह / मिश्री लाल, मनीखेडीकोट, गुराडिया | Approved | 0 | 0 | 2025-04-14
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1728002099/IF/22012035629983 — एक बगिया मॉं के नाम रानी बाई / अजय सिंह, MP28002004003/29A,जानकी समूह मनीखेडी कोट, गुराडिया | Ongoing | 263511.37 | 0 | 2025-11-24
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1728002099/IF/22012035650225 — कपिलधारा कूप निर्माण कार्य रामबाबू / द्वारका प्रसाद, मनीखेडीकोट, गुराडिया | New | 0 | 0 | 2025-04-15
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/4708857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124294988 | Completed | 23490 | 21168 | 2024-11-13 | 2026-06-16
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4710523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123430284 | Ongoing | 27000 | 20412 | 2025-01-29
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4710539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123436266 | Ongoing | 27000 | 21168 | 2025-01-29
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4710540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123436906 | Ongoing | 27000 | 18576 | 2024-11-13
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/4713052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126605868 | Completed | 23490 | 21924 | 2025-06-04 | 2025-09-22
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4713603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127205985 | Ongoing | 27000 | 20412 | 2025-01-29
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4767033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123513463 | Ongoing | 27000 | 20520 | 2024-11-13
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4770255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123888835 | Ongoing | 27000 | 9396 | 2025-04-02
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/4770786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124311747 | Physically Completed | 23490 | 20628 | 2024-11-13 | 2026-04-19
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4770802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124318764 | Ongoing | 27000 | 20952 | 2024-11-27
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4776250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127253490 | Ongoing | 27000 | 20412 | 2024-11-06
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/4780755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128151716 | Completed | 23490 | 21384 | 2024-12-11 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4789311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140479492 | Physically Completed | 27000 | 20358 | 2025-04-09 | 2026-10-18
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4790123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126578130 | Ongoing | 27000 | 20412 | 2024-12-11
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/4859368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124276414 | Approved | 27000 | 0 | 2024-09-24
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5822700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123434768 | Ongoing | 27000 | 19728 | 2026-05-06
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5822704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123457301 | Completed | 23490 | 23490 | 2025-12-03 | 2026-05-04
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5822795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127321750 | Completed | 23490 | 21924 | 2026-05-06 | 2026-08-06
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5823261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126638022 | Physically Completed | 23490 | 20880 | 2025-11-05 | 2026-03-15
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5823347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123883804 | Completed | 23490 | 22446 | 2025-10-15 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5823441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124313582 | Completed | 23490 | 21924 | 2026-01-28 | 2026-06-16
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5824434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126031630 | Ongoing | 27000 | 18162 | 2026-05-13
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5824761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124285929 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5824765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124316644 | Completed | 23490 | 23229 | 2026-01-21 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5825063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125058078 | Completed | 23490 | 22446 | 2025-10-15 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5825184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126656114 | Completed | 23490 | 22446 | 2026-02-18 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5825802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106628132 | Completed | 23490 | 22185 | 2025-12-24 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5825803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106628212 | Completed | 23490 | 22707 | 2025-10-29 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5825804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106628290 | Completed | 23490 | 22968 | 2025-10-29 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5825805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106628316 | Completed | 23490 | 22968 | 2025-12-17 | 2026-06-16
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5826155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106628425 | Ongoing | 27000 | 12600 | 2025-02-07
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5826313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123433998 | Completed | 23490 | 22446 | 2025-10-15 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5826325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124289337 | Completed | 23490 | 22446 | 2025-10-15 | 2026-06-16
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5826422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124293674 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5826552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127249006 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5826996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123431024 | Completed | 23490 | 22446 | 2025-10-15 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5827634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126294948 | Completed | 23490 | 22968 | 2025-10-29 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5827648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125793454 | Completed | 23490 | 22446 | 2025-10-15 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5827772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126588110 | Completed | 23490 | 22446 | 2025-10-15 | 2026-06-16
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5828016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126653804 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5828453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125059464 | Completed | 23490 | 21402 | 2025-12-03 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5828459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126456789 | Physically Completed | 23490 | 19575 | 2025-10-15 | 2025-12-11
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5843970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123437481 | Ongoing | 27000 | 16200 | 2025-02-07
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5844262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129459430 | Completed | 23490 | 21924 | 2025-11-12 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5844858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127254619 | Physically Completed | 23490 | 15660 | 2025-11-05 | 2025-12-11
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5844859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127256620 | Completed | 23490 | 21924 | 2026-02-04 | 2026-05-04
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061257 | Ongoing | 27000 | 22464 | 2026-06-17
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061345 | Completed | 23490 | 21924 | 2026-04-29 | 2026-06-16
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061419 | Ongoing | 27000 | 0 | 2025-02-07
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061516 | Ongoing | 27000 | 21924 | 2026-04-29
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061609 | Completed | 23490 | 22968 | 2026-02-04 | 2026-05-04
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061721 | Ongoing | 27000 | 15660 | 2026-05-13
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140061914 | Completed | 23490 | 21924 | 2026-01-21 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140062020 | Completed | 23490 | 23490 | 2025-11-05 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129460131 | Completed | 23490 | 22968 | 2025-12-17 | 2026-06-16
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140710327 | Ongoing | 27000 | 23094 | 2026-04-29
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139896288 | Completed | 23490 | 23490 | 2025-11-05 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140667499 | Physically Completed | 23490 | 20358 | 2025-11-12 | 2025-12-11
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140669128 | Completed | 23490 | 22446 | 2025-12-31 | 2026-06-16
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127236528 | Completed | 23490 | 23229 | 2025-12-17 | 2026-06-16
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140535285 | Ongoing | 27000 | 22464 | 2026-06-17
PHANDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140535454 | Physically Completed | 27000 | 22464 | 2026-06-17 | 2026-10-18
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1728002099/IF/IAY/5845673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140535615 | Completed | 23490 | 22968 | 2025-12-31 | 2026-05-04
PHANDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5845674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140536321 | Ongoing | 27000 | 21402 | 2026-03-25
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5878229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127255636 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5878237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127257705 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/5878286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126660651 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/6264626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126019444 | Approved | 27000 | 0 | 2025-02-07
PHANDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1728002099/IF/IAY/6305922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126635780 | Approved | 27000 | 0 | 2025-02-14
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002099/RC/22012034654854 — सी सी रोड निर्माण कार्य मनरेगा+15 वां वित्‍त, जीवन से राकेश के घर की ओर, गुराडिया | Completed | 21224 | 19976 | 2023-09-20 | 2024-10-03
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1728002099/RC/22012034661980 — खेत सडक निर्माण कार्य मनरेगा+जनभागीदारी, ठाकुर बाबा से जोगीबर्री खेत तक, गुराडिया | Ongoing | 3644000 | 2173619.56 | 2023-10-08
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002099/RC/22012034663865 — सी सी रोड निर्माण कार्य मनरेगा+15 वां वित्‍त, गंगाराम से कमलेश के घर की ओर, मनीखेडीकोट, गुराडिया | Closed | 25622 | 0 | 2023-04-14
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002099/RC/22012034681494 — सी सी रोड निर्माण मनरेगा +15वां वित्त, प्रकाश से अशोक के घर की ओर, गुराडिया | Completed | 25622 | 21870 | 2024-09-04 | 2024-11-28
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1728002099/RC/22012034830828 — सी सी रोड निर्माण मनरेगा +15 वां वित्त गब्‍बू से कमलेश के घर की ओर, गुराडिया | Physically Completed | 53400 | 21645 | 2025-01-22 | 2026-06-27
PHANDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002099/RS/22012035116711 — पाइप नाली निर्माण मनरेगा+15वां वित्‍त,नदी से शाला भवन की ओर, गुराडिया | Completed | 44257 | 43308 | 2023-10-06 | 2024-12-02
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1728002099/RS/22012035125101 — सी सी नाली निर्माण ग्राम पंचायत गुराडिया | New | 0 | 0 | 2024-04-14
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002099/RS/22012035134098 — अण्‍डर ग्राउंड नाली निर्माण कार्य मनरेगा +15 वां वित्‍त सूरज के घर से पुलिया की ओर, गुराडिया | Completed | 15000 | 7290 | 2025-01-29 | 2026-05-11
PHANDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1728002099/RS/22012035134099 — अण्‍डर ग्राउंड नाली निर्माण कार्य मनरेगा +15 वां वित्‍त हीरालाल के घर से पुलिया की ओर, गुराडिया | Completed | 31247 | 30618 | 2024-12-25 | 2025-04-04
PHANDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002099/WC/22012035001525 — सामुदायिक सोख्‍ता गढढा निर्माण कार्य (संख्‍या 3), गुराडिया | Completed | 66678.37 | 35700 | 2022-11-30 | 2025-06-28
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1728002099/WC/22012035069722 — सामुदायिक सोख्‍ता गढढा निर्माण कार्य ग्राम पंचायत गुराडिया | Physically Completed | 153036.87 | 57960 | 2023-06-21 | 2026-06-28
PHANDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1728002099/WC/22012035138928 — सामुदायिक पोण्‍ड निर्माण कार्य दयाराम के खेत के पास,गुराडिया | Completed | 316244.2 | 222428 | 2024-03-15 | 2026-06-04
PHANDA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1728002099/WC/22012035235416 — सामुदायिक पोण्‍ड निर्माण कार्य, मनीखेडीकोट, ग्राम पंचायत गुराडिया | Approved | 537762.81 | 0 | 2024-08-16
PHANDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1728002099/WC/22012035256034 — चेक डेम निर्माण कार्य मनरेगा + 15 वां वित्त ग्राम पंचायत गुराडिया | Completed | 64000 | 55332 | 2025-12-03 | 2026-04-16
PHANDA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1728002099/WC/VB/22012035332485 — रेन वाटर हार्वेस्टिंग कार्य सामुदायिक शेड,मनीखेडीकोट, ग्राम पंचायत गुराडिया | Deleted | 0 | 0 | 2026-07-10