## Work List
Exported on: 2026-10-05 01:19:22
Filters applied:
Data source: VBGRAMG
District: SEHORE
Block: All
Panchayat: BARCHEDA DEVA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1729001027/IF/22012035444313 — JGSA 20252025Recharge Structure kapil dhara narendra | New | 0 | 0 | 2025-04-14
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1729001027/IF/22012035532796 — JGSA2025Recharge Structure kapil daea kup dindayl jay singh1729001027/If/22012035532772 | Approved | 25899.46 | 0 | 2025-04-14
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1729001027/IF/22012035532917 — JGSA2025Recharge Structure kapil daea kup dindayl jay singh1729001027/If/22012035532772 | New | 0 | 0 | 2025-04-14
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1729001027/IF/22012035532960 — JGSA2025Recharge Structure kapil daea kup AJab singh 1729001027/If/22012035532939 | New | 0 | 0 | 2025-04-14
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1729001027/IF/22012035547133 — JGSA2025Recharge Structure kapil daea kup dindayl jay singh1729001027/If/220120355347119 | New | 0 | 0 | 2025-04-14
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729001027/IF/22012035605651 — Ek bagiya maa ke naam Imarat bai / kamal singh 1729001027/If/22012035605598 | Ongoing | 266577.25 | 0 | 2025-09-06
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729001027/IF/22012035609491 — ek bagiya ma ke naam Seema /bhagvan singh 1729001027/IF/ 22012035609486 | Ongoing | 266577.25 | 0 | 2025-11-19
SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/102769 — Construction of IAY House -IAY REG. NO. MP-29-001-027-001/147 | Approved | 27000 | 0 | 2015-09-23
SEHORE | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/102770 — Construction of IAY House -IAY REG. NO. MP-29-001-027-001/79 | Approved | 27000 | 0 | 2015-09-23
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4653425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742604 | Physically Completed | 27000 | 0 | 2025-01-26 | 2026-09-22
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4713456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125974688 | Ongoing | 27000 | 0 | 2025-01-26
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4727618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740388 | Physically Completed | 27000 | 0 | 2025-01-26 | 2026-09-22
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4727619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740492 | Ongoing | 27000 | 0 | 2025-01-05
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4727620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740985 | Ongoing | 27000 | 0 | 2024-11-11
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4807264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146738705 | Physically Completed | 23490 | 0 | 2025-01-26 | 2026-08-04
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4807266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740560 | Physically Completed | 27000 | 0 | 2024-12-03 | 2026-09-22
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4807267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740680 | Physically Completed | 27000 | 0 | 2025-01-12 | 2026-09-22
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4807268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741145 | Physically Completed | 27000 | 0 | 2025-01-12 | 2026-09-22
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4807269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741591 | Physically Completed | 27000 | 0 | 2025-01-12 | 2026-09-22
SEHORE | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4860184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740955 | Physically Completed | 27000 | 0 | 2025-02-13 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4965141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125972809 | Ongoing | 27000 | 0 | 2025-08-09
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4980909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742010 | Physically Completed | 27000 | 0 | 2025-08-09 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4980910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742167 | Physically Completed | 27000 | 0 | 2025-08-09 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4980912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742426 | Ongoing | 27000 | 0 | 2025-08-09
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/4980915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742520 | Physically Completed | 27000 | 0 | 2025-09-11 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5165225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126319462 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5168665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125970711 | Ongoing | 27000 | 0 | 2025-08-09
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5202915 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146739376 | Physically Completed | 27000 | 0 | 2025-08-09 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5228769 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741679 | Ongoing | 27000 | 0 | 2026-03-25
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5232536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740543 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5581083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146739121 | Physically Completed | 27000 | 0 | 2025-08-09 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5583005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742374 | Physically Completed | 27000 | 0 | 2025-08-09 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5724198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742479 | Ongoing | 27000 | 14400 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742699 | Physically Completed | 27000 | 0 | 2025-09-02 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126447197 | Physically Completed | 27000 | 0 | 2025-09-02 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125972144 | Physically Completed | 27000 | 0 | 2025-08-25 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742486 | Physically Completed | 27000 | 0 | 2025-09-02 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740053 | Ongoing | 27000 | 0 | 2026-03-25
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146739209 | Ongoing | 27000 | 0 | 2025-09-02
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125970190 | Physically Completed | 27000 | 0 | 2025-09-02 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741573 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5749956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740291 | Physically Completed | 27000 | 0 | 2025-09-02 | 2026-09-22
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5750015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125949088 | Ongoing | 27000 | 0 | 2025-09-11
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5750059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742259 | Ongoing | 27000 | 0 | 2026-03-25
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5750074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146739087 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5750106 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742139 | Ongoing | 27000 | 0 | 2026-03-25
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5761382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740422 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5761441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125958928 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5762945 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146738930 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5762946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740798 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5775067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146742292 | Ongoing | 27000 | 10200 | 2026-03-25
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/5775091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125558666 | Ongoing | 27000 | 0 | 2026-03-21
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6123466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125961559 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6134302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146738387 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6134306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146739428 | Approved | 27000 | 0 | 2026-03-05
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6134317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741379 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6134318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741424 | Approved | 27000 | 0 | 2026-02-11
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6134319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741432 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6134320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741466 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6147350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146740590 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6147352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146741967 | Approved | 27000 | 0 | 2026-02-10
SEHORE | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6228973 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146738333 | Approved | 27000 | 0 | 2026-03-29
SEHORE | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729001027/IF/IAY/6228974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146739556 | Approved | 23490 | 0 | 2026-04-16
SEHORE | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1729001027/RC/22012034825906 — cc road aur nali nirman sitaram ke ghar se choki tak barkheda deva | Physically Completed | 105144 | 0 | 2024-09-06 | 2026-08-12
SEHORE | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1729001027/WC/22012035125277 — pokhar nirman | Ongoing | 326591.21 | 0 | 2023-10-04
SEHORE | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1729001027/WC/22012035206981 — Rain water harvesting panchyat bhavan | Approved | 0 | 0 | 2024-06-14
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1729001027/WC/22012035291727 — JGSA 20252025Recharge Structure hend ke pass mandir ke pass729001027/wc/22012035291717 | Approved | 25899.46 | 0 | 2025-04-14
SEHORE | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1729001027/WC/22012035291741 — JGSA 20252025Recharge Structure hend pum vahid gan me1729001027/w/c/22012035291736 | Approved | 25899.46 | 0 | 2025-04-14