## Work List
Exported on: 2026-10-12 17:23:11
Filters applied:
Data source: VBGRAMG
District: SEHORE
Block: All
Panchayat: KALYANPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729002010/AV/22012034656654 — शांतिधाम निर्माण कार्य ग्राम कान्याखेड़ी | Approved | 334906.09 | 0 | 2024-06-06
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1729002010/DP/22012034580869 — दूधी नदी किनारे बांस वृक्षा रोपण ग्राम कल्याणपुरा ग्राम पंचायत कल्याणपुरा | Physically Completed | 427106.07 | 0 | 2023-07-25 | 2026-09-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002010/IF/22012035613557 — EK BAGIYA MAA KE NAAM HITGRAHI SARITA /RAJU SINGH GRAM KALYANPURA GP KALYANPURA | Ongoing | 263510.03 | 0 | 2025-09-11
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002010/IF/22012035613609 — EK BAGIYA MAA KE NAAM HITGRAHI NEETU /JITENDRA SINGH GRAM KALYANPURA GP KALYANPURA | Ongoing | 263510.03 | 1800 | 2025-09-11
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4634602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130348293 | Completed | 27000 | 1701 | 2024-11-11 | 2026-10-01
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4672105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115396827 | Completed | 27000 | 1215 | 2024-10-18 | 2026-10-04
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4673910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119415321 | Completed | 27000 | 0 | 2024-10-18 | 2026-09-29
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4675236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119600028 | Completed | 27000 | 358 | 2024-10-18 | 2026-10-01
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4678922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130348164 | Completed | 27000 | 0 | 2024-10-18 | 2026-09-29
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4746876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114118621 | Completed | 27000 | 972 | 2024-11-11 | 2026-10-01
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4747649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115190429 | Physically Completed | 27000 | 0 | 2024-11-11 | 2026-10-01
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4761502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120852592 | Completed | 27000 | 0 | 2024-11-11 | 2026-09-29
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/4773991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125796043 | Completed | 27000 | 972 | 2024-11-11 | 2026-10-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5156558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119415415 | Completed | 23490 | 2088 | 2025-04-12 | 2026-07-31
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5172269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119599910 | Physically Completed | 23490 | 0 | 2025-04-05 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5173261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114772086 | Completed | 23490 | 1044 | 2025-04-05 | 2026-09-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5187806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120835150 | Completed | 23490 | 0 | 2025-04-12 | 2026-08-10
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5190697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119588840 | Physically Completed | 23490 | 0 | 2025-04-12 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5200711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120082492 | Completed | 23490 | 1044 | 2025-04-28 | 2026-09-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5228145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115397036 | Completed | 23490 | 0 | 2025-04-05 | 2026-08-10
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5235550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114118635 | Completed | 23490 | 1827 | 2025-04-12 | 2026-07-31
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5237884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119659849 | Completed | 23490 | 0 | 2025-04-28 | 2026-08-10
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5238524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114538361 | Completed | 23490 | 0 | 2025-04-12 | 2026-08-10
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5244217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115740135 | Completed | 23490 | 538 | 2025-04-05 | 2026-09-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5742433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120082393 | Completed | 23490 | 1044 | 2025-08-20 | 2026-09-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5743822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120835224 | Completed | 23490 | 1305 | 2025-08-20 | 2026-09-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5745563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130349567 | Completed | 23490 | 783 | 2025-08-20 | 2026-09-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5746783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119658926 | Completed | 23490 | 1827 | 2025-08-20 | 2026-07-31
ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/5937305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119659418 | Completed | 23490 | 8200 | 2026-05-23 | 2026-09-28
ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1729002010/IF/IAY/6227645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119659167 | Completed | 23490 | 783 | 2026-05-23 | 2026-09-28
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1729002010/RS/22012035128918 — नाली निर्माण कार्य प्रेम सिंह के मकान से ओमप्रकाश पुजारी के मकान की और ग्रामकल्याणपुरा ग्राम पंचायत | Approved | 16000 | 0 | 2024-06-20