## Work List
Exported on: 2026-09-12 00:36:43
Filters applied:
Data source: VBGRAMG
District: SEHORE
Block: All
Panchayat: RAMPURAKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHTA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1729002055/AV/22012034512755 — गोशाला निर्माण कार्य ग्राम रामपुरा कला | Ongoing | 3784582.21 | 392968.22 | 2020-08-10
ASHTA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1729002055/AV/22012034512757 — चारागाह विकास कार्य ग्राम रामपुरा कला | Ongoing | 792213.45 | 0 | 2021-01-19
ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG Building for Community | Construction of building/workshed for SHG | 1729002055/AV/22012034596493 — Daining Tabel Praimari School Awalikheda | Ongoing | 16093.2 | 0 | 2021-09-23
ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG Building for Community | Construction of building/workshed for SHG | 1729002055/AV/22012034596495 — DainingTabel Gram Rampurkalan | Ongoing | 16093.2 | 0 | 2021-09-23
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002055/IF/22012035446255 — JGSA 2025 Khet Talab Dev Singh /Chota ji Rampurakala | Approved | 450885.64 | 0 | 2025-04-14
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002055/IF/22012035616373 — Ek Bagiya Maa Ke Naam Rajal Bai / Parvat singh Rampurakalan | New | 0 | 0 | 2025-09-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002055/IF/22012035617125 — Ek Bagiya ma Ke Nam Rajal Bai /Parvat Rampurakala | New | 0 | 0 | 2025-09-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5270540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118837399 | Ongoing | 27000 | 0 | 2025-04-21
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5278130 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118835207 | Completed | 23490 | 0 | 2025-05-09 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5300050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118835173 | Completed | 23490 | 0 | 2025-05-09 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5304919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118835407 | Ongoing | 27000 | 0 | 2025-05-09
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5305955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118835467 | Ongoing | 27000 | 0 | 2025-04-21
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5316210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118834242 | Physically Completed | 27000 | 0 | 2025-07-28 | 2026-08-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5332109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130516165 | Ongoing | 27000 | 0 | 2025-05-09
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5691461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106509494 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5691800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106498351 | Ongoing | 27000 | 0 | 2025-07-28
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002055/IF/IAY/5691820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106525892 | Physically Completed | 23490 | 0 | 2025-07-28 | 2026-08-02
ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002055/RC/22012034523675 — Aproch Road Main Road Se Shantidham Tak Gram Awlikheda | Ongoing | 875050.13 | 0 | 2020-06-19
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002055/RC/22012034833907 — cc road Ram Singh ke ghar se kedar ke ghar tak Rampurakalan | New | 0 | 0 | 2024-08-15
ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002055/RC/22012034843864 — 15fc mnrega CC Road Badri Patidar ke ghar se Base Kha ke ghar ki or Rampurakala | Approved | 46000 | 0 | 2025-04-14
ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002055/RC/22012034847471 — CC Road Durgesh ke makan se Pani ki tanki or Rampurakala | Ongoing | 80000 | 0 | 2026-02-17
ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002055/RC/22012034853352 — CC Road Nirman Karya School Ke Kone Se School Ke Main Gate Ki Or Rampurakalan | Approved | 48000 | 0 | 2026-01-26
ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729002055/WC/22012034443272 — Check dam nirman - Lotiya nala | Ongoing | 1470819.04 | 0 | 2019-03-10
ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002055/WC/22012034530186 — Pokhar Nirman karya Dharedi Nale ke pas | Ongoing | 310386.65 | 0 | 2020-04-28
ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002055/WC/22012034530187 — Pokhar Nirman karya Lotiya nale par Rampura kala | Ongoing | 310386.65 | 0 | 2020-05-17
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1729002055/WC/22012034812606 — CRT Roof Rain Water Harvestingh Middile Schoole Gram Awalikheda | Ongoing | 22229.14 | 0 | 2021-09-15
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1729002055/WC/22012034812609 — CRT Roof Rain Water Harvestingh P Schoole Gram Awalikheda | Ongoing | 22229.14 | 0 | 2021-09-15