## Work List
Exported on: 2026-09-07 23:53:52
Filters applied:
Data source: VBGRAMG
District: SEHORE
Block: All
Panchayat: KHAMKHEDABEJNAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHTA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012034915513 — सेवा भूमी कपिलधारा कूप निर्माण रमेश आ सेवाराम खामखेड़ा बेजनाथ | Ongoing | 250732.62 | 0 | 2022-01-27
ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012035170713 — कपिल धारा कूप निर्माण मोहन लाल / घांसीराम | Ongoing | 282417.57 | 0 | 2023-10-07
ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012035170807 — कपिल धारा कूप निर्माण हजारी लाल /कोदा जी | Ongoing | 282417.57 | 0 | 2023-10-07
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012035175100 — कपिल धारा कूप निर्माण राम सिंह/ सिंगाराम | Ongoing | 282417.57 | 0 | 2025-02-17
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1729002085/IF/22012035230476 — Nandan faloudhan chandar singh/jagannath khamkhefa baijnath | Ongoing | 145050.83 | 0 | 2024-07-05
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1729002085/IF/22012035230793 — nandan faloudhan shivraj/devkaran gram panchayat khamkheda baijnath | Ongoing | 145050.83 | 0 | 2024-07-13
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012035522032 — कपिल धारा कूप निर्माण दिनेश कुमार / जगन्नाथ सिंह खामखेड़ा बैजनाथ 2025 | Approved | 0 | 0 | 2025-04-14
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012035522064 — कपिल धारा कूप निर्माण गायत्री बाई / विनोद कुमार खामखेड़ा बैजनाथ 2025 | Approved | 0 | 0 | 2025-04-14
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002085/IF/22012035522093 — कपिल धारा कूप निर्माण मुकेश कुमार / प्रहलाद सिंह खामखेड़ा 2025 | Approved | 0 | 0 | 2025-04-14
ASHTA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/2113851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4417734 | Approved | 27000 | 0 | 2019-06-13
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4742489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113715942 | Ongoing | 27000 | 0 | 2025-01-06
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4743630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933323 | Ongoing | 27000 | 0 | 2025-03-17
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4747472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115749979 | Ongoing | 27000 | 0 | 2024-11-23
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4749193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115949963 | Ongoing | 27000 | 0 | 2025-01-06
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4751563 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116677886 | Ongoing | 27000 | 0 | 2025-01-06
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4751728 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116957911 | Ongoing | 27000 | 0 | 2024-11-23
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4751729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116957954 | Ongoing | 27000 | 0 | 2025-01-06
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4755756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117845202 | Ongoing | 27000 | 0 | 2025-01-06
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/4796262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147670393 | Ongoing | 27000 | 0 | 2025-02-15
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5490337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115751533 | Ongoing | 27000 | 0 | 2025-07-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5490662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116958144 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-08-16
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5492194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113920657 | Ongoing | 27000 | 0 | 2025-07-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5492195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113923981 | Ongoing | 27000 | 4200 | 2025-05-21
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5493118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116719732 | Ongoing | 27000 | 0 | 2025-07-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5493667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115953950 | Ongoing | 27000 | 0 | 2025-05-21
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5493793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295851 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5571767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293923 | Physically Completed | 23490 | 0 | 2025-05-21 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5588502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122004528 | Ongoing | 27000 | 8700 | 2025-07-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5638525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120385127 | Ongoing | 27000 | 11100 | 2025-07-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5640449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113941166 | Ongoing | 27000 | 8400 | 2025-07-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5641675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116958336 | Ongoing | 27000 | 0 | 2025-07-01
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5691588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989726 | Ongoing | 27000 | 0 | 2025-07-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5691864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117632804 | Ongoing | 27000 | 12600 | 2025-07-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5691921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116958306 | Ongoing | 27000 | 12600 | 2025-07-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5720405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113713800 | Approved | 27000 | 0 | 2025-07-16
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295598 | Physically Completed | 23490 | 0 | 2025-08-22 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295730 | Approved | 27000 | 0 | 2025-04-24
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116957986 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116958622 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117629783 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117632978 | Ongoing | 27000 | 19500 | 2025-08-29
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633047 | Physically Completed | 23490 | 0 | 2025-08-29 | 2026-07-30
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293819 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5742984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117293849 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989652 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743614 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989681 | Approved | 27000 | 0 | 2025-03-13
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989766 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117011313 | Ongoing | 27000 | 0 | 2025-08-21
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117011375 | Physically Completed | 23490 | 0 | 2025-08-21 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117949008 | Physically Completed | 23490 | 0 | 2025-09-19 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117676695 | Physically Completed | 23490 | 0 | 2025-08-22 | 2026-07-30
ASHTA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5743882 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117676762 | Ongoing | 27000 | 16800 | 2026-08-14
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5744666 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116069235 | Approved | 27000 | 0 | 2025-03-13
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5744684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115375215 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117845602 | Physically Completed | 23490 | 0 | 2025-12-18 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116758964 | Physically Completed | 23490 | 0 | 2025-08-21 | 2026-07-30
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117295574 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989783 | Physically Completed | 23490 | 0 | 2025-08-22 | 2026-07-30
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989855 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745185 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116989899 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117845265 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115377788 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5745946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115750056 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5746737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115934581 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5747238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117676016 | Ongoing | 27000 | 0 | 2025-08-21
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5747782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117632911 | Physically Completed | 23490 | 0 | 2025-09-10 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5747785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116958417 | Approved | 27000 | 0 | 2025-04-15
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5747786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116958465 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5748014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115390913 | Physically Completed | 23490 | 0 | 2025-09-12 | 2026-07-30
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5748322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115402508 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5748423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120446143 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5749093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117011151 | Physically Completed | 23490 | 0 | 2025-08-29 | 2026-07-30
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/5749394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113802773 | Physically Completed | 23490 | 0 | 2025-08-29 | 2026-07-30
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/6192220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117676885 | Approved | 27000 | 0 | 2025-03-13
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/6195531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115949882 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/6206359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122558869 | Approved | 27000 | 0 | 2025-02-20
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/6208908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116990032 | Approved | 27000 | 0 | 2025-09-06
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002085/IF/IAY/6213154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117011233 | Approved | 27000 | 0 | 2025-09-06
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002085/RC/22012034837326 — सीसी रोड निर्माण माता मंदिर के पास खामखेड़ा बैजनाथ | Ongoing | 83000 | 0 | 2025-03-17
ASHTA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002085/RC/22012034844867 — सीसी रोड पलिया के ओटले से मांगलिक भवन तक ग्राम पंचायत खामखेड़ा बैजनाथ | Approved | 247000 | 0 | 2025-04-14
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002085/RS/22012035136442 — PVC पाईप लाईन व नाली निर्माण गल चौराहा से आर्य मंदिर की और खामखेड़ा 2025 | Approved | 52000 | 0 | 2025-02-28
ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1729002085/WC/22012035196767 — pokhar nirman1 pathari khamkheda baijnath | Ongoing | 489864.85 | 0 | 2024-06-14
ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1729002085/WC/22012035196771 — pokhar nirman2 pathari khamkheda baijnath | Ongoing | 489864.85 | 0 | 2024-06-14
ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002085/WC/22012035202682 — संकन पोण्ड निर्माण ईमली वाला खाल पर खामखेड़ा बैजनाथ | Approved | 0 | 0 | 2024-06-08
ASHTA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1729002085/WH/22012034929204 — चेक डैम से गाद निकालना गड़ी वाले की बीड़ के पास खामखेड़ा बेजनाथ | Ongoing | 75550.81 | 0 | 2022-04-22