## Work List
Exported on: 2026-10-13 13:04:15
Filters applied:
Data source: MGNREGA
District: SEHORE
Block: All
Panchayat: LORASKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002030/IF/891 — कपिलधारा कूप निर्माण कार्य मनोहर पिता घासीलाल लोरासकला | Completed | 223000 | 6000 | 2011-06-30 | 2013-07-04
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729002091/AV/22012034354556 — SANTIDHAM NIRMAN CHAPRI DEVKI | Physically Completed | 180000 | 170997.45 | 2017-07-31 | 2026-04-07
ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1729002091/AV/22012034562948 — boundry wall nirman panchayat bhavan parishar | Closed | 16660 | 0 | 2020-10-02
ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1729002091/AV/22012034570282 — डायनिंग टेबल निर्माण माध्यमिक शाला भवन लोरास कला | Completed | 21093.2 | 3474 | 2021-10-29 | 2023-11-29
ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1729002091/AV/22012034570283 — डायनिंग टेबल निर्माण प्राथमिक शाला भवन लोरास कला | Closed | 21093.2 | 0 | 2021-04-14
ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1729002091/AV/22012034604418 — 15th vit +manrega nali nirman loraskala panchayat bhavan ke pass | Physically Completed | 50356 | 52500 | 2022-03-21 | 2026-05-02
ASHTA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1729002091/AV/22012034608365 — 15th vit +manrega nali nirman loraskala high secondry school ke pass | Physically Completed | 56850 | 53856 | 2022-05-25 | 2026-05-02
ASHTA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1729002091/AV/22012034624125 — Khel Maidan Nirman High School Prangan Loraskala | Deleted | 0 | 0 | 2022-08-16
ASHTA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1729002091/AV/22012034624562 — Playground high school Loras kala | Ongoing | 139212.27 | 81206.18 | 2022-12-09
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of intrmediate and Link Water Drain-Comm / Construction of intermediate and Link Storm Water Drain for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1729002091/AV/22012034643511 — pani ki tanki nirman gram loraskala harijan mohola loraskala | Closed | 10543 | 0 | 2023-04-14
ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1729002091/DP/22012034435449 — plantation samsan side | Ongoing | 335000 | 16676 | 2019-02-14
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Shelter Belt Trees-Comm / Road Line Plantation of Shelter Belt Trees for Community | Plantation | 1729002091/DP/22012034580668 — Road side tree plantation pm road high school se hakimabad ki or gram loraskala | Ongoing | 427106.07 | 111723 | 2023-07-22
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1729002091/DP/22012034582168 — road side plantation prdhan mantri sadak pappu singh ke ghar se chapri ki or | Ongoing | 427106.07 | 102398 | 2023-07-26
ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1729002091/DP/22012034609049 — nirmal nir nirman samsan chapri GP loraskala | Ongoing | 585301.31 | 353654 | 2023-10-05
ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1729002091/DP/22012034609050 — nirmal nir nirman nursury loraskala GP loraskala | Ongoing | 585301.31 | 221 | 2023-10-05
ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1729002091/DP/22012034622562 — सर्वजनिक पोधारोपण शमशान लोरास कला | Ongoing | 453563.17 | 45510 | 2024-08-29
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1729002091/FP/22012034640440 — बाढ़ नियंत्रण चेनल का पुनरूत्थान ग्राम लोरास कला बलवान के खेत से माता मंदिर कि और ग्राम पंचायत लोरास | Approved | 110836.16 | 0 | 2024-06-08
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1000066877 — kapildharakup nirman-dev singh s/o ladhsingh | Completed | 295000 | 134288.8 | 2014-01-30 | 2017-06-27
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1000067099 — kapildharakup- soram bai w/o jivan singh | Completed | 295000 | 230712.16 | 2014-01-30 | 2017-01-27
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1000067171 — kapildharakup nirman - shivcharan s/o ramprasadh | Completed | 295000 | 149196.2 | 2014-01-30 | 2017-01-27
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1000069175 — kapildharakup papu s/o anar singh | Completed | 295000 | 252527.84 | 2014-02-06 | 2017-01-27
ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1264 — कपिलधारा कूप निर्माण कार्य रामचरण पिता नरबत लौरासकला | Completed | 223000 | 214207 | 2011-05-21 | 2013-08-05
ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1458 — Kapildhara kup nirman MOHANSINGH PITA KESHRSINGH | Completed | 242000 | 85000 | 2012-04-01 | 2013-10-07
ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1666 — कपिलधारा कुप निर्माण कार्य विक्रमसिह पिता बाफुसिह | Completed | 242000 | 121909 | 2012-05-18 | 2014-06-12
ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1828 — कपिलधारा कूप निर्माण कार्य धरमसिह पिता गंगाराम लोर | Completed | 242000 | 164602 | 2012-05-10 | 2014-03-31
ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002091/IF/1837 — कपिलधारा कूप निर्माण कार्य मोहनसिह पिता केशरसिह लोरसकला | Completed | 242000 | 75400 | 2012-04-30 | 2013-08-01
ASHTA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/1911 — कपिलधारा कूप निर्माण कार्य मुकेश पिता कालू लोरासकल | Completed | 242000 | 188426 | 2012-05-25 | 2014-03-27
ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/22012034407159 — KAPILDHARA KUP NIRMAN PAWAN SO MOHAN SINGH | Completed | 210000 | 192916 | 2018-05-12 | 2019-05-04
ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Block Plantation of Shelter Belt Trees for Individuals | Plantation | 1729002091/IF/22012034449766 — podharopan | Deleted | 0 | 0 | 2018-10-15
ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/22012034471260 — KAPILDHARAKUP NIRMAN DEVKARAN SINGH SO GHISILAL LORASKALA | Completed | 230400.79 | 207927.5 | 2019-03-08 | 2022-10-10
ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/22012035154471 — kapildhara kup nirman kedar singh S/o karan singh | Deleted | 0 | 0 | 2023-04-14
ASHTA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/22012035215913 — कपिलधारा कूप निर्माण केदार सिंह पिता करण सिंह ग्राम लोरास कलां | Closed | 282417.57 | 0 | 2024-01-26
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/22012035288431 — KAPILDHARAKUP NIRMAN MANGILAL SO UMRAV SINGH SINGH GRAM LORASKALA | Ongoing | 312155.12 | 220235.08 | 2025-03-12
ASHTA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/22012035304728 — kapildhara kup nirman chhatar singh s/o sukhram gram loraskala | Ongoing | 312155.12 | 222547.94 | 2025-03-25
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035425637 — Recharge Openwell hitgrahimulak devkaran s/o ghisilal gram loraskala | Deleted | 0 | 0 | 2025-04-14
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035426270 — dug Well recharge hitgrahi devkaran s/o ghisilal gram loraskala | Physically Completed | 25899.46 | 11210.8 | 2025-05-04 | 2026-04-26
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035437470 — dug Well recharge hitgrahi prem singh s/o ghisilal gram loraskala | Physically Completed | 25899.46 | 7559.11 | 2025-05-24 | 2026-04-15
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035440268 — JGSA 2025 Dug wall rechage hitgrahi devi singh s/o lad singh gram loraskala | Physically Completed | 25899.46 | 11203.01 | 2025-05-24 | 2026-04-26
ASHTA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1729002091/IF/22012035445880 — Khet talab nirman dhapu bai w/o ramcharan gram chhapri | Physically Completed | 450885.64 | 145716.48 | 2025-05-18 | 2026-04-30
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035460584 — JGSA 2025 dugwell recharge structure hitgrahi mohan singh S/O keshar singh gram loraskala | Physically Completed | 25899.46 | 13017.62 | 2025-05-24 | 2026-04-26
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035570310 — Dugwell recharge mohan singh /balkrishan gram loraskala | Approved | 0 | 0 | 2025-06-11
ASHTA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1729002091/IF/22012035570345 — Dugwell recharge structure ramesh /kannu gram loraskala | Approved | 0 | 0 | 2025-06-12
ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/265 — कपिलधारा कूप निर्माण कार्य सजनसिह पिता फतेसिह लौरास कला | Completed | 214000 | 170150 | 2009-01-22 | 2010-04-21
ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/278 — कपिलधारा कूप निर्माण कार्य मोहनसिह पिता बालकशिन लोरासकला | Completed | 214000 | 176972 | 2009-01-05 | 2010-04-21
ASHTA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/279 — कपिलधारा कूप निर्माण कार्य सुखराम पिता कनीराम लोरासकला | Completed | 214000 | 103770 | 2009-04-16 | 2012-03-31
ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/280 — कपिलधारा कूप निर्माण कार्य मेहरवान पिता कनिराम लोरासकला | Completed | 214000 | 139330 | 2009-02-22 | 2009-12-31
ASHTA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/889 — कपिलधारा कूप निर्माण कार्य हीरालाल पिता पन्‍नालाल लोरासकला | Completed | 223000 | 136544 | 2011-02-23 | 2013-08-04
ASHTA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/892 — कपिलधारा कूप निर्माण कार्य मनोहर पिता घीसीलाल लोरासकला | Completed | 223000 | 61373 | 2011-06-02 | 2013-07-05
ASHTA | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1729002091/IF/893 — कपिलधारा कूप निर्माण कार्य केदारसिह पिता प्रथ्‍वीसिह लोरासकला | Completed | 223000 | 97899 | 2011-03-16 | 2013-10-07
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/9926705934 — kapildharakup_bapu singh s/o sankar lal | Completed | 295000 | 14367 | 2014-02-22 | 2016-10-03
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/9926708650 — kapildhara kup- prem singh s/o ghisilal | Completed | 295000 | 144536.7 | 2014-02-27 | 2017-03-10
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/9926708673 — kapildharakup-vikram s/o hemraj | Completed | 295000 | 287349.4 | 2014-02-27 | 2017-01-27
ASHTA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Goat Shelter / Construction of Goat Shelter for Individuals | Goat Shelter | 1729002091/IF/9926710726 — goat shelter niman ramcharan s/o narbad singh | Completed | 47000 | 146 | 2014-03-01 | 2016-10-03
ASHTA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/9993680364 — indra avash nirman makhmal s/o misrilal | Completed | 14310 | 6351 | 2015-10-15 | 2017-08-10
ASHTA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/9993680370 — indra avash nirman ramprsadh s/o ladsingh | Completed | 1431000000 | 11533 | 2015-10-15 | 2017-08-10
ASHTA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/1863155 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4208259 | Deleted | 15660 | 0 | 2018-06-23
ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/4080189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122709841 | Completed | 18360 | 18156 | 2022-09-06 | 2023-01-31
ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/4279551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125055691 | Completed | 18360 | 18088 | 2022-10-07 | 2023-11-29
ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/4349221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122708518 | Physically Completed | 18360 | 18292 | 2022-10-07 | 2024-11-21
ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/4363939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117101582 | Completed | 18360 | 18224 | 2023-01-19 | 2024-05-22
ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/4385689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119832798 | Completed | 18360 | 17680 | 2023-01-04 | 2023-09-04
ASHTA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/4385715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124637374 | Completed | 18360 | 18258 | 2023-01-04 | 2023-09-04
ASHTA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/513470 — Construction of IAY House -IAY REG. NO. MP2421117 | Completed | 15030 | 16482 | 2017-02-10 | 2018-01-15
ASHTA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1729002091/IF/IAY/517723 — Construction of IAY House -IAY REG. NO. MP2503146 | Completed | 15030 | 17462 | 2017-02-10 | 2018-11-09
ASHTA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1729002091/IF/कुप निर्माण हेमराज पिता लाडसिंह ग्रा — कुप निर्माण हेमराज पिता लाडसिंह ग्राम लोरास कलां | Completed | 156400 | 80400 | 2008-05-20 | 2010-04-06
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1729002091/LD/22012034314995 — SANTI DHAM NIRMAN GRAM LORASKALA | Completed | 180000 | 169024 | 2017-06-02 | 2018-07-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1729002091/PG/22012034366168 — playground | Deleted | 0 | 0 | 2017-10-02
ASHTA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002091/RC/185 — सी.सी रोड निर्माण कार्य लोरास कला | Completed | 200000 | 22386 | 2010-01-07 | 2010-12-04
ASHTA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002091/RC/206 — नवीन ग्रेवलरोड निर्माण कार्य लौरासकला से शमशान तक लौरासकला | Completed | 474000 | 159305 | 2009-12-13 | 2011-07-15
ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034168794 — Panch Parmeswar C.C.Road T.S.No.2135 Koraskala | Completed | 200900 | 91070 | 2013-05-31 | 2015-11-04
ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034186198 — Panch Parmeshwar C.C. Road T.S.No.1123 Loras Kala | Completed | 204180 | 192268 | 2013-09-27 | 2014-03-27
ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034195873 — panchparmeshwar cc road gendalal ke ghar ke pas ki | Completed | 204000 | 112998 | 2013-12-27 | 2014-10-24
ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034197877 — panchparmeshwar | Completed | 200000 | 191052 | 2014-01-09 | 2014-03-25
ASHTA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002091/RC/22012034202726 — gram khat sadak talab se sukram ke kup tak | Completed | 1347000 | 199814 | 2014-02-06 | 2017-03-15
ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034286408 — panchparmeshwer c c road | Completed | 130410 | 135604 | 2016-04-07 | 2017-10-10
ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034318795 — c c road nirman vidhayaknidhi +nrega | Completed | 80000 | 49977 | 2016-12-29 | 2017-11-15
ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034318807 — c c road nirman 14th vitiayoge+nrega | Completed | 98000 | 62862 | 2016-12-29 | 2017-11-15
ASHTA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034327291 — c c road nirman panchparmeshwar raghuveer ke makan se | Ongoing | 25000 | 167 | 2017-02-16
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002091/RC/22012034340232 — sudur sampark yojna loraskala se tandat ak | Deleted | 1409000 | 0 | 2017-05-01
ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034397302 — c c road nirman 14th vit ayoge +manrega mata choke se mulchand ke ghar tak and mata chok se hanuman | Completed | 51000 | 49190 | 2019-02-12 | 2020-05-10
ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034439019 — ccroad | Deleted | 0 | 0 | 2019-01-26
ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034449527 — c c road nirman pm road se higher secondry school tak | Deleted | 30600 | 0 | 2019-01-26
ASHTA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034449541 — c c road nirman pm road se higher secondry school tak | Completed | 30600 | 30270 | 2019-03-08 | 2020-12-25
ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034515560 — c c road nirman samsan se gav ki or | Completed | 60000 | 69540 | 2020-06-27 | 2020-11-15
ASHTA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034516990 — CC road nirman gajraj ke Ghar see jasmat ke Ghar tak | Completed | 45000 | 39944 | 2020-02-18 | 2020-05-10
ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1729002091/RC/22012034523772 — maintainance workof gravel road loraskala to chhapri | Completed | 90930.4 | 89246.94 | 2021-03-10 | 2021-10-30
ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034538257 — c c road nirman bhadar ke godawn se kelash ke ghar tak | Completed | 53550 | 43950 | 2021-03-11 | 2021-11-18
ASHTA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034563318 — c c road nirman kelash ke ghar se mohan ke ghar tak | Completed | 28878 | 31845 | 2021-12-22 | 2026-01-20
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034581820 — 15fc+mnrega cc road nirman pm road se makhmal ke ghar ki or gram loraskala gp loraskala | Ongoing | 36000 | 32929 | 2023-10-06
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1729002091/RC/22012034643492 — खेत सड़क निर्माण -पीएम रोड से बगडावदा कांकड़ की और | Closed | 0 | 0 | 2023-04-14
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034653337 — C C road nirman mukesh ke makan se ram mandir ki or | Completed | 16055 | 15992 | 2023-10-05 | 2024-07-28
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034660428 — C C ROAD NIRMAN GRAM CHAPRI RAM MADIR KE PASS | Closed | 61600 | 0 | 2023-08-15
ASHTA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1729002091/RC/22012034834172 — C C ROAD NIRMAN RAM SINGH KE GHAR SE HANUMAT KE GHAR TAK GRAM LORASKALA | Approved | 39288 | 0 | 2024-08-15
ASHTA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1729002091/RC/350 — शांतीधाम उपयोजना कार्य ग्राम लोरासकला | Completed | 184000 | 155677 | 2011-01-03 | 2012-11-15
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034346639 — sochalye nirman jagannath singh ganpat singh | Completed | 12000 | 11952 | 2017-05-19 | 2017-11-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034347425 — sochalaye nirman karan singh lal s/o ganpat | Completed | 12000 | 11952 | 2017-05-19 | 2017-11-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034347430 — sochalye nirman - mulchand s/o munsilal | Completed | 12000 | 11952 | 2017-05-19 | 2017-11-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034347433 — schalye nirman devji s/o joraver | Completed | 12000 | 11952 | 2017-05-20 | 2017-11-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034350137 — sochalye nirman dev singh s/o lad singh | Completed | 12000 | 11952 | 2017-05-20 | 2017-11-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355588 — sochalye nirman ramesh s/o bapu singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355590 — sochalye nirman prem singh S/o ghisilal | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355591 — sochalye nirman rajmal S/o gangaram | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355592 — sochalye nirman ramesh S/o babu lal | Completed | 12000 | 2752 | 2017-06-28 | 2017-07-15
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355593 — sochalye nirman madan singh madho singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355594 — sochalye nirman gokul bai S/o ramcharan | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355595 — sochalye nirman mangilal S/o garver singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355596 — sochalye nirman Vikram singh S/o bapu singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355597 — sochalye nirman hemraj s/o lad singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355598 — sochalye nirman ambaram S/o harnath | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355599 — sochalye nirman Papu s/o anar singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355600 — sochalye nirman kelash s/o man singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034355601 — sochalye nirman bane singh S/o prathvi singh | Completed | 12000 | 11952 | 2017-06-28 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034356781 — SOCHALYE NIRMAN DEVKARAN SING S/O GHISILAL | Completed | 12000 | 11952 | 2017-07-05 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034362728 — SOCHALYE NIRMAN SAVAI SINGH S/O RAMKISHAN | Completed | 12000 | 11264 | 2017-07-31 | 2017-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034362731 — SOCHALYE NIRMAN AMAR SINGH S/O BHAGIRATH | Completed | 12000 | 11952 | 2017-07-31 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034362734 — SOCHALYE NIRMAN JAGANNATH S/O KANIRAM | Completed | 12000 | 11952 | 2017-07-31 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034362736 — SOCHALYE NIRMAN BALKISHAN S/O PRTAP SINGH | Completed | 12000 | 11952 | 2017-07-31 | 2018-10-10
ASHTA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1729002091/RS/22012034363254 — sochalye nirman fhulkuwer bai bane singh | Completed | 12000 | 2752 | 2017-08-02 | 2017-10-25
ASHTA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1729002091/RS/22012034511774 — sochaye nirman panchayat bhawan parishar | Closed | 16800 | 0 | 2021-03-01
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002091/RS/22012034704192 — PVC nali nirman 1.chhater ke Ghar se gajraj ke Ghar tak2.ramprsad ke Ghar se dev ji gram loraskala | Ongoing | 29978 | 24531 | 2023-09-18
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002091/RS/22012034704195 — C C Nali nirman Ram mandir ke pass gram chapri GP loraskala | Ongoing | 27000 | 26741 | 2023-10-05
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002091/RS/22012034704224 — R C C Nali nirman mandir chok se chacha khedi ki or gram chapri | Ongoing | 25120 | 18785 | 2023-10-06
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1729002091/RS/22012034706053 — PVC NALI NIRMAN GRAM LORASKALA sujan singh ke ghar ke pas se mukesh ke ghar ki or | Completed | 27175 | 25415 | 2023-10-05 | 2025-02-14
ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1729002091/WC/22012034442852 — recharge pits school 1 handpump ke pass | Completed | 11217.58 | 7392 | 2019-03-08 | 2020-01-15
ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1729002091/WC/22012034442854 — recharge pits school 2 handpump ke pass | Completed | 10337.14 | 8448 | 2019-03-08 | 2020-01-15
ASHTA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1729002091/WC/22012034442857 — recharge pits high school handpump ke pass | Completed | 10337.14 | 6324 | 2019-03-08 | 2020-01-15
ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002091/WC/22012034544641 — Pokar nirman loraskala goha ke pas chapri road par | Completed | 332572.21 | 275880 | 2020-05-09 | 2022-04-15
ASHTA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002091/WC/22012034617112 — पोखर ि‍निर्माण | Closed | 0 | 0 | 2021-01-26
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729002091/WC/22012034760717 — roof rain water harvesting panchayat bhavan loraskala | Closed | 9970 | 0 | 2021-04-14
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729002091/WC/22012034812750 — roof water harvesting middle school loraskala | Completed | 22229.14 | 11784 | 2021-10-30 | 2024-07-18
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1729002091/WC/22012034812751 — roof water harvesting middle school lchapri gram panchayat loraskala | Closed | 22229.14 | 0 | 2021-08-15
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002091/WC/22012034883186 — नाला विस्तारिकरणकृपाल सिंह के खेत से हरेंद्र के खेत तक | Closed | 0 | 0 | 2021-06-15
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002091/WC/22012035115664 — Pokhar nirman gram chapri mehrwan ka khet ke pass | Completed | 458813.83 | 340240 | 2023-10-05 | 2025-05-21
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002091/WC/22012035189458 — Pokhar nirman gram loraskala juga ke pass gram panchayat loraskala | Completed | 385261.22 | 282587 | 2024-03-14 | 2025-05-21
ASHTA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1729002091/WC/22012035191900 — बाय डाइवर्जन चेनल :( नाला गहरीकरण बलवान के खेत से माता मं) ग्राम लोरास कला ग्राम पंचायत लोरास कला | Closed | 0 | 0 | 2024-01-26
ASHTA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1729002091/WC/22012035201715 — संकन पोंड ग्राम लोरास कला माता मंदिर वाले नाले पर ग्राम पंचायत लोरास कला | Approved | 78228.55 | 0 | 2024-06-08
ASHTA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1729002091/WC/321 — निर्मलनीर कूप निर्माण कार्य लोरासकला | Completed | 211000 | 210542 | 2010-04-21 | 2012-08-24
ASHTA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002091/WH/22012034442517 — talab gahari karan chhapri | Deleted | 0 | 0 | 2020-01-26
ASHTA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002091/WH/22012034448574 — nala vistarikaran mata mandir se gyan singh ke khet tak | Closed | 0 | 0 | 2021-04-14
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002091/WH/22012034936292 — नाला विस्तारीकरण कार्य आम वाले महाराज से माता मंदिर की ओर लोरासकला | Completed | 245971.47 | 192491 | 2023-06-23 | 2025-12-24
ASHTA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1729002091/WH/22012034938435 — नाला विस्तारीकरण कार्य बलवान के खेत से माता मंदिर की ओर लोरासकला | Closed | 0 | 0 | 2023-08-15