## Work List
Exported on: 2026-10-14 11:52:25
Filters applied:
Data source: VBGRAMG
District: RAISEN
Block: All
Panchayat: GUNDRAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SANCHI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1730001082/DP/22012034597920 — AMRIT VATIKA NIRMAN ( HAIGH SCHOOL KE PAS)GUNDRAI | Ongoing | 55847.4 | 0 | 2023-09-09
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035583890 — EK BAGIYA MA KE NAAM PARWATI BAI GRAM GUNDRAI | New | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035583896 — EK BAGIYA MA KE NAAM PHULWATI GRAM CHANDANGODA | New | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035597838 — EK BAGIYA MA KE NAAM SULOCHANA / OMPRAKASH GRAM GUNDRAI | New | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600026 — EK BAGIYA MA KE NAAM SULOCHAMA / OMPRAKASH GRAM GUNDRAI | Approved | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600027 — EK BAGIYA MA KE NAAM PARWATI BAI / MADANLAL GRAM GUNDRAI | Approved | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600030 — EK BAGIYA MA KE NAAM BAIJANTI BAI / BHOLERAM GRAM GUNDRAI | Approved | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035600635 — EK BAGIYA MA KE NAAM BABLI BAI GRAM CHANDANGODA | Approved | 0 | 0 | 2025-06-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035604782 — EK BAGIYA MA KE NAAM PHULWATI BAI GRAM CHANDANGODA | Ongoing | 129651.41 | 16200 | 2025-09-05
SANCHI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730001082/IF/22012035604787 — EK BAGIYA MA KE NAAM KISHORI GRAM CHANDANGODA | Ongoing | 129651.41 | 12600 | 2025-09-05
SANCHI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730001082/RC/22012034846895 — CC ROAD JASWANT NAYAK KE GHAR SE PUROSHOTTAM NAYAK KE GHAR KI AUR | Approved | 50000 | 0 | 2025-04-14
SANCHI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730001082/RC/VB/YD/22012034854612 — Constr of Cement Concrete Roads for Comm GUNDRAI | Approved | 0 | 0 | 2026-09-02
SANCHI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1730001082/RS/VB/YD/22012035139953 — Construction of Soak Pit for 1 | Ongoing | 27804.31 | 0 | 2026-10-06
SANCHI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1730001082/WC/22012035220242 — Pashu Hoj Shantidham ke pas Gundrai Tola | Approved | 10000 | 0 | 2024-04-14
SANCHI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1730001082/WC/VB/YD/22012035334986 — Constr of Masonry/CC Anicut for 1 GUNDRAI | Approved | 0 | 0 | 2026-07-25