## Work List
Exported on: 2026-10-24 06:33:53
Filters applied:
Data source: VBGRAMG
District: RAISEN
Block: All
Panchayat: AGARIYA KALAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GAIRATGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1730002001/DP/22012034578263 — SAMUDAYAK KOOP HANUMAN MANDIR KE PASS GRAM AGRIYAKALAN | Ongoing | 537251.35 | 0 | 2023-12-13
GAIRATGANJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1730002001/IF/22012034517653 — kapildhara koop rajaram/sahiba | Ongoing | 234458.57 | 0 | 2020-05-27
GAIRATGANJ | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1730002001/IF/22012034519344 — Kapildharakoop bhura/panna | Ongoing | 234458.57 | 0 | 2021-10-24
GAIRATGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1730002001/IF/22012035369129 — Jgsa recharge structure munnalal /bhaiyalal agariyakalan | New | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002001/IF/22012035586084 — EK BAGIYA MAA KE NAAM ANGURI BAI NAMDEV MP-30-002-001-002/99 AGARIYAKALAN | Approved | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002001/IF/22012035605218 — EK BAGIYA MAA KE NAAM GEETA BAI MP-30-002-001-002/378 GRAM AGARIYAKALAN | Ongoing | 129363.82 | 0 | 2025-09-22
GAIRATGANJ | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/3038238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4862099 | Physically Completed | 23490 | 0 | 2022-05-10 | 2026-08-09
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4578095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118103294 | Ongoing | 27000 | 0 | 2024-09-22
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4635938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131329726 | Ongoing | 27000 | 0 | 2024-09-25
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4694291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116145581 | Ongoing | 27000 | 6300 | 2024-12-16
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4939193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106693795 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4950208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634781 | Ongoing | 27000 | 0 | 2025-03-22
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4950691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117916788 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4951316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118417611 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4984979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106772397 | Ongoing | 27000 | 0 | 2025-04-11
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4984980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106772414 | Ongoing | 27000 | 0 | 2025-04-11
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/4999872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116972541 | Physically Completed | 27000 | 16500 | 2025-04-27 | 2026-10-04
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5000065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117581224 | Ongoing | 27000 | 8400 | 2025-03-22
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5000359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116971600 | Ongoing | 27000 | 0 | 2025-04-22
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5002846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118106974 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5003756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118228857 | Ongoing | 27000 | 0 | 2025-03-22
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5004983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117916632 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5005035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117941295 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5455418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118107097 | Ongoing | 27000 | 0 | 2025-04-27
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5598277 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633535 | Ongoing | 27000 | 0 | 2025-08-28
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5598447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116145690 | Ongoing | 27000 | 0 | 2025-08-28
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5656596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634707 | Ongoing | 27000 | 25200 | 2025-08-28
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5656792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131332215 | Ongoing | 27000 | 0 | 2025-08-28
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5657050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116145830 | Ongoing | 27000 | 0 | 2025-08-28
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5950532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106637256 | Ongoing | 27000 | 12600 | 2026-09-02
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5953796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634528 | Ongoing | 27000 | 16800 | 2026-09-02
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5953797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634611 | Ongoing | 27000 | 16800 | 2026-07-24
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5953997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117941226 | Ongoing | 27000 | 26700 | 2026-07-24
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5955784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116970977 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5955785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116971502 | Ongoing | 27000 | 26700 | 2026-07-24
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5955786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116971824 | Ongoing | 27000 | 26700 | 2026-07-24
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5956504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118228922 | Physically Completed | 27000 | 26700 | 2026-09-02 | 2026-10-11
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5956505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118229226 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5956955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123883339 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5956970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116971541 | Ongoing | 27000 | 16800 | 2026-09-02
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5960037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117634286 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5960040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117635353 | Ongoing | 27000 | 26700 | 2026-07-24
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5963457 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633600 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5963701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116145641 | Ongoing | 27000 | 16800 | 2026-07-24
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/5966443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121946472 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6129332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117635686 | Approved | 27000 | 0 | 2026-02-26
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6131699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118229938 | Ongoing | 27000 | 25200 | 2026-09-02
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6140479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131296069 | Ongoing | 27000 | 22800 | 2026-07-16
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6228367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116972332 | Ongoing | 27000 | 12600 | 2026-09-02
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6228774 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106366802 | Approved | 27000 | 0 | 2026-03-17
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6229952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118106746 | Approved | 23490 | 0 | 2026-04-07
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6279575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131334040 | Approved | 27000 | 0 | 2026-03-17
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/6372901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117581179 | Approved | 27000 | 0 | 2026-07-09
GAIRATGANJ | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1730002001/IF/IAY/834002 — Construction of IAY House -IAY REG. NO. MP1257121 | Ongoing | 27000 | 0 | 2020-09-09
GAIRATGANJ | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1730002001/RC/22012034843938 — SUDUR SAMPARK NIRMAN ALAMPUR PAKKI SADAK SE AGARIYAKALAN KI OR GADAGHANT NADI TAK GRAM AGARIYAKALAN | Approved | 0 | 0 | 2025-04-14
GAIRATGANJ | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1730002001/RC/VB/YD/22012034855563 — Construction of Gravel Road Roads for 1 | Approved | 0 | 0 | 2026-10-22