## Work List
Exported on: 2026-09-07 21:31:14
Filters applied:
Data source: VBGRAMG
District: RAISEN
Block: All
Panchayat: CHANDPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GAIRATGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1730002012/AV/22012034663128 — PULIYA NIRMAN KARYA CHOUKIDAR KE KHET KE PASS GRAM CHANDPUR | Approved | 53000 | 0 | 2024-08-16
GAIRATGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1730002012/IF/22012035349896 — JGSA2025recharge structure koop harnam singh s/o badri prasad | New | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002012/IF/22012035602754 — एक बगिया माँ के नाम लताबाई /वीरसिंह लोधी | New | 0 | 0 | 2025-08-15
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002012/IF/22012035602837 — एक पेड़ माँ के नाम लता बाई /वीर सिंह | Approved | 0 | 0 | 2025-08-16
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002012/IF/22012035603061 — एक पेड़ माँ के नाम रचना / बहादुर सिंह चांदपुर | Approved | 0 | 0 | 2025-08-16
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/5955480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145558488 | Ongoing | 27000 | 0 | 2026-04-01
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/5956971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117518273 | Ongoing | 27000 | 0 | 2026-04-07
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/5956985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113852922 | Ongoing | 27000 | 600 | 2026-04-09
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/5959599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142522492 | Ongoing | 27000 | 600 | 2026-04-07
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/5960241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145583862 | Ongoing | 27000 | 0 | 2026-04-07
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/5961770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144877348 | Ongoing | 27000 | 3600 | 2026-04-01
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/6004908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142525285 | Physically Completed | 23490 | 0 | 2026-04-01 | 2026-08-02
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/6009959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145578424 | Ongoing | 27000 | 0 | 2026-04-01
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002012/IF/IAY/6128825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142308690 | Ongoing | 27000 | 0 | 2026-04-24
GAIRATGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730002012/RC/22012034833438 — CC ROAD NIRMAN KARYA GOPAL LODHI KE GHAR SE HARIRAM KE GHAR KI OR GRAM CHANDPUR | Approved | 46000 | 0 | 2024-04-14