## Work List
Exported on: 2026-09-03 04:17:29
Filters applied:
Data source: VBGRAMG
District: RAISEN
Block: All
Panchayat: SAHAJPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
GAIRATGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730002043/IF/22012035199478 — KHET TALAB NIRMAN KARYA RAGHUVEER/NIRPAT SINGH GRAM TIJALPUR | Ongoing | 367862.6 | 0 | 2024-03-16
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002043/IF/22012035591662 — EK BAGIYA MAA KE NAAM SANDHYA YADAV MP-30-002-043-005/88 GRAM SAHAJPUR | Ongoing | 129174.22 | 0 | 2025-10-08
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730002043/IF/22012035598865 — JGSA 2025 KAPIL DHARA KOOP NIRMAN KARYA JAGDISH LODHI / KHILAN SINGH | Approved | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730002043/IF/22012035598878 — JGSA 2025 KAPIL DHARA KOOP NIRMAN | Approved | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002043/IF/22012035605721 — EK BAGIYA MAA KE NAAM PRABHA BAI MP-30-002-043-004/13-d GRAM TIJALPUR | Ongoing | 129138.2 | 0 | 2025-09-05
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002043/IF/22012035625935 — EK BAGIYA MAA KE NAAM VIMALA ADIWASI MP-30-002-043-001/127-A GRAM BAMHORI GHAT | Approved | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002043/IF/22012035625943 — EK BAGIYA MAA KE NAAM PUSHPA BAI MP-30-002-043-001/33-X GRAM BAMHORI GHAT | New | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730002043/IF/22012035625944 — EK BAGIYA MAA KE NAAM PUSHPA BAI MP-30-002-043-001/33-X GRAM BAMHORI GHAT | Approved | 0 | 0 | 2025-04-14
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1730002043/IF/22012035653520 — KAPILDHARA KOOP NIRMAN KARYA SURESH/JAMNAPRASAD ST GRAM BAMHORI GHAT | Approved | 0 | 0 | 2025-10-02
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4564284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116088668 | Ongoing | 27000 | 8400 | 2025-03-21
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4592771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122049464 | Ongoing | 27000 | 9600 | 2025-07-29
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4790610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141339110 | Ongoing | 27000 | 5100 | 2025-05-14
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4870289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116087159 | Ongoing | 27000 | 0 | 2024-12-27
GAIRATGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4872176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126306984 | Ongoing | 27000 | 0 | 2025-02-13
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4990359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011624 | Ongoing | 27000 | 0 | 2025-04-23
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4990362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107013502 | Ongoing | 27000 | 4800 | 2025-04-16
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/4990365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107013715 | Ongoing | 27000 | 3900 | 2025-05-16
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5002765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117543830 | Ongoing | 27000 | 2400 | 2025-07-29
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5020826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126369048 | Ongoing | 27000 | 0 | 2025-07-29
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5021181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126404432 | Ongoing | 27000 | 7200 | 2025-07-29
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5021208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126412629 | Ongoing | 27000 | 0 | 2025-07-29
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5656992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126304876 | Physically Completed | 23490 | 0 | 2025-07-29 | 2026-07-26
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5686224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107010066 | Ongoing | 27000 | 8700 | 2025-07-29
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5960452 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116088345 | Ongoing | 27000 | 9600 | 2026-03-25
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/5965459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107011349 | Ongoing | 27000 | 0 | 2026-03-25
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6126012 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141339213 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6126013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141339264 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6128180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116090149 | Ongoing | 27000 | 0 | 2026-08-20
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6129551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107004111 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6134779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126639289 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6140232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126462784 | Ongoing | 27000 | 0 | 2026-08-20
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6140320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126369850 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6148167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107012160 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6149655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138888293 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6149656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138888328 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6149657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138888385 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6158005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107010283 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6158420 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127228115 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6159089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107009604 | Ongoing | 27000 | 4800 | 2026-07-11
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6173879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116086754 | Approved | 27000 | 0 | 2026-02-19
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6228659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125804550 | Ongoing | 27000 | 0 | 2026-08-20
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6228661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126368282 | Ongoing | 27000 | 0 | 2026-08-20
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6228729 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126414887 | Approved | 23490 | 0 | 2026-04-22
GAIRATGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6228730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126418241 | Approved | 27000 | 0 | 2026-03-17
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6228828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107008529 | Ongoing | 27000 | 0 | 2026-06-03
GAIRATGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730002043/IF/IAY/6229143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116086681 | Ongoing | 27000 | 0 | 2026-06-03