## Work List
Exported on: 2026-10-21 06:58:11
Filters applied:
Data source: MGNREGA
District: RAISEN
Block: All
Panchayat: SIMRODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Infra for Liquid Biomanure for Comm / Construction of Infrastructure for Liquid Biomanure for Community | Bio-Fertilizer | 1730004080/AV/22012034660590 — नाली आर सी सी छत्रपाल के घर से पुलिया तक, सिमरोदा | Completed | 28800 | 20169 | 2024-09-28 | 2026-05-26
OBEDULLAHGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wastelands Block Plantation-Sericulture-Comm / Wasteland Block Plantation of Sericulture Trees for Community | Plantation | 1730004080/DP/22012034595163 — AMRIT VATIKA NIMAN KARY CHANDLA KHEDI SE HANUMAN MANDIR PARISAR GRAM CHANDLAKHEDIRAJMAU | Closed | 0 | 0 | 2023-08-01
OBEDULLAHGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1730004080/IC/22012034885695 — खेत तालाब निर्माण दपतिराम/भोगीराम चांदलाखेडी | New | 0 | 0 | 2024-10-02
OBEDULLAHGANJ | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1730004080/IC/22012034885696 — खेत तालाब निर्माण लक्ष्‍मीबाई/भोगीराम, चांदलाखेडी, सिमरोदा | Approved | 137475.93 | 0 | 2024-10-02
OBEDULLAHGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/22012035121280 — pm awas malkhan singh/ bhogiram gram dadrod | Closed | 18360 | 0 | 2023-04-14
OBEDULLAHGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/22012035121286 — pm awas sevaram /banshilal gram dadrod | Closed | 18360 | 0 | 2023-04-14
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1730004080/IF/22012035260109 — cc road nirman karya parwati bai ke ghar se mukesh meena ke ghar ki or simroda | Deleted | 0 | 0 | 2024-09-18
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1730004080/IF/22012035260110 — cc road nirman karya parwati bai ke ghar se mukesh meena ke ghar ki or simroda | Deleted | 0 | 0 | 2024-09-18
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730004080/IF/22012035268581 — खेत तालाब निर्माण पतिराम/भोगीराम, चांदलाखेडी, सिमरोदा | Deleted | 0 | 0 | 2024-10-02
OBEDULLAHGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry/CC Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1730004080/IF/22012035319763 — khet talab nirman kary patiram / bhogiram gram chandla khedi simroda | Physically Completed | 450885.64 | 417390.2 | 2025-04-18 | 2026-04-01
OBEDULLAHGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry/CC Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1730004080/IF/22012035319769 — khet talab nirman kary awadhnarayan / ram singh gram simroda | Physically Completed | 450885.64 | 434392.59 | 2025-04-18 | 2026-04-21
OBEDULLAHGANJ | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Masonry/CC Anicut for Individuals / Construction of Masonry/CC Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1730004080/IF/22012035416460 — khet talab nirman kary Shiv charan / Balmukand gram simroda | Physically Completed | 450885.64 | 439352.65 | 2025-04-29 | 2026-04-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730004080/IF/22012035571855 — khet talab nirman karya mohar bai duarka pasad simroda | Physically Completed | 55865.38 | 43670.52 | 2025-06-21 | 2026-04-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730004080/IF/22012035571857 — khet talab nirman karya rajendra duarka prasad simroda | Physically Completed | 55865.38 | 49151.52 | 2025-06-21 | 2026-04-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1730004080/IF/22012035579753 — IAY PMAY MP116476556 | Approved | 0 | 0 | 2025-04-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035601042 — Ek Bagiya Maa Ke Naam Sudama Bai Dadrod Simroda | Deleted | 0 | 0 | 2025-07-15
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035601291 — Ek Bagiya Man Ke Nam SUDAMA BAI DADROD SIMRODA | Deleted | 0 | 0 | 2025-07-15
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035601735 — Ek Bagiya Man Ke Nam SUDAMA BAI DADROD SIMRODA | Ongoing | 169192.21 | 31052.91 | 2025-09-03
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035601738 — Ek Bagiya Man Ke Nam POOJA MEENA DADROD SIMRODA | Ongoing | 169192.21 | 94123.93 | 2025-09-03
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035601742 — Ek Bagiya Man Ke Nam MANJU BAI DADROD SIMRODA | Approved | 0 | 0 | 2025-07-15
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035602804 — Ek Bagiya Man Ke Nam SONU MEENA DADROD SIMRODA | Ongoing | 169192.21 | 84987.95 | 2025-09-03
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035606255 — Ek Bagiya Man Ke Nam LAXMI BAI DADROD SIMRODA | Ongoing | 169192.21 | 70372.86 | 2025-09-03
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730004080/IF/22012035629718 — Ek Bagiya Man Ke Nam Munni Bai Dadrod Simroda | Deleted | 0 | 0 | 2025-07-15
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1730004080/IF/22012035631687 — Ek Bagiya Man Ke Nam Munni Bai Dadrod Simroda | Ongoing | 169192.94 | 13050 | 2025-11-04
OBEDULLAHGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4402162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120783056 | Completed | 19890 | 18122 | 2023-07-31 | 2024-01-11
OBEDULLAHGANJ | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4404787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126978601 | Completed | 19890 | 18122 | 2023-07-31 | 2024-01-11
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4568025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116502773 | Completed | 23490 | 21753 | 2024-09-28 | 2025-07-29
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4568029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116503672 | Ongoing | 23490 | 19926 | 2024-09-28
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4568034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116504288 | Completed | 23490 | 20412 | 2024-09-28 | 2025-07-28
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4568043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116505512 | Completed | 21870 | 21627 | 2024-09-28 | 2025-02-13
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4568047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116505957 | Completed | 23490 | 20280 | 2024-09-28 | 2026-01-23
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4584795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120049014 | Physically Completed | 23490 | 20412 | 2024-09-28 | 2026-04-19
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4592276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122136334 | Completed | 21870 | 21627 | 2024-09-28 | 2025-02-21
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4597863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123043371 | Completed | 21870 | 20412 | 2024-09-28 | 2025-02-19
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4633659 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129727626 | Completed | 23490 | 20412 | 2024-10-05 | 2025-06-15
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4672193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476188 | Completed | 23490 | 20898 | 2024-09-28 | 2025-06-15
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4672194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476257 | Completed | 21870 | 18711 | 2024-10-05 | 2025-08-26
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4672195 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476474 | Completed | 21870 | 21627 | 2024-09-28 | 2025-02-13
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4672974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116502816 | Completed | 23490 | 20412 | 2024-10-05 | 2026-01-23
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4672975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116502874 | Completed | 23490 | 20898 | 2024-09-28 | 2025-07-09
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4672980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116504978 | Ongoing | 23490 | 21627 | 2024-10-05
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4694800 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116505352 | Completed | 23490 | 20412 | 2024-10-05 | 2025-06-15
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4783389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129913229 | Completed | 21870 | 20169 | 2024-11-20 | 2025-02-19
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4881306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500929 | Completed | 21870 | 21384 | 2025-01-08 | 2025-03-24
OBEDULLAHGANJ | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/4883635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500496 | Completed | 21870 | 18711 | 2025-01-08 | 2025-08-26
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5821557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120057684 | Completed | 23490 | 21924 | 2025-10-25 | 2025-11-17
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5821558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120059302 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5821765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128504393 | Ongoing | 23490 | 18270 | 2025-12-20
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5821968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500431 | Completed | 23490 | 20358 | 2025-11-23 | 2026-02-24
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5821969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116506303 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5822384 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116503209 | Ongoing | 23490 | 19575 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5822385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116503306 | Completed | 23490 | 21924 | 2025-10-25 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5822386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116503390 | Ongoing | 23490 | 21924 | 2026-01-22
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5822387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116505712 | Completed | 23490 | 21924 | 2025-10-25 | 2025-11-17
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5822388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116505741 | Completed | 23490 | 21924 | 2025-10-25 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5822940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120784579 | Completed | 23490 | 21924 | 2025-11-08 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5823611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128509377 | Completed | 23490 | 21924 | 2025-12-20 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5823612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128510135 | Completed | 23490 | 21924 | 2025-10-25 | 2025-11-17
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5825128 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128505034 | Completed | 23490 | 21924 | 2025-12-20 | 2026-02-04
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5825868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116502941 | Ongoing | 23490 | 21924 | 2026-01-22
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5826851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115121863 | Ongoing | 23490 | 18270 | 2026-01-08
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5828244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128508062 | Completed | 23490 | 21924 | 2025-11-08 | 2025-11-27
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125519309 | Completed | 23490 | 21924 | 2026-01-08 | 2026-02-04
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129911962 | Completed | 23490 | 21924 | 2025-12-20 | 2026-02-04
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116505794 | Completed | 23490 | 21924 | 2025-11-08 | 2025-11-27
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127705944 | Completed | 23490 | 21924 | 2026-01-22 | 2026-02-24
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476815 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129894342 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129904335 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128708236 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5843958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128710446 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120784388 | Physically Completed | 23490 | 18270 | 2026-01-22 | 2026-02-15
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120784906 | Completed | 23490 | 21924 | 2025-11-08 | 2025-12-02
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126993020 | Completed | 23490 | 21924 | 2025-12-20 | 2026-02-02
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123048866 | Physically Completed | 23490 | 18270 | 2025-12-20 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126960804 | Ongoing | 23490 | 14616 | 2026-01-22
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126961786 | Completed | 23490 | 21924 | 2025-11-08 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126962818 | Completed | 23490 | 21924 | 2025-11-08 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844488 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126985979 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844558 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127682822 | Completed | 23490 | 21924 | 2026-01-08 | 2026-02-04
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127705694 | Physically Completed | 23490 | 18270 | 2026-01-22 | 2026-02-18
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127689657 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150245314 | Completed | 23490 | 20358 | 2025-11-23 | 2026-02-24
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5844989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120784712 | Ongoing | 23490 | 18270 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116506084 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116503802 | Completed | 23490 | 21924 | 2025-10-25 | 2026-01-01
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476556 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122218925 | Completed | 23490 | 21924 | 2025-12-06 | 2026-01-23
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150212447 | Completed | 23490 | 21924 | 2026-01-08 | 2026-02-04
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120043844 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5845815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150204691 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/5856799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127703418 | Ongoing | 23490 | 21924 | 2026-02-05
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6061805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128533009 | Ongoing | 23490 | 5481 | 2026-06-07
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6090468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127706162 | Ongoing | 23490 | 21924 | 2026-04-20
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6181842 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120045280 | Ongoing | 23490 | 21924 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6188154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128534404 | Ongoing | 23490 | 21924 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6188353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138214276 | Ongoing | 23490 | 18270 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6190941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476020 | Ongoing | 23490 | 14616 | 2026-06-07
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6194628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116503934 | Ongoing | 23490 | 21924 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6197475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116476130 | Ongoing | 23490 | 21924 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6197789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116500558 | Ongoing | 23490 | 14616 | 2026-06-07
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6200181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116477047 | Ongoing | 23490 | 18270 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6200188 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120047214 | Ongoing | 23490 | 18270 | 2026-05-24
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6203302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129913822 | Ongoing | 23490 | 21924 | 2026-05-06
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6212439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP139511877 | Ongoing | 23490 | 14616 | 2026-06-07
OBEDULLAHGANJ | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730004080/IF/IAY/6215826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128623090 | Ongoing | 23490 | 10962 | 2026-06-07
OBEDULLAHGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730004080/RC/22012034681237 — C. C. ROAD NIRMAN KARY SATISH PAAL KE GHAR SE DEVIRAM KE GHAR TAK GRAM SIMRODA | Completed | 55650 | 55405.88 | 2024-03-09 | 2024-11-05
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730004080/RC/22012034827508 — cc road nirman karya parwati bai ke ghar se mukesh meena ke ghar ki or simroda | Completed | 32850 | 27701.5 | 2024-10-03 | 2025-03-03
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730004080/RC/22012034827583 — सी सी रोड डामर रोड से स्‍कूल तरफ, सिमरोदा | Approved | 46200 | 0 | 2024-08-29
OBEDULLAHGANJ | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730004080/RC/22012034835712 — cc road nirman karya school se ghnasiram ke ghar taraf simroda | Completed | 58000 | 50373 | 2025-06-02 | 2025-10-08
OBEDULLAHGANJ | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730004080/RC/22012034838558 — सी सी रोड निर्माण डामर रोड से स्‍कूल तक, सिमरोदा | Completed | 46200 | 37845 | 2025-07-07 | 2025-09-25
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730004080/RC/22012034838561 — cc road nirman karya deviram ke ghar se school taraf simroda | Approved | 0 | 0 | 2025-02-15
OBEDULLAHGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730004080/RS/22012034694851 — नाली हयूम पाईप निर्माण चांदलाखेडी, सिमरोदा | Deleted | 0 | 0 | 2023-04-14
OBEDULLAHGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730004080/RS/22012034694852 — नाली हयूम पाईप निर्माण चांदलाखेडी, सिमरोदा | Completed | 130000 | 128401 | 2023-07-25 | 2024-06-01
OBEDULLAHGANJ | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730004080/RS/22012035118614 — नाली हयूम पाईप घनश्‍याम के घर से वेयर हाउस नाली तक, चांदलाखेडी, सिमरोदा | Completed | 15000 | 14144 | 2024-01-10 | 2024-06-01
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730004080/RS/22012035132990 — नाली निर्माण कच्‍ची नाली खुमान सिंह की पुलिया से गोहा तक, चांदलाखेडी, सिमरोदा | Completed | 99259.96 | 84321.94 | 2024-11-06 | 2025-02-13
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730004080/RS/22012035132994 — नाली निर्माण कच्‍ची नाली स्‍कूल पुलिया से वकलिया तक, दादरोद सिमरोदा | Completed | 99695.84 | 82376.69 | 2024-11-06 | 2025-02-13
OBEDULLAHGANJ | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730004080/RS/22012035134744 — NALI NIRMAN KACHHI NALI PULIYA SE PUMP HOUSH KI OR SIMRODA | Completed | 97792.06 | 81044.64 | 2025-01-29 | 2025-12-29
OBEDULLAHGANJ | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1730004080/WC/22012035081784 — Stop dam nirman agrawal ji ke khet ke pas dadrod Simroda | Closed | 965231.36 | 0 | 2023-04-04