## Work List
Exported on: 2026-10-19 13:34:43
Filters applied:
Data source: VBGRAMG
District: RAISEN
Block: All
Panchayat: AKOLA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730005002/IF/22012035349333 — खेत तालाब निर्माण कार्य हमीर सिंह के खेत में ग्राम ढीमरढ़ाना | Approved | 450885.64 | 0 | 2025-04-14
BADI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1730005002/IF/22012035472580 — JGSA 2025 Recharge Structure Lakshman baretha gp akola | Approved | 0 | 0 | 2025-04-24
BADI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1730005002/IF/22012035472600 — JGSA 2025 Recharge Structure ramesh harijan gp akola | Approved | 0 | 0 | 2025-04-24
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/5821679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105885839 | Completed | 27000 | 2100 | 2025-10-21 | 2026-10-16
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/5822798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135924422 | Ongoing | 27000 | 16500 | 2026-08-16
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/5826981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115237008 | Physically Completed | 23490 | 0 | 2025-12-23 | 2026-08-02
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6006653 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131448341 | Physically Completed | 23490 | 0 | 2026-05-16 | 2026-08-02
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6006654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131448613 | Ongoing | 27000 | 26700 | 2026-08-12
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6010574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132010225 | Physically Completed | 27000 | 0 | 2026-05-16 | 2026-09-13
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6187261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131448688 | Ongoing | 27000 | 2100 | 2026-05-29
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6208795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132010242 | Physically Completed | 27000 | 18300 | 2026-07-14 | 2026-09-13
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6209301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132079816 | Ongoing | 27000 | 14100 | 2026-08-13
BADI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6321030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132079833 | Ongoing | 27000 | 0 | 2026-10-15
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005002/IF/IAY/6330970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP135924121 | Approved | 27000 | 0 | 2025-02-05
BADI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730005002/RC/22012034842387 — सीसीरोड निर्माण कार्य छहमासिया के मकान से दिनदयाल के मकान की ओर | Approved | 20000 | 0 | 2025-04-01
BADI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730005002/RC/VB/YD/22012034855051 — सी सी रोड निर्माण कार्य अकोला | Approved | 0 | 0 | 2026-07-02