## Work List
Exported on: 2026-10-18 12:28:58
Filters applied:
Data source: MGNREGA + VBGRAMG
District: RAISEN
Block: All
Panchayat: BHILADIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
BADI | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1730005017/AV/22012034600728 — पोषण वाटिका निर्माण शासकीय शाला प्रांगण भिलाड़िया | Closed | 9343.73 | 0 | 2021-09-15
BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1730005017/AV/22012034634669 — पुलिया निर्माण कार्य सिरवाड़ा रोड ग्राम पंचायत भिलाड़िया | Completed | 254794.14 | 207220.68 | 2023-09-07 | 2024-05-12
BADI | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1730005017/AV/22012034661848 — बाउन्ड्री वाल निर्माण कार्य माध्यमिक शाला भवन परिसर | Completed | 35000 | 32562 | 2024-11-29 | 2025-01-19
BADI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/DP/22012034229624 — सोख्ता गड्डा निर्माण हनुमान माडिया के सामने | Deleted | 20000 | 0 | 2016-04-08
BADI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/DP/22012034229625 — सोख्ता गड्डा निर्माण बलीराम /छोटे बरेठा के पीछे | Deleted | 20000 | 0 | 2016-05-09
BADI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/DP/22012034229627 — सोख्ता गड्डा निर्माण कन्हैया/हकम के माकन के पीछे | Deleted | 20000 | 0 | 2016-05-09
BADI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/DP/22012034229723 — सोखता गडडा निर्माण भवानी सिह/मनोहर सिंह के मकान के पास | Deleted | 20000 | 0 | 2016-04-08
BADI | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/DP/22012034229744 — सोखता गडडा निमाॅण आटा चककी के पास | Deleted | 20000 | 0 | 2015-10-02
BADI | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land development / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/DP/22012034237825 — सोख्ता गड्डा सीताराम पुर्विया के घर के पास | Deleted | 0 | 0 | 2017-01-26
BADI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1730005017/DP/22012034242787 — सार्वजनिक परिसर में वृक्षारोपण निर्माण कार्य भिलाडिया | Deleted | 84000 | 0 | 2017-05-24
BADI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1730005017/DP/22012034489419 — गोकुल केवट के घर के पास सोख्ता गड्ढा निर्माण भिलाड़िया | Completed | 14283.77 | 6840 | 2020-08-07 | 2023-09-16
BADI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1730005017/DP/22012034584909 — बृक्षारोपण कार्य (मेरी माटी मेरा देश ) तालाब के पास भिलाड़िया | Closed | 55847.4 | 0 | 2023-04-14
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034345559 — सार्वजनिक परिसरखेल मैदान में वृक्षारोपण | Completed | 84000 | 20096 | 2017-06-26 | 2018-08-24
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034346969 — रोड साईड में वृक्षारोपण कार्य गुरारीया सड़क भिलाडिया | Completed | 335000 | 21128 | 2017-06-24 | 2019-08-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034351518 — सार्वजनिक परिसर में वृक्षारोपण कार्य भिलाडिया | Completed | 335000 | 22160 | 2017-06-24 | 2019-08-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034351534 — सर्वजनिक पथ वृछा रोपन कार्य | Closed | 335000 | 0 | 2017-06-02
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034357555 — हनुमान जी के मंदिर से पाजरा रास्ता | Completed | 335000 | 104092 | 2017-06-27 | 2021-12-12
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034357560 — वृक्षारोपण सामुदायिक परिसर | Completed | 335000 | 20784 | 2017-06-27 | 2019-08-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034360024 — road side lantation breli raste par | Completed | 335000 | 22160 | 2017-06-28 | 2019-08-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034360029 — road side plantation rivar raste par | Completed | 335000 | 147652 | 2017-07-01 | 2021-12-13
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034360032 — road side plantation tola ke pass | Completed | 335000 | 3096 | 2017-07-01 | 2019-08-29
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034360036 — road side plantation school ke samene | Completed | 582000 | 4128 | 2017-07-01 | 2019-08-29
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1730005017/IF/22012034360042 — road side plantation shantidham ke raste par | Completed | 335000 | 21128 | 2017-06-28 | 2019-08-15
BADI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1730005017/IF/22012034601123 — नितिन/धर्मेश कुमार के खेत की मेड में बृक्षारोपण कार्य भिलाड़िया | Completed | 135587.2 | 52862 | 2020-09-19 | 2024-11-27
BADI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1730005017/IF/22012034612621 — मिथलेश/गौरीशंकर के खेत की मेड़ पर बृक्षारोपण कार्य ग्राम पंचायत भिलाड़िया | Completed | 135587.2 | 49997 | 2020-09-28 | 2024-11-27
BADI | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1730005017/IF/22012034929689 — सेठ सिंह लीच पिट निर्माण कार्य | Completed | 9916.27 | 1804 | 2022-02-05 | 2025-02-09
BADI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1730005017/IF/22012034929693 — प्रकाश केवट लीच पिट निर्माण कार्य | Closed | 9916.27 | 0 | 2021-10-02
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1730005017/IF/22012035229961 — MED BANDHAN RATNA SHILPI | Completed | 52872.84 | 45198 | 2024-06-13 | 2024-11-27
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1730005017/IF/22012035229967 — MED BANDHAN KALIRAM | Approved | 51817.38 | 0 | 2024-06-08
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1730005017/IF/22012035229969 — MED BANDHAN CHAIN SINGH | Approved | 52872.84 | 0 | 2024-06-08
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1730005017/IF/22012035229971 — MED BANDHAN HALKE BHAIYA | Completed | 52615.41 | 46413 | 2024-06-26 | 2024-11-27
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1730005017/IF/22012035562583 — JGSA 2025 Khet Talab Nirman Kiran Bai Thakur | Physically Completed | 55865.38 | 46860 | 2025-06-06 | 2026-04-20
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1003954 — Construction of IAY House -IAY REG. NO. MP1214033 | Completed | 15480 | 15504 | 2017-08-14 | 2018-05-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1018382 — Construction of IAY House -IAY REG. NO. MP1871930 | Completed | 17100 | 15278 | 2017-09-12 | 2023-04-04
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1018386 — Construction of IAY House -IAY REG. NO. MP1872046 | Completed | 15480 | 14704 | 2017-08-14 | 2018-08-28
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019073 — Construction of IAY House -IAY REG. NO. MP1900824 | Completed | 15480 | 14704 | 2017-08-14 | 2019-01-08
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019556 — Construction of IAY House -IAY REG. NO. MP1918618 | Completed | 15480 | 15208 | 2017-09-12 | 2018-06-23
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019638 — Construction of IAY House -IAY REG. NO. MP1922091 | Completed | 15480 | 15320 | 2017-08-14 | 2018-05-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019639 — Construction of IAY House -IAY REG. NO. MP1922129 | Completed | 15480 | 15588 | 2017-08-14 | 2018-05-27
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019640 — Construction of IAY House -IAY REG. NO. MP1922136 | Completed | 15480 | 15208 | 2017-09-12 | 2018-08-28
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019960 — Construction of IAY House -IAY REG. NO. MP1935727 | Completed | 15480 | 15504 | 2017-08-14 | 2018-05-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1019992 — Construction of IAY House -IAY REG. NO. MP1937160 | Completed | 15480 | 15368 | 2017-08-14 | 2018-07-14
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1020338 — Construction of IAY House -IAY REG. NO. MP1953381 | Completed | 15480 | 15368 | 2017-08-14 | 2018-05-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1020339 — Construction of IAY House -IAY REG. NO. MP1953390 | Completed | 15480 | 15688 | 2017-08-14 | 2018-05-15
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1020774 — Construction of IAY House -IAY REG. NO. MP1972754 | Completed | 15480 | 14660 | 2017-08-14 | 2018-08-28
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1021741 — Construction of IAY House -IAY REG. NO. MP2011868 | Completed | 15480 | 15160 | 2017-09-12 | 2018-06-07
BADI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1022073 — Construction of IAY House -IAY REG. NO. MP2025925 | Completed | 15480 | 15320 | 2017-08-14 | 2018-05-15
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553372 — Construction of IAY House -IAY REG. NO. MP1972180 | Completed | 15480 | 14442 | 2018-05-02 | 2019-04-12
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553373 — Construction of IAY House -IAY REG. NO. MP1973299 | Completed | 15480 | 14094 | 2018-05-01 | 2019-04-15
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553408 — Construction of IAY House -IAY REG. NO. MP1985685 | Completed | 15480 | 14094 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553456 — Construction of IAY House -IAY REG. NO. MP2011879 | Completed | 15480 | 15486 | 2018-05-02 | 2018-11-01
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553461 — Construction of IAY House -IAY REG. NO. MP2014263 | Completed | 15480 | 15138 | 2018-05-02 | 2019-03-15
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553481 — Construction of IAY House -IAY REG. NO. MP2021846 | Completed | 15480 | 15660 | 2018-05-02 | 2018-11-15
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553489 — Construction of IAY House -IAY REG. NO. MP2025941 | Completed | 15480 | 15486 | 2018-05-01 | 2019-03-13
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553519 — Construction of IAY House -IAY REG. NO. MP2036012 | Completed | 15480 | 15486 | 2018-05-02 | 2018-10-12
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553520 — Construction of IAY House -IAY REG. NO. MP2036079 | Completed | 15480 | 15486 | 2018-05-02 | 2018-09-25
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553542 — Construction of IAY House -IAY REG. NO. MP2044510 | Completed | 15480 | 15312 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1553671 — Construction of IAY House -IAY REG. NO. MP2117296 | Completed | 15480 | 14616 | 2018-05-02 | 2019-03-15
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1554895 — Construction of IAY House -IAY REG. NO. MP2600715 | Completed | 15480 | 15486 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1554965 — Construction of IAY House -IAY REG. NO. MP2631014 | Completed | 15480 | 16530 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1554966 — Construction of IAY House -IAY REG. NO. MP2631033 | Completed | 15480 | 15486 | 2018-05-02 | 2018-12-12
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1555057 — Construction of IAY House -IAY REG. NO. MP2682395 | Completed | 15480 | 14790 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1556471 — Construction of IAY House -IAY REG. NO. MP3230343 | Completed | 15480 | 16356 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1556479 — Construction of IAY House -IAY REG. NO. MP3234786 | Completed | 15480 | 15312 | 2018-05-02 | 2018-12-12
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1556480 — Construction of IAY House -IAY REG. NO. MP3234803 | Completed | 15480 | 15486 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1556483 — Construction of IAY House -IAY REG. NO. MP3236514 | Completed | 15480 | 15312 | 2018-05-02 | 2018-11-05
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1556484 — Construction of IAY House -IAY REG. NO. MP3237070 | Completed | 15480 | 15312 | 2018-05-02 | 2018-11-05
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1556624 — Construction of IAY House -IAY REG. NO. MP3301925 | Completed | 15480 | 15312 | 2018-05-02 | 2018-11-30
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1557352 — Construction of IAY House -IAY REG. NO. MP3568031 | Completed | 15480 | 15312 | 2018-05-02 | 2019-01-08
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1557410 — Construction of IAY House -IAY REG. NO. MP3592991 | Completed | 15480 | 15312 | 2018-05-02 | 2018-11-05
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1557486 — Construction of IAY House -IAY REG. NO. MP3625049 | Completed | 15480 | 15660 | 2018-05-02 | 2018-11-15
BADI | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/1557980 — Construction of IAY House -IAY REG. NO. MP3867090 | Completed | 15480 | 15486 | 2018-05-02 | 2018-11-15
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2051941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3518728 | Completed | 15840 | 15796 | 2019-07-16 | 2020-06-26
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2059518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3624610 | Completed | 15840 | 15840 | 2019-07-16 | 2020-01-29
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2060125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3633453 | Completed | 15840 | 16092 | 2019-07-16 | 2020-06-01
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2060379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3638768 | Completed | 15840 | 15840 | 2019-07-16 | 2019-11-19
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2060392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3639372 | Completed | 15840 | 15924 | 2019-07-16 | 2020-05-03
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2060979 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3648824 | Completed | 15840 | 15656 | 2019-07-16 | 2020-06-30
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2082163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3870411 | Completed | 15840 | 15734 | 2019-07-16 | 2020-05-21
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2084669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3905091 | Completed | 15840 | 15840 | 2019-07-16 | 2019-11-19
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2085733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3921031 | Completed | 15840 | 15840 | 2019-07-16 | 2019-11-19
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2085788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3921844 | Completed | 15840 | 15840 | 2019-07-16 | 2019-11-19
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2086343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3921833 | Completed | 17100 | 16340 | 2019-07-16 | 2023-04-04
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2086631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3930755 | Completed | 15840 | 15734 | 2019-07-16 | 2020-05-21
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2086713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3930738 | Completed | 15840 | 15818 | 2019-07-16 | 2020-05-21
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2087684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3948649 | Completed | 15840 | 15840 | 2019-07-16 | 2019-11-27
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2088354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3953924 | Completed | 15840 | 15840 | 2019-07-16 | 2020-01-29
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2088407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3953467 | Completed | 15840 | 15882 | 2019-07-16 | 2020-04-29
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2265044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3921854 | Completed | 17100 | 16442 | 2019-08-01 | 2024-05-10
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2265156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3615069 | Completed | 15840 | 16050 | 2019-08-01 | 2020-06-01
BADI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/2309562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2600767 | Completed | 17100 | 16722 | 2020-02-24 | 2020-09-30
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3064811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4889311 | Completed | 17370 | 17199 | 2021-07-01 | 2023-11-28
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3065259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4248721 | Completed | 17370 | 16791 | 2021-07-01 | 2022-07-05
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3065450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5589267 | Completed | 17370 | 15054 | 2021-07-01 | 2023-04-04
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3065454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5589271 | Completed | 17370 | 16716 | 2021-07-01 | 2023-07-01
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3066182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5593123 | Completed | 17370 | 17346 | 2021-09-03 | 2024-03-11
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3066183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5593838 | Completed | 17370 | 17219 | 2021-09-03 | 2024-09-13
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3066337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5575327 | Completed | 17370 | 16806 | 2021-07-01 | 2022-09-27
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3066340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5575867 | Completed | 17370 | 17356 | 2022-12-19 | 2024-03-11
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3066489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4110034 | Completed | 17370 | 16791 | 2021-07-01 | 2022-04-21
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3140648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5615513 | Completed | 17370 | 17050 | 2021-07-01 | 2022-08-23
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3140649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5615580 | Completed | 17370 | 17238 | 2023-02-22 | 2024-08-03
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3140651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5615941 | Completed | 17370 | 17226 | 2021-07-01 | 2022-09-27
BADI | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3279689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5623376 | Completed | 17370 | 17262 | 2022-02-27 | 2024-01-29
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3646640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1900881 | Completed | 17370 | 17221 | 2022-04-25 | 2023-11-28
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3646646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1972841 | Completed | 17370 | 17220 | 2022-04-25 | 2024-02-24
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3646941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3567828 | Completed | 17370 | 16932 | 2022-04-25 | 2022-11-18
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3647276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4486229 | Completed | 17370 | 17136 | 2022-05-01 | 2022-09-27
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3985141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124826117 | Completed | 18360 | 18360 | 2022-07-14 | 2023-01-20
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/3985164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124839381 | Completed | 18360 | 18207 | 2022-11-12 | 2023-07-21
BADI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4013259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125625052 | Completed | 18360 | 18276 | 2023-06-17 | 2024-09-02
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4013264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125629797 | Completed | 18360 | 17340 | 2022-07-14 | 2023-04-04
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4022346 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100548 | Completed | 18360 | 18360 | 2022-07-14 | 2023-01-20
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4022347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100552 | Completed | 18360 | 17136 | 2022-07-14 | 2023-04-04
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4217663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100546 | Completed | 18360 | 18360 | 2022-08-13 | 2024-10-02
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4320516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124849283 | Completed | 18360 | 17850 | 2022-12-19 | 2024-03-11
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4365976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124847595 | Completed | 18360 | 17798 | 2022-12-05 | 2024-01-29
BADI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4377902 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100534 | Completed | 23490 | 18600 | 2023-06-17 | 2025-10-25
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4377903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100541 | Completed | 18360 | 18190 | 2022-12-19 | 2023-09-16
BADI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4388066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125627493 | Completed | 18360 | 17760 | 2023-02-22 | 2024-07-01
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4613606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125631011 | Completed | 23490 | 17916 | 2024-09-24 | 2025-05-10
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4613624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125634270 | Completed | 21870 | 21627 | 2024-10-12 | 2025-02-25
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4613645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125636735 | Completed | 21870 | 21627 | 2024-10-08 | 2025-02-20
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4613657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125639219 | Completed | 21870 | 21870 | 2024-10-12 | 2025-03-16
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4618529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126124482 | Completed | 21870 | 19197 | 2024-10-01 | 2025-04-07
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4623113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126670807 | Completed | 23490 | 22482 | 2024-10-01 | 2026-02-16
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4640820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100515 | Completed | 21870 | 21384 | 2024-09-24 | 2025-03-16
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/4678306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126075303 | Physically Completed | 27000 | 16425 | 2024-10-12 | 2026-09-13
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4678310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126077609 | Completed | 23490 | 21006 | 2024-10-12 | 2025-12-16
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4678311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126078695 | Completed | 23490 | 21753 | 2024-11-05 | 2026-05-24
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4678995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100565 | Completed | 23490 | 21141 | 2024-10-09 | 2025-05-10
BADI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/475065 — Construction of IAY House -IAY REG. NO. MP1900796 | Completed | 15030 | 15200 | 2017-02-17 | 2018-06-23
BADI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/476466 — Construction of IAY House -IAY REG. NO. MP1922161 | Completed | 15030 | 14868 | 2017-02-17 | 2018-08-28
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4773455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125633176 | Completed | 23490 | 22050 | 2024-11-07 | 2026-01-24
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/4773466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125635488 | Ongoing | 27000 | 22980 | 2024-11-07
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4782148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126080948 | Completed | 23490 | 19440 | 2024-11-07 | 2025-05-09
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4788577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134401274 | Completed | 23490 | 20898 | 2024-11-07 | 2025-05-09
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4912717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100536 | Completed | 23490 | 23229 | 2025-06-06 | 2026-03-19
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4912745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134430934 | Completed | 23490 | 22599 | 2025-03-25 | 2025-12-20
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4914136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124867703 | Completed | 23490 | 23121 | 2025-03-25 | 2026-02-06
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/4914239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126079109 | Completed | 23490 | 23364 | 2025-03-19 | 2026-02-12
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/5019165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125637933 | Completed | 23490 | 23382 | 2025-03-25 | 2026-02-12
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/5082972 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126079670 | Completed | 23490 | 23382 | 2025-03-25 | 2026-02-12
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/5084186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126962732 | Completed | 23490 | 23274 | 2025-03-25 | 2026-02-12
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/5084207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126967292 | Completed | 23490 | 21141 | 2025-06-18 | 2025-10-16
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/5361681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126965875 | Ongoing | 27000 | 14616 | 2025-08-02
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/5370833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125632231 | Ongoing | 27000 | 22743 | 2025-08-02
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/5374763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126081478 | Completed | 23490 | 22968 | 2025-09-20 | 2025-12-21
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/5400204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134100504 | Ongoing | 27000 | 21924 | 2025-10-17
BADI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/5724264 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126963762 | Approved | 27000 | 0 | 2025-07-16
BADI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730005017/IF/IAY/5726302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125626260 | Approved | 27000 | 0 | 2025-02-05
BADI | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1730005017/IF/IAY/597529 — Construction of IAY House -IAY REG. NO. MP1083145 | Completed | 15030 | 16392 | 2017-02-17 | 2018-03-10
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263155 — मेड बंधान निर्माण कार्य हरिराम/आसाराम | Deleted | 40000 | 0 | 2015-10-02
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263187 — मेड़ बंधान निर्माण कार्य प्रभु/रामदयाल | Deleted | 40000 | 0 | 2016-04-06
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263266 — मेडबंधान निर्माण कार्य मंशाराम/आशाराम | Deleted | 40000 | 0 | 2016-04-08
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263267 — मेडबंधान निर्माण कार्य मुरारी/गुलाब | Deleted | 40000 | 0 | 2016-04-08
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263490 — मेड़बधान निमार्ण कायँ रतनसिंह | Deleted | 40000 | 0 | 2016-04-08
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263495 — मेड़बंधान निर्माण कार्य भगवत /करिया | Deleted | 40000 | 0 | 2016-04-09
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263499 — मेड बंधान निर्माण कार्य भडुआ /अलुआ | Deleted | 40000 | 0 | 2015-12-09
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263510 — मेडबंधान निर्माण कार्य हरिराम/काशीराम | Deleted | 40000 | 0 | 2016-04-08
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263513 — मेड बंधान निर्माण कार्य रामेश्वर /रामसिंह | Deleted | 40000 | 0 | 2016-04-09
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1730005017/LD/22012034263515 — मेड बंधान निर्माण कार्य चैन सिंह /कमल सिंह | Deleted | 40000 | 0 | 2016-04-09
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1730005017/LD/22012034293274 — शांति धाम नदी के पास | Completed | 225000 | 226647.49 | 2016-11-14 | 2018-07-20
BADI | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1730005017/LD/22012034543328 — समतलीकरण पांजरा रास्ते के पास ग्राम पंचायत भिलाडिया | Completed | 69889.81 | 47991 | 2021-03-25 | 2024-09-23
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1730005017/OP/9425889589 — बकरी आश्रय निर्माण संतोष /बाबूलाल | Deleted | 67000 | 0 | 2015-10-02
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1730005017/OP/9425889592 — बकरी आश्रय निर्माण जुम्मन /बली खा | Deleted | 67000 | 0 | 2015-10-02
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1730005017/OP/9425889594 — बकरी आश्रय निर्माण जालम /अलुआ | Deleted | 67000 | 0 | 2015-10-02
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1730005017/OP/9425889596 — बकरी आश्रय निर्माण गुड्डू /जयराम | Deleted | 67000 | 0 | 2015-10-02
BADI | 2015-2016 | D--RURAL INFRASTUCTURE / Other Works | Production of building material / Production of building material for Community | Construction of Other Community Building/Assets | 1730005017/OP/9425889597 — बकरी आश्रय निर्माण मुन्ना /आसाराम | Deleted | 67000 | 0 | 2015-10-02
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Infrastructure for NADEP composting / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730005017/OP/9425891220 — नाडेप निर्माण स्कूल के पास | Completed | 16000 | 15872.12 | 2016-12-18 | 2018-09-06
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Infrastructure for NADEP composting / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730005017/OP/9425891242 — नाडेप निर्माण कार्य तालाब के पास | Completed | 16000 | 15695.12 | 2016-12-18 | 2018-09-06
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Other Works | Infrastructure for NADEP composting / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1730005017/OP/9425892023 — नाडेप निर्माण | Closed | 0 | 0 | 2016-11-01
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1730005017/PG/9425891323 — खेल मैदान निर्माण पांजरा रास्ता | Completed | 353000 | 329472.92 | 2016-12-15 | 2018-10-12
BADI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/202 — मंदिर से महेश पटेल की ओर आंतरिक पथ सीसीरोड भिलाडिया | Completed | 103000 | 95340 | 2012-06-05 | 2012-08-14
BADI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034192582 — मझलेपंडितकेमकानसेजुम्मनकेमकानकीऐओरआंतरिकपथ | Completed | 200000 | 174185.3 | 2013-12-12 | 2015-06-30
BADI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1730005017/RC/22012034214565 — ग्रेवल सडक निर्माण बगलवाडा रोड से रामगोपाल पुआर के | Completed | 1497000 | 1287156.42 | 2014-03-15 | 2016-04-30
BADI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034219365 — भगवत पटेल के मकान से पंडित के मकान की ओर आंतरिक पथ | Completed | 55000 | 26417.7 | 2014-05-08 | 2015-06-30
BADI | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034219366 — हरिजन मोहल्‍ला से नदी की ओर आंतरिक पथ सीसीरोड | Completed | 74000 | 68127.2 | 2014-09-01 | 2015-06-25
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034299508 — सोना सिंह के घर से पांजरा रास्‍ता एवं सोना सिंह के घर से मिस्‍टर लाल के घर तक आंतरिक पथ सीसीरोड | Completed | 125000 | 126830.22 | 2016-04-21 | 2016-06-18
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034313513 — हक्कू बरेठा के घर से पांजरा रास्ता तक | Completed | 72000 | 64055.78 | 2016-06-11 | 2016-07-10
BADI | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1730005017/RC/22012034339907 — सी सी रोड भाई जी पुरविया के मकान से रमेश भार्गव के मकान तक | Deleted | 40000 | 0 | 2016-10-02
BADI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034375232 — बरेली रास्‍ता से दादू कर्चली के मकान तक | Closed | 0 | 0 | 2017-10-02
BADI | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034375236 — गुरारिया रोड से रामजानकी मंदिर की ओर | Deleted | 0 | 0 | 2017-10-02
BADI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034438855 — cc road | Closed | 0 | 0 | 2019-01-26
BADI | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034449664 — पांजरा रास्‍ता से कुबेर सिंह के मकान की ओर सीसीरोड | Completed | 52000 | 51672 | 2019-03-09 | 2019-09-20
BADI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034450118 — बरेली रास्‍त से दादू कर्चली के मकान की ओर | Completed | 36900 | 34496 | 2019-06-10 | 2019-09-20
BADI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034473007 — बरेली रास्‍ता से सुरेश सिंह के मकान की ओर सीसीरोड | Completed | 46912 | 45584 | 2019-09-04 | 2020-01-20
BADI | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034473009 — चैन सिंह के मकान से पांजरा रास्‍ता तक सीसीरोड | Completed | 13965 | 13728 | 2019-08-22 | 2020-04-30
BADI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034526423 — C C ROAD MANGAL SINGH KE MAKAN SE MUNNI BAI KE MAKAN KI OR | Closed | 0 | 0 | 2020-04-14
BADI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034526681 — सी सी रोड मंगल सिंह के मकान से मुन्नी बाई के मकान की ओर | Completed | 44000 | 44460 | 2020-06-21 | 2020-09-30
BADI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034549128 — हरिसिंह के मकान से राम जानकी मंदिर की ओरसीसीरोड | Completed | 26000 | 19162 | 2020-11-25 | 2021-11-12
BADI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034549132 — भगवत ि‍सिंह के मकान मदन ि‍सिंह के मकान की ओर सीसीरोड | Completed | 7600 | 7536 | 2020-11-22 | 2024-05-09
BADI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034551019 — आर सीसी नाली निर्माण बगलवाडा रोड से पांजरा रोड की ओर | Completed | 34500 | 29974 | 2021-01-02 | 2021-11-12
BADI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1730005017/RC/22012034567266 — भिलाड़िया से सिरवाड़ा की और ग्रेवल रोड निर्माण कार्य ग्राम पंचायत भिलाड़िया | Completed | 1499644.72 | 1386529.82 | 2021-04-08 | 2023-08-03
BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034651092 — C C ROAD GOVIND SINGH KE GHAR SE VISHRAM RAJAK KE GHAR KI AOR | Completed | 8935 | 7579 | 2023-08-31 | 2025-07-05
BADI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034680912 — नाली निर्माण कार्य बगीचा से बगलवाडा रास्‍ता की ओर | Completed | 19000 | 18711 | 2024-09-28 | 2024-10-16
BADI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034681347 — नाली निर्माण कार्य कुलदीप पटेल के खलिहान से पांजरा रास्‍ता की ओर | Completed | 10000 | 8262 | 2024-10-15 | 2026-02-16
BADI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034829760 — C C ROAD SAH NALI NIRMAN BHAGWAT SINGH KE MAKAN SE SHANKAR SINGH GOUR KE MAKAN KI OR | Completed | 48000 | 46458 | 2025-04-12 | 2026-03-13
BADI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034839455 — सीसीरोड निर्माण कार्य चैन सिंह के मकान से वलीराम के मकान की ओर | Completed | 25000 | 23490 | 2025-04-02 | 2026-02-16
BADI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/22012034847230 — सीसीरोड निर्माण कार्य चैन सिंह के घर से शंकर सिंह के घर की ओर | Completed | 36000 | 34713 | 2025-08-24 | 2026-06-02
BADI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1730005017/RC/259 — राम जानकी मंदिर से जुम्‍मन के घर की ओर कनवर्जेन्‍स सीसीरोड | Completed | 51000 | 44290 | 2012-06-12 | 2013-06-20
BADI | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1730005017/RC/337 — मा शाला से हरिजन मोहल्‍ला तक आंतरिक पथ सीसीरोड | Completed | 160000 | 158524 | 2012-12-27 | 2013-02-21
BADI | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730005017/RC/VB/YD/22012034855044 — सी सी रोड निर्माण कार्य भिलाडिया | Approved | 0 | 0 | 2026-07-02
BADI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730005017/RS/22012034512594 — NALI NIRMAN BHAGWAT SINGH MAKAN SE PANJRA RASTA KI OR | Completed | 27000 | 26634 | 2021-08-12 | 2021-11-28
BADI | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1730005017/RS/22012034639052 — सामुदायिक स्‍वच्‍छता परिसर निर्माण माध्‍यमिक शाला भवन के पास भिलाडिया | Completed | 44000 | 43998 | 2022-02-04 | 2022-05-16
BADI | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1730005017/RS/22012034702861 — NALI NIRMAN VISHRAM RAJAK KE GHAR SE BAGICHA KI AOR | Completed | 51000 | 49538 | 2023-09-14 | 2024-10-16
BADI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1730005017/RS/22012035137188 — KACHHI NALI NIRMAN KUBER SINGH KE KHILYAN SE NADI KI AOR | Approved | 0 | 0 | 2025-04-01
BADI | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1730005017/RS/33371 — श्री रघुवीरसिंह आत्‍मज श्री कमलसिंह - मर्यादा शौ | Completed | 50000 | 266 | 2013-06-13 | 2016-08-17
BADI | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1730005017/WC/22012034325173 — तालाब जीर्णोद्धार निर्माण कार्य भिलाडिया | Completed | 183000 | 179540.21 | 2017-05-22 | 2017-07-25
BADI | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1730005017/WC/22012034495978 — naveen talab nirman karya bhiladiya | Closed | 0 | 0 | 2019-08-15
BADI | 2019-2020 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1730005017/WC/22012034506362 — community sunken pond | Completed | 310385.56 | 240918 | 2019-11-26 | 2022-05-20
BADI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1730005017/WC/VB/YD/22012035334900 — Roof top rain wat. har. str. in gov/panchayat bldg ग्राम पंचायत भिलाडिया | Approved | 30357.06 | 0 | 2026-07-02
BADI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1730005017/WC/VB/YD/22012035335065 — रिचार्ज पिट निर्माण कार्य भगवान सिंह जी के धर के पास ग्राम भिलाडिया | Approved | 25991.95 | 0 | 2026-07-02