## Work List
Exported on: 2026-10-04 12:02:07
Filters applied:
Data source: VBGRAMG
District: RAISEN
Block: All
Panchayat: CHUNHETIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SILWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1730006016/AV/22012034666880 — shantidham unnayan kary madhai bale donga pr Chunhetiya | New | 0 | 0 | 2025-04-14
SILWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Wasteland Block Plantation-Horticulture-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1730006016/DP/22012034619698 — braksharopan kary shanti dham ke pass chunhetiya | Ongoing | 338999.83 | 0 | 2024-09-03
SILWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1730006016/IF/22012034616859 — खेत में वृक्षारोपण कार्य श्री प्रकाश श्रीवास्तव चुहैटिया | Ongoing | 142446.41 | 0 | 2021-07-07
SILWANI | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730006016/IF/22012035172231 — Braksha Ropan Halkeveer / Chhotelal Chunhetiya | Ongoing | 161586.73 | 0 | 2024-02-15
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730006016/IF/22012035569702 — JGSA25 khet talab nirman kary ramprsad Adiwasi | Approved | 55865.38 | 0 | 2025-04-14
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1730006016/IF/22012035577564 — JGSA25 khet talab brajlal Adiwasi | Approved | 55865.38 | 0 | 2025-04-14
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730006016/IF/22012035597876 — Ek Bagiya Maa ke Naam Mamta/Brajlal | New | 0 | 0 | 2025-04-14
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1730006016/IF/22012035597887 — Ek Bagiya Maa ke Naam Mamta/Brajlal | Approved | 0 | 0 | 2025-04-14
SILWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/2607541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP3823286 | Ongoing | 27000 | 4200 | 2023-03-11
SILWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/3135353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5427483 | Ongoing | 27000 | 0 | 2022-09-14
SILWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/4629070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128713429 | Ongoing | 27000 | 0 | 2025-02-13
SILWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/4629077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128714070 | Ongoing | 27000 | 0 | 2024-10-08
SILWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/4902520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125738277 | Ongoing | 27000 | 0 | 2025-02-20
SILWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/4902868 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115804120 | Ongoing | 27000 | 6300 | 2025-03-15
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/4975807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125669087 | Ongoing | 27000 | 8400 | 2025-11-24
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/4976204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128720262 | Completed | 23490 | 0 | 2025-04-03 | 2026-08-14
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5669390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125584786 | Ongoing | 27000 | 4200 | 2025-11-24
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5683783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115227106 | Physically Completed | 23490 | 0 | 2025-11-24 | 2026-08-02
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5733339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115804002 | Ongoing | 27000 | 6300 | 2025-11-24
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5858451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115804159 | Ongoing | 27000 | 2100 | 2025-11-24
SILWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5858641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115804021 | Physically Completed | 23490 | 1800 | 2025-11-24 | 2026-07-26
SILWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5869851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114035579 | Physically Completed | 27000 | 14700 | 2026-05-29 | 2026-09-13
SILWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/5951336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114028400 | Ongoing | 27000 | 12600 | 2026-06-09
SILWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1730006016/IF/IAY/6216011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128013634 | Ongoing | 27000 | 0 | 2026-06-09
SILWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730006016/RC/22012034823256 — c.c. Road sah nali narman kary kamlesh ke ghr se prem adiwasi ke ghr ki aur | Approved | 17000 | 0 | 2024-06-08
SILWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730006016/RC/22012034827471 — c.c. Road sah nali narman karyrajkumar ke ghr se choraha ki aur | Ongoing | 58000 | 0 | 2024-12-30
SILWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730006016/RC/22012034842298 — c.c. Road sah nali narman kary chorahe se ramsevak ke ghr ki aur | Approved | 19000 | 0 | 2025-04-01
SILWANI | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1730006016/RC/22012034842299 — c.c. Road sah nali narman kary shivnarayan ke ghr se bajar ki aur | Approved | 58000 | 0 | 2025-04-01
SILWANI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1730006016/RS/22012034511360 — nadep nirman kary madan adiwasi ke ghar ke pass | Ongoing | 64535.21 | 0 | 2021-03-19
SILWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1730006016/WC/22012035280461 — JGSA25 recharge structures panchyat bhavan nal ke pass | Approved | 25899.46 | 0 | 2025-04-14
SILWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1730006016/WC/22012035284631 — JGSA25 recharge structures Nicha Tola School nal ke pass | Approved | 25899.46 | 0 | 2025-04-24
SILWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1730006016/WC/VB/22012035332376 — Chek dem nirman kary tularam ke khet ka pass | New | 0 | 0 | 2026-06-05
SILWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1730006016/WC/VB/22012035332378 — bolder chek dem tularam ke khet ke pass | Approved | 84299.47 | 0 | 2026-06-05