## Work List
Exported on: 2026-10-27 17:56:22
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: GURADIYAJAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001006/AV/22012034465837 — बाउंड्री बाल निर्माण कार्य शासकीय पथ्मिक माध्यमिक शाला गुराडिया जाट | Completed | 171379 | 172252 | 2019-07-24 | 2020-07-03
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Food grain storage / Construction of Food grain Storage Building for Community | Constr of Food Grain storage | 1732001006/AV/22012034578020 — dainig hall saskiy madhymik sala gp guradiya jat | Closed | 19449.15 | 0 | 2021-04-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001006/AV/22012034635119 — Saarvjanik chbutra | Completed | 8200 | 7276 | 2023-05-20 | 2024-07-17
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001006/AV/22012034635123 — Saarvjanik chbutra | Closed | 0 | 0 | 2023-04-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/AV/22012034648790 — Payber blok holi chouk par guradiya jat | Closed | 0 | 0 | 2023-04-14
SEONI MALWA | 2024-2025 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural Produce Storage Building for Community | Constr of Food Grain storage | 1732001006/AV/22012034664235 — nandan falodhan kary umesh sharma ke khaliya par gram guradiya jat | New | 0 | 0 | 2025-01-24
SEONI MALWA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732001006/DP/22012034407230 — सडक कि‍नारे गुराडि‍याजाट से मेन रोड जामुनिया मार्ग गुराडि‍याजाट | Completed | 342000 | 257977 | 2019-06-05 | 2023-01-05
SEONI MALWA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732001006/DP/22012034407259 — सार्वजनि‍क परि‍सर शांति‍धाम गुराडि‍याजाट | Completed | 342000 | 77876 | 2019-06-05 | 2026-04-19
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732001006/DP/22012034544076 — माँ की बगिया शास्कीय प्रा.मा.साला गुराडिया जाट | Completed | 16976.64 | 1224 | 2022-04-06 | 2022-04-20
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1732001006/DP/22012034563139 — ब्रक्षरोपन कार्य शाशकिय प्राथमिक माध्मिक शाला गुराडिया जाट | Completed | 154038.72 | 100799 | 2022-08-31 | 2026-03-29
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732001006/DP/22012034563156 — नंदन फलोउधन केलाश उपाध्याय के खेत में ग्राम पंचायत गुराडिया जाट | Closed | 127309.88 | 0 | 2022-04-14
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1732001006/DP/22012034596528 — बसुधा वंदन अमृत वाटिका युगांतर स्कूल गुराड़िया जाट | Completed | 55847.4 | 9642 | 2023-08-30 | 2026-04-19
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1732001006/FP/22012034366090 — cleaning of dry silt | Completed | 226502.6 | 175940 | 2020-06-24 | 2020-08-30
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001006/FP/22012034633497 — CTR बाढ़ नियंत्रण कार्य गोविन्द कोंगरे के खेत के पास से मेन रोड तक ग्राम गुराडिया जाट | Completed | 93437.75 | 74576 | 2023-08-02 | 2024-09-04
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034345257 — braksharopan kary GURADIYA JAT sadak kinare | Completed | 335000 | 127448 | 2017-05-31 | 2021-05-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352365 — braksharopan kary high school guradiya jat | Completed | 335000 | 126624 | 2017-06-21 | 2022-05-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352387 — bas ropan kary nadi kinare | Completed | 535000 | 358214 | 2017-06-21 | 2022-05-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352402 — bas ropan kary nadi kinar 2 | Completed | 535000 | 98856 | 2017-06-21 | 2019-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352412 — bas ropann kary guradiya jat 3 | Completed | 535000 | 105068 | 2017-06-21 | 2019-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352423 — bas ropan kary nadi kinar par 4 | Completed | 535000 | 98296 | 2017-06-21 | 2019-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352433 — bas ropan kary nadi kinare guradiya jat5 | Completed | 535000 | 104470 | 2017-06-21 | 2019-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034352453 — bas ropan kary nadi kinare 6 guradiya jat | Completed | 535000 | 89054 | 2017-06-21 | 2019-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001006/IF/22012034377810 — khet ki med par braksharopan | Completed | 187600 | 7496 | 2017-10-11 | 2017-11-28
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/22012034485074 — मेड बंधान कार्य दगडू लाल गोहारे के खेत में | Completed | 23348.15 | 11315 | 2021-01-06 | 2021-12-05
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/22012034485082 — मेड बंधान कार्य ओम प्रकाश अश्वारे के खेत में | Completed | 24118.87 | 14789 | 2021-01-06 | 2021-12-05
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Drainage of chaur/waterlogged Land for Indiv / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/22012034485083 — मेड बंधान कार्य देवका बाई अश्वारे के खेत में | Completed | 22577.55 | 19421 | 2021-01-06 | 2021-12-05
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1732001006/IF/22012035254092 — nandan faloudan kary umesh sharma ki bhumi par guradiya jat | New | 0 | 0 | 2024-04-14
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Line Plantation of Horticulture Trees for Individual | Plantation | 1732001006/IF/22012035254096 — nandan faloudan kary umesh sharma ki bhumi par guradiya jat | New | 0 | 0 | 2024-04-14
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plntation Horti-TreesIndividual / Wasteland Block Plantation of Horticulture Trees for Individuals | Plantation | 1732001006/IF/22012035254100 — nandan faloudan kary umesh kumar ki bhumi par guradiya jat | Approved | 0 | 0 | 2024-04-14
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Afforestation of wasteland Forestry trees for ind / Agro Forestry Block Plantation for Individual | Plantation | 1732001006/IF/22012035301551 — nandan falodhan kary umesh sharma ke khaliya par gram guradiya jat | Ongoing | 145122.1 | 16084.74 | 2025-04-30
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001006/IF/22012035376635 — खेत तालाब निर्माण कार्य बलवीर सिंह धुर्वे के खेत पर गुराड़ियाजाट | Completed | 147621.16 | 61297.32 | 2025-04-22 | 2026-03-26
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732001006/IF/22012035533497 — khet talab nirman kary sugna bai ki bhumi par gp guradiya jat | New | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001006/IF/22012035533668 — khet talab nirman kary sugna bai ki bhumi par gp guradiya jat | Deleted | 0 | 0 | 2025-05-19
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001006/IF/22012035533689 — khet talab nirman kary Lakshmi bai ki bhumi par gp guradiya jat | Deleted | 0 | 0 | 2025-05-19
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001006/IF/22012035558438 — khet talab nirman kary Lakshmi bai ki bhumi par gp guradiya jat | Closed | 450885.64 | 0 | 2025-06-06
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001006/IF/22012035558448 — khet talab nirman kary sugna bai ki bhumi par gp guradiya jat | Closed | 450885.64 | 0 | 2025-06-06
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/9993667073 — मेढबंधान हरिप्रसाद मनोहर गुराडियाजाट | Completed | 26136 | 21465 | 2015-06-24 | 2016-06-24
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001006/IF/9993667546 — पशुशेड प्रहलाद सीताराम गुराडियाजाट | Completed | 88073 | 75862 | 2015-06-24 | 2017-08-18
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001006/IF/9993667547 — पशुशेड संजय हरिप्रसाद गुराडियाजाट | Completed | 88073 | 67569 | 2015-06-24 | 2017-08-18
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001006/IF/9993667620 — मेढबंधान प्रहलाद सीताराम के खेत मे | Completed | 26136 | 24804 | 2015-06-24 | 2016-01-23
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001006/IF/9993668262 — पशुशेड धनसिंह रामेश्‍वर गुराडियाजाट | Completed | 88073 | 64571 | 2015-06-24 | 2017-08-18
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001006/IF/9993668277 — पशुशेड राजेन्‍द राम िवलास गुरा िडयाजाट | Completed | 88073 | 81199 | 2015-07-22 | 2017-08-18
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001006/IF/9993668378 — पशु शेड सिताराम /पृेमराज गुराडिया जाट | Completed | 88073 | 64730 | 2015-06-24 | 2017-08-18
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/9993677804 — medbandhan raghuveer/ghasiram ke khet me guradiya jat | Completed | 26136 | 23850 | 2015-09-30 | 2016-06-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/9993680915 — medbandhan krya ramvilash gobardhan ke khet m guradiyajat | Completed | 26136 | 24327 | 2015-10-14 | 2016-01-23
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/9993680942 — MED BANDHAN KRYA TEELAK BUDAN KE KHET M GURADIYA JAT | Completed | 26136 | 22578 | 2015-10-14 | 2016-01-23
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/9993687348 — med bandhan karya ramnath/ prahlad ke khet m guradiya jat | Completed | 26136 | 25440 | 2015-11-11 | 2016-06-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001006/IF/9993687365 — md bandhan karya sumantra bai /ashok ke khet m guradiya jat | Completed | 25502 | 24327 | 2015-11-11 | 2016-06-24
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/2120318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4552381 | Completed | 15840 | 15136 | 2019-11-27 | 2020-05-10
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/2120758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4561863 | Completed | 15840 | 15136 | 2019-11-27 | 2020-05-10
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/2158273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5470363 | Completed | 15840 | 15840 | 2019-07-24 | 2019-11-12
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/2338179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5159795 | Completed | 15840 | 15808 | 2020-01-08 | 2020-05-30
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/3875066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146970687 | Ongoing | 27000 | 5072 | 2022-06-01
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/3895054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150201738 | Completed | 18360 | 18357 | 2022-07-27 | 2023-05-10
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/3905421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148289685 | Completed | 18360 | 17544 | 2022-06-01 | 2024-01-23
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4112186 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150183672 | Closed | 18360 | 0 | 2022-05-20
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4113382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149671535 | Completed | 18360 | 18360 | 2022-06-01 | 2022-12-20
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4180681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150681988 | Closed | 18360 | 0 | 2022-06-14
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4181983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148640100 | Completed | 18360 | 18357 | 2022-07-27 | 2023-05-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/446068 — Construction of IAY House -IAY REG. NO. MP1519247 | Completed | 15030 | 15842 | 2017-03-08 | 2018-09-13
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/453867 — Construction of IAY House -IAY REG. NO. MP1617056 | Completed | 15030 | 14726 | 2017-02-01 | 2018-06-05
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/4665095 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151044102 | Approved | 27000 | 0 | 2024-09-10
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4665936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150209292 | Completed | 21870 | 21870 | 2024-11-21 | 2025-03-24
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/4666329 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150651243 | Approved | 27000 | 0 | 2024-09-10
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4797714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148202665 | Completed | 21870 | 21870 | 2024-11-21 | 2025-03-24
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/4799948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150224780 | Completed | 21870 | 21627 | 2024-11-21 | 2025-03-24
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/50989 — Construction of IAY House -IAY REG. NO. MP-32-001-006-001/38 | Completed | 14310 | 10020 | 2016-07-06 | 2017-11-13
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/50991 — Construction of IAY House -IAY REG. NO. MP-32-001-006-001/65 | Completed | 14310 | 15030 | 2016-11-23 | 2017-07-24
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5102402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148599216 | Completed | 23490 | 23490 | 2025-04-23 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5472777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146970549 | Completed | 23490 | 23490 | 2025-05-14 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5473239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150191982 | Ongoing | 27000 | 23241 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5474172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148284001 | Completed | 23490 | 23490 | 2025-05-14 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/5474227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149681820 | Physically Completed | 23490 | 23490 | 2025-05-14 | 2026-01-09
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5474746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148603979 | Completed | 23490 | 23490 | 2025-05-14 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5476647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148191834 | Ongoing | 27000 | 24087 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5476650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148279729 | Completed | 23490 | 23490 | 2025-05-14 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5476698 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148612079 | Completed | 23490 | 23490 | 2025-05-14 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5478243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126084377 | Ongoing | 27000 | 23229 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5480045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126088403 | Completed | 23490 | 23490 | 2025-08-01 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/5480357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148274504 | Physically Completed | 23490 | 23490 | 2025-05-21 | 2026-05-03
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5480780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148196677 | Completed | 23490 | 23490 | 2025-08-01 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5480790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148210346 | Ongoing | 27000 | 12006 | 2025-08-01
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5717803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100858383 | Completed | 23490 | 23202 | 2025-08-01 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/5822965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150707133 | Approved | 27000 | 0 | 2025-03-11
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/5844792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149721286 | Physically Completed | 23490 | 0 | 2025-03-03 | 2026-02-18
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/617326 — Construction of IAY House -IAY REG. NO. MP2929564 | Completed | 15030 | 15182 | 2017-03-08 | 2018-06-25
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/639273 — Construction of IAY House -IAY REG. NO. MP2861553 | Completed | 15030 | 15660 | 2018-08-01 | 2018-09-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/661900 — Construction of IAY House -IAY REG. NO. MP1599170 | Completed | 15030 | 15492 | 2017-08-16 | 2018-08-01
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/663612 — Construction of IAY House -IAY REG. NO. MP1830283 | Completed | 15030 | 15480 | 2017-08-09 | 2017-11-13
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/665522 — Construction of IAY House -IAY REG. NO. MP2005753 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/674855 — Construction of IAY House -IAY REG. NO. MP2763494 | Completed | 15030 | 15480 | 2017-08-30 | 2017-11-13
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/675569 — Construction of IAY House -IAY REG. NO. MP2822156 | Completed | 15030 | 16584 | 2017-08-16 | 2018-06-05
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/676262 — Construction of IAY House -IAY REG. NO. MP2933367 | Completed | 15030 | 14448 | 2017-08-16 | 2018-06-05
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732001006/IF/IAY/681076 — Construction of IAY House -IAY REG. NO. MP3535989 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/681086 — Construction of IAY House -IAY REG. NO. MP3537334 | Completed | 15030 | 15480 | 2017-08-16 | 2018-08-01
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/681088 — Construction of IAY House -IAY REG. NO. MP3537338 | Completed | 15030 | 15480 | 2017-08-16 | 2017-11-13
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/681238 — Construction of IAY House -IAY REG. NO. MP3545617 | Completed | 15030 | 15480 | 2017-08-16 | 2018-04-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/681554 — Construction of IAY House -IAY REG. NO. MP3604029 | Completed | 15030 | 15480 | 2017-08-16 | 2018-08-01
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/681582 — Construction of IAY House -IAY REG. NO. MP3610722 | Completed | 15030 | 15480 | 2017-08-16 | 2017-11-13
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001006/IF/IAY/681640 — Construction of IAY House -IAY REG. NO. MP3613821 | Completed | 17100 | 17568 | 2022-01-26 | 2022-12-20
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732001006/LD/22012034295327 — शातिधाम निमाण गुराडियाजाट | Completed | 180000 | 177395.8 | 2016-12-21 | 2019-01-07
SEONI MALWA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001006/LD/22012034309584 — शन्तिधाम निर्माण | Deleted | 0 | 0 | 2017-04-01
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732001006/PG/9425891465 — खैल मैदान शासकीय हाई सकूल गुराडियाजाट | Completed | 76800 | 70010 | 2016-12-28 | 2018-10-25
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/193 — P.P.C.C.road Nali Muliyabai ke ghar se Mangu kha | Completed | 139170 | 38544 | 2012-09-12 | 2014-02-16
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034190345 — पंच परमेश्‍वर रोड राधाबाई के मकान से नदी की ओर गुर | Completed | 139018 | 116234 | 2013-10-16 | 2014-11-02
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034198020 — आदिवासी मोहल्‍ले में रेवाराम जी के मकान के पास से | Completed | 179985 | 135178 | 2014-01-08 | 2015-03-26
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034217733 — सांसद निधी रोड एससीवार्ड में मूलचंदसिंह गौतम के | Completed | 37463 | 37351 | 2014-05-07 | 2015-02-25
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034226837 — पंचपरमेश्‍वर नदी पुल के पास से रामविलासजी के घर की ओर गुराडियाजाट | Completed | 51302 | 7904 | 2014-08-13 | 2016-09-30
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034226838 — पंचपरमेश्‍वर रोड रमेश भामी के घर से नदी की ओर स्‍कूल के पास गुराडियाजाट | Completed | 133674 | 12089 | 2014-08-06 | 2016-09-30
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034294518 — पंचपरमेश्‍वर रोड नाली नदी पुल से देवनारायण के खलिहान की ओर गुराडियाजाट | Completed | 73985 | 50880 | 2016-01-13 | 2016-12-09
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034296839 — पंचपरमेश्‍वर रोड नाली देवनारायण के खलियान से नाले की ओर गुराडियाजाट | Completed | 52846 | 33567 | 2016-05-11 | 2017-08-18
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034303368 — ccroad1 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034303370 — ccroad2 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034303371 — ccroad3 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034324885 — C C ROAD NIRMAN | Closed | 0 | 0 | 2017-04-01
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034326665 — सी सी सड़क/नाली निर्माण कार्य हेमराज के घर से बादामी के घर कीओर | Completed | 39712 | 40920 | 2017-02-15 | 2017-11-20
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034326677 — सी सी सड़क/नाली निर्माण कार्य प्रेम नारायण के घर से राम मंदिर की ओर | Completed | 39712 | 36292 | 2017-09-13 | 2017-11-20
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034374385 — सी सी रोड व नाली नि‍मार्ण | Closed | 0 | 0 | 2018-04-01
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034397105 — सी सी सड़क निर्माण कार्य जोखिलाल से रामदास के घर की और हरिजन मोहल्ला | Completed | 69435 | 66984 | 2018-12-20 | 2019-06-10
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034397137 — सी सी सड़क निर्माण कार्य कमल मेंबर से निर्भय दरोई की और | Completed | 47089 | 45144 | 2019-01-23 | 2019-06-10
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034397334 — सी सी सड़क निर्माण कार्य अमरसिंह हरिजन के घर से रामचरण के घर की ओर गुरदिया जाट | Completed | 34718 | 27144 | 2019-01-23 | 2019-03-15
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034397341 — सी सी नाली निर्माण कार्य हापिज खा के घर से मनीष व्राह्मण के घर की और | Completed | 64383 | 47516 | 2019-02-27 | 2020-05-20
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034439033 — c c road nirman karya | Closed | 0 | 0 | 2019-04-14
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034445590 — सी सी नाली निर्माण कार्य रामेश्वर नार्धनिया के घर से नितिन शर्मा के घर की और | Completed | 28971 | 27464 | 2019-02-27 | 2019-06-15
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034445592 — सी सी सड़क एवं नाली निर्माण कार्य रामेश्वर के घर से हरी गुर्जर के घर की और | Completed | 23714 | 25164 | 2019-02-27 | 2019-04-30
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034445593 — सी सी सड़क एवं नाली निर्माण कार्य शंकर गोंड के घर से विजेंदर के घर की और | Completed | 62386 | 59860 | 2019-02-27 | 2019-06-01
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034468030 — सी सी सड़क एवं नाली निर्माण कार्य महेश पटेल के घर से नाले की और | Deleted | 31192 | 0 | 2016-04-14
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034468031 — सी सी नाली निर्माण कार्य रामकिशोर स्याग के घर से किशोर पड़ोदा के घर की और | Closed | 16096 | 0 | 2016-04-14
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034468032 — सी सी सड़क निर्माण कार्य रमेश लेघा के घर से हरदीन के घर की और | Deleted | 46290 | 0 | 2016-04-14
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034512686 — C C sadak evm nali nirman kary hanuman mandir se s | Closed | 0 | 0 | 2019-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034541968 — पुलिया निमाण् कार्य जयनारायण के घर के पास गुरडियजाट | Completed | 35596 | 33060 | 2020-10-21 | 2021-06-22
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034541996 — पुलिया निर्माण कार्य शातिधाम मार्ग पर गुरडियाजाट | Completed | 94146 | 42694 | 2020-12-23 | 2021-12-05
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034559912 — CC ROAD HANUMAN MANDIR SE SHANTIDHAM KI AUR GURADIYAJAT | Completed | 66300 | 63574 | 2021-02-17 | 2022-02-22
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034608026 — CC ROAD NALI NIRMAN | Closed | 0 | 0 | 2022-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034609288 — c c sadak nirman kary barjor ke ghar se abdul ke ghar ki or | Completed | 56698 | 53896 | 2022-03-16 | 2024-01-29
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034663239 — सी सी रोड राधा बाई के घर से कोदर के घर की ओर गुराडियाजाट | Completed | 19587 | 18409 | 2023-10-07 | 2024-01-23
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034665447 — c c sadak nirman kary salim khan ke ghar se sunil padoda ke ghar ki or guradiya jat | Completed | 50771 | 50731 | 2023-10-07 | 2026-03-29
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034665582 — C C sadak nirman kary balram ke ghar se majjid ki or guradiya jat | Completed | 26628 | 25636 | 2023-10-07 | 2024-01-23
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034823605 — saskiy prathmik madymik salal matdan kendra par c c nirman kary guradiya jat | Completed | 55800 | 49547.91 | 2024-09-03 | 2026-03-29
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034828052 — cc road nirman kary shankar mandir se nadi ki or gram guradiya jat | Completed | 55800 | 55262.76 | 2024-10-30 | 2026-03-29
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034843894 — Cc road nirman kary devnarayan patel ke ghar se nadi ki or gram guradiya jat | Approved | 57000 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034843898 — cc road nirman kary rajendra thuseya ke ghar se rajendra varma ke ghar ki or gram guradiya jat | Approved | 72000 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034843900 — cc road nirman kary radheshyam jat ke ghar se nadi ki or gram guradiya jat | Approved | 57000 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001006/RC/22012034843901 — cc road nirman kary gulab navre ke ghar se shreeram khema ji ke ghar ki or gram guradiya jat | Approved | 57000 | 0 | 2025-04-14
SEONI MALWA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001006/RC/43 — ग्रेवल रोड निमार्ण गुराडियाजाट | Completed | 473181 | 2659 | 2008-09-20 | 2015-03-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732001006/RS/22012034498786 — सामुदायिक स्वछता परिसर गुराडिया जाट | Completed | 43700 | 43130 | 2020-10-21 | 2021-03-26
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001006/RS/22012034655002 — सी सी नाली बरजोर के घर से अब्दुल के घर की ओर गुराडियाजाट | Completed | 23750 | 21624 | 2022-05-18 | 2024-01-29
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001006/RS/22012035116621 — c c nali nirman kary vinod sallam ke ghar se kodar ke ghar ki or guradiya jat | Completed | 16215 | 14920 | 2023-10-07 | 2024-09-04
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732001006/RS/22012035117547 — CC nali nirman kary shayamlala ke ghar se panchayat bahvan ki or guradiya jat | Ongoing | 23270 | 11649 | 2023-10-07
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732001006/RS/22012035117560 — C C nali nirman kary mahendra sharma ke ghar se santosh syag ke ghar ki or guradiya jat | Ongoing | 34905 | 33147.44 | 2023-10-07
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001006/RS/22012035124187 — सी सी नाली निर्माण कार्य हकीम खा के घर से मुबारिक खा के घर की या गुराड़िया जाट | Completed | 15787 | 11092 | 2024-03-20 | 2025-05-17
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001006/WC/002 — कूप निर्माण | Completed | 75774 | 1794 | 2008-04-07 | 2008-04-07
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001006/WC/22012034727381 — CTR कच्ची नाली निर्माण कार्य मगन के घर से कैलाश के खेत की ओर ग्राम गुराडिया जाट ग्राम पंचायत गुराडिय | Completed | 162083.13 | 54572.72 | 2021-10-06 | 2025-05-18
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1732001006/WC/22012034727389 — CTR कच्ची नाली निर्माण कार्य हरि गुजर के खलियान से भैरु बाबा की ओर ग्राम गुराडिया जाट ग्राम पंचायत ग | Ongoing | 122514.23 | 6120 | 2022-05-18
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732001006/WC/22012034727396 — CTR cleaning of dry silt | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1732001006/WC/22012034727406 — CTR cleaning of dry silt gram panchayt guradiya jat | Completed | 130455.58 | 128538 | 2021-06-09 | 2022-02-22
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/22012034780383 — water harvesting kary gp guradya jat panchayat bhavan | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/22012034976970 — CTR कच्ची नाली कार्य नाले से सुशीला बाई बकोरिया के घर की और | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/22012034976980 — CTR कच्ची नाली कार्य हाई स्कूल गुराडिया जाट | Completed | 140926.37 | 110777.42 | 2022-08-17 | 2026-03-26
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/22012034976981 — CTR कच्ची नाली कार्य हाई स्कूल गुराडिया जाट | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1732001006/WC/22012034977282 — CTR कच्ची नाली कार्य शंकर लाल धुर्वे के घर से नाले की और गुराडिया जाट | Completed | 72159.64 | 19357 | 2022-08-17 | 2026-04-19
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001006/WC/22012034977291 — CTR कच्ची नाली कार्य शंकर लाल धुर्वे के घर से नाले की और गुराडिया जाट | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001006/WC/22012034977327 — CTR कच्ची नाली कार्य हनुमानमंदिर से शांति धाम की और गुराडिया जाट | Closed | 84631.12 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001006/WC/22012034978391 — ctr kacchi nali nirman kry nale se sushila bai ke ghar ki or guradiya jat | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001006/WC/22012034978396 — ctr kacchi nali nirman kry nale se sushila bai bakoriya ke ghar ki or guradiya jat | Completed | 138819.17 | 79488 | 2022-06-08 | 2025-05-17
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001006/WC/22012034978417 — ctr kacchi nali nirman kary bheru baba se nahar ki or gram panchayat guradiya jat | Ongoing | 92291.13 | 2448 | 2022-06-01
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/22012035206073 — ren water harvesting kary panchayt bhavan | Approved | 36550 | 0 | 2024-04-14
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/22012035206089 — ren water harvesting kary high school guradiya jat | Completed | 46162 | 22842 | 2024-07-03 | 2026-03-29
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001006/WC/272 — निर्मलनी‍र गुडारियाजाट | Completed | 136383 | 455 | 2009-03-19 | 2023-08-01
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001006/WC/76 — कूप निमार्ण तिलक / बुध्‍दू गुराडियाजाट | Completed | 75774 | 595 | 2008-09-20 | 2023-08-01
SEONI MALWA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732001006/WC/VB/YD/22012035335689 — Roof top rain wat. har. str. in gov/panchayat bldg | Approved | 45399.61 | 0 | 2026-04-14
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1732001006/WH/22012034919828 — स्टापडेम कडी शटर सामुदायिक स्वच्छता केंद्र के पास गुराडियाजाट | Deleted | 0 | 0 | 2022-03-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1732001006/WH/22012034919830 — स्टापडेम कडी शटर सामुदायिक स्वच्छता केंद्र के पास गुराडियाजाट | Completed | 3357 | 3474 | 2022-03-16 | 2022-12-30
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | /SK/105 — Bharat Nirman Rajeev Gandhi Sewa Kendra,GURADIYAJAT | Completed | 452000 | 236857 | 2013-06-12 | 2015-07-30