## Work List
Exported on: 2026-09-03 02:04:26
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: AMLADAKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001017/IF/22012035236972 — KAPIL DHARA KOOP NIRMAN KARY SUNDARLAL/BABULAL AMLADA KALAN GP AMLADA KALAN | Ongoing | 316434.46 | 0 | 2024-11-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001017/IF/22012035352294 — KHET TALAB NIRMAN KARY RAJKUMAR AMLADA KALAN | Ongoing | 450885.64 | 0 | 2025-04-22
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001017/IF/22012035450746 — khet talab nirman kary pradeep amlada kalan | Ongoing | 147621.16 | 15000 | 2025-05-30
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001017/IF/22012035605660 — Ek Bagiya Maa ke Naam Ganga Bai Pal GP Amlada Kalan | Ongoing | 269387.37 | 0 | 2025-12-03
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001017/IF/22012035605725 — Ek Bagiya Maa ke naam Meera Bai Pal GP Amlada Kalan | Approved | 0 | 0 | 2025-08-15
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001017/IF/22012035641697 — EK BAGIYA MAA KE NAAM PARVATI BAI/VISHNU KORKU AMLADA KALAN GP AMLADA KALAN | Ongoing | 269387.37 | 0 | 2025-11-24
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732001017/IF/22012035646188 — EK BAGIYA MAA KE NAAM RAMA BAI/LALMAN AMLADA KALAN GP AMLADA KALAN | Ongoing | 199117.83 | 0 | 2025-12-22
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001017/IF/22012035646200 — EK BAGIYA MA KE NAM SOUDRA BAIKEER AMLADAKALA | Approved | 169941.98 | 0 | 2025-08-15
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001017/IF/IAY/85947 — Construction of IAY House -IAY REG. NO. MP-32-001-017-001/013 | Approved | 27000 | 0 | 2016-01-13
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001017/RC/22012034844150 — CC ROAD NIRMAN KARY KISHORI KE GHAR SE SANTOSH KE GHAR KI OR AMLADA KALAN GP AMLADA KALAN | Ongoing | 49483 | 0 | 2025-11-03
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001017/RC/22012034853686 — CC ROAD NIRMAN KARY VIJAY KE GHAR SE JITENDRA KE GHAR KI 0R AMLADA KALAN | Approved | 42000 | 0 | 2026-01-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001017/RS/22012034575918 — R.C.C.NALI NIRMAN KARY RAMLAL KE GHAR SE SUNDARLAL KE GHAR KI OR,AMLADA KALAN,GP AMLADA KALAN | Ongoing | 451895 | 0 | 2021-11-25
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-Wastelands for comm / Block Plantation of Biodrainage trees in Wastelands for community | Plantation | 1732001017/WC/22012034809869 — GOU SHALA KE PICHHE BLOCK PLANTATIONS KARY,AMLADA KALAN | Ongoing | 394489.84 | 7500 | 2021-09-16