## Work List
Exported on: 2026-10-28 10:58:03
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: BILDHI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1732001022/DP/22012034556704 — वृक्षारोपण कार्य पंचायत के सामने नदी किनारे ग्राम बिल्धी ग्राम पंचायत बिल्धी | Ongoing | 411218.19 | 4200 | 2022-12-30
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/4662510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149675487 | Completed | 23490 | 0 | 2024-09-30 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5095838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143120269 | Completed | 23490 | 0 | 2025-03-18 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5096870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145201980 | Completed | 23490 | 0 | 2025-03-18 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5105040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149647646 | Ongoing | 27000 | 1200 | 2025-03-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5105057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149652299 | Completed | 23490 | 0 | 2025-04-22 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5105091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149669203 | Completed | 23490 | 0 | 2025-04-29 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5105124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149685397 | Approved | 27000 | 0 | 2025-02-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5107783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151041752 | Completed | 23490 | 0 | 2025-03-20 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5293962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149640400 | Completed | 23490 | 0 | 2025-05-06 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5445284 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145209766 | Completed | 23490 | 0 | 2025-07-29 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001022/IF/IAY/5448071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149693411 | Physically Completed | 23490 | 0 | 2025-05-27 | 2026-07-30
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001022/RC/22012034826463 — CC ROAD Nirman Nitin Rajput ke khale se madan Lal Rajput ke Ghar ki or Bildhi | Ongoing | 13763 | 0 | 2024-11-19
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001022/RC/22012034827359 — सी सी रोड निर्माण रमेश के घर से स्वच्छता परिसर की ओर बिलधी | Ongoing | 32354 | 0 | 2024-10-07
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001022/RC/22012034836036 — सी सी RAOD NIRMAN SANTOSH KE GHAR SE SWACHHTA PARISAR KI OR BILDHI | New | 0 | 0 | 2024-10-02
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001022/RC/22012034836037 — सी सी ROAD NIRMAN SANTOSH KI DUKAAN SE SWACHHTA PARISAR KI OR BILDHI | Ongoing | 26621 | 0 | 2025-03-18
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732001022/RS/22012035131109 — Canstruction of COMMUNITY NADEP NIRMAN WORK 05 Non GP Bildhi | Ongoing | 45225 | 0 | 2024-12-24
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732001022/RS/22012035133079 — RCC नाली निर्माण कार्य पूनम के घर से मंगल भवन की और बिल्धी | Ongoing | 53607 | 0 | 2024-11-05
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732001022/WC/22012035221238 — रेनवाटर हारवेस्टिंग कार्य मंगल भवन परिसर ग्राम पंचायत बिल्धी | Approved | 26831 | 0 | 2024-06-06