## Work List
Exported on: 2026-09-06 04:31:32
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: BHADHWADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001032/AV/22012034375326 — आगनवाडी भवन निर्माण ग्राम पंचायत बघवाडा | Completed | 180000 | 163986 | 2018-08-07 | 2020-05-14
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001032/AV/22012034506909 — boundri wall nirman prathmik shala baghwada | Closed | 0 | 0 | 2019-10-02
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732001032/AV/22012034511635 — शांति धाम निर्माण ग्राम पंचायत बघवाड़ा | Completed | 194312.08 | 170686.97 | 2020-09-01 | 2022-03-14
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1732001032/AV/22012034539522 — पेवर ब्लाक लगवाना ई कक्ष भवन परिसर में बघवाड़ा | Completed | 30000 | 26220 | 2020-10-13 | 2020-12-04
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1732001032/AV/22012034569299 — स्व सहायता समूह भवन (CLF) निर्माण कार्य बघवाडा | Physically Completed | 999999.83 | 819570.99 | 2021-09-11 | 2026-05-26
SEONI MALWA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1732001032/AV/22012034575871 — कचरा उपचार / भंडार केंद्र शेड निर्माण ग्राम बघवाड़ा | Ongoing | 100783 | 20478 | 2021-10-23
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034578289 — Bench and diningwork ms baghwada gram panchyat baghwada | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034578302 — Bench and diningwork ps baghwada gram panchyat baghwada | Deleted | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034578363 — Bench and diningwork ps baghwada gram panchyat baghwada | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034578480 — Bench and diningwork ps baghwada gram panchyat baghwada1 | Closed | 17593.2 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034578499 — Bench and diningwork ms baghwada gram panchyat baghwada2 | Ongoing | 17593.2 | 1158 | 2021-09-11
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034595489 — ग्राम पंचायत बघवाड़ा पंचायत भवन निर्माण कार्य | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034595490 — ग्राम पंचायत बघवाड़ा पंचायत भवन निर्माण कार्य | Deleted | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001032/AV/22012034605277 — बाउंड्रीबाल निर्माण माध्यमिक शाला परिसर बघवाड़ा | Completed | 54785 | 55162 | 2021-10-30 | 2022-07-28
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034634589 — panchayat bhawan nirman bhadwada | Deleted | 0 | 0 | 2023-04-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/AV/22012034634618 — पंचायत भवन निर्माण बगवाडा | Ongoing | 918000 | 736430.15 | 2023-06-29
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1732001032/DP/22012034543899 — मा की बगिया माधमिक शाला बघवाडा | Closed | 0 | 0 | 2021-10-02
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1732001032/DP/22012034543900 — मा की बगिया माधमिक शाला बघवाडा | Closed | 0 | 0 | 2021-10-02
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001032/IF/22012034346188 — वृक्षारोपण कार्य रोड किनारे बघवाड़ा | Completed | 335000 | 40776 | 2017-06-06 | 2022-03-16
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001032/IF/22012034350463 — व़क्षारोपण कार्य सार्वजनिक परिसर बघवाडा | Completed | 335000 | 52606 | 2017-06-13 | 2021-06-29
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001032/IF/22012034352376 — वास रोपण कार्य नदी किनारे बघवाडा ०१ | Completed | 535000 | 35040 | 2017-06-20 | 2019-11-24
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001032/IF/22012034352381 — वास रोपण कार्य नदी किनारे बघवाडा 02 | Completed | 535000 | 39340 | 2017-06-20 | 2019-11-24
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001032/IF/22012035556979 — KHET TALAB NIRMAN KARY BENIRAM LOWANSHI KE KHET PAR GP BAGHWADA | Completed | 55865.38 | 10179 | 2025-05-31 | 2026-04-15
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001032/IF/9993666320 — पशु शेड हरिओम सुंदरलाल बघवाडा | Completed | 88073 | 82653 | 2015-06-16 | 2016-09-15
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001032/IF/9993666575 — मेढबंधान संजयकुमार महेशप्रसाद मेहरा बघवाडा | Completed | 36591 | 32754 | 2015-06-16 | 2016-06-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Saline/Alkaline Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001032/IF/9993677580 — मेढ बंधान कार्य रामनारायण/रामदास बघवाडा | Completed | 30602 | 477 | 2015-09-29 | 2016-08-16
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Saline/Alkaline Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001032/IF/9993677585 — मेढ बंधान कार्य रामेश्‍वर/रामदयाल बघवाडा | Completed | 30602 | 20511 | 2015-10-06 | 2016-06-24
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001032/IF/9993728156 — MED BANDHAN | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2248776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4126112 | Completed | 15840 | 16512 | 2019-10-01 | 2020-08-06
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2248846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4221116 | Completed | 15840 | 16218 | 2019-08-20 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2248873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4250218 | Completed | 15840 | 16218 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2249189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4591675 | Completed | 15840 | 16218 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2249196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5094617 | Completed | 15840 | 16022 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2249242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4654145 | Completed | 15840 | 15840 | 2019-08-20 | 2020-05-14
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2249656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5080042 | Completed | 15840 | 16316 | 2019-10-01 | 2020-06-16
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2249673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5106872 | Completed | 15840 | 16022 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2250059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5149057 | Completed | 15840 | 16120 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4495298 | Completed | 15840 | 16218 | 2019-08-20 | 2020-06-16
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4528669 | Completed | 15840 | 16218 | 2019-08-20 | 2020-07-02
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4654913 | Completed | 15840 | 16218 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252323 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4677369 | Completed | 15840 | 15840 | 2019-10-01 | 2020-05-14
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4893247 | Completed | 15840 | 16218 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4894304 | Completed | 15840 | 16218 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4939390 | Completed | 15840 | 16316 | 2019-10-01 | 2020-07-02
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5109313 | Completed | 15840 | 15840 | 2019-10-01 | 2020-03-11
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2252521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5169349 | Completed | 15840 | 16316 | 2019-10-01 | 2020-08-07
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2255223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4079534 | Completed | 15840 | 16316 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2255578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4599174 | Completed | 17100 | 17370 | 2021-10-16 | 2022-01-22
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2255635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4698136 | Completed | 15840 | 15840 | 2019-10-01 | 2020-03-11
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2255755 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5693883 | Completed | 17100 | 17370 | 2021-10-09 | 2022-01-15
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2255819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5141741 | Completed | 15840 | 15840 | 2019-10-01 | 2020-05-14
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2256135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5726786 | Completed | 15840 | 15924 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2261731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4121381 | Completed | 15840 | 16120 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2261782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4558024 | Completed | 15840 | 15840 | 2019-10-01 | 2020-03-11
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2262143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4599143 | Completed | 15840 | 16022 | 2019-10-01 | 2020-06-09
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2262896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4898740 | Completed | 15840 | 16708 | 2019-10-01 | 2020-07-02
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/2262900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5504654 | Completed | 15840 | 15840 | 2019-10-01 | 2020-05-14
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/3223667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4964635 | Completed | 17370 | 16984 | 2021-10-16 | 2022-03-31
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/3224387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4597867 | Completed | 17370 | 17238 | 2022-04-09 | 2024-02-22
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/3227421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4652989 | Completed | 17370 | 16984 | 2021-10-09 | 2022-03-31
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/3231611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5470535 | Completed | 17370 | 16984 | 2021-10-09 | 2022-03-31
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/3231992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4599082 | Completed | 17370 | 17061 | 2021-10-16 | 2022-10-11
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/3653271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143403719 | Completed | 18360 | 17714 | 2022-12-17 | 2023-07-14
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732001032/IF/IAY/37658 — Construction of IAY House -IAY REG. NO. MP-32-001-032-001/17 | Completed | 14310 | 12690 | 2016-01-05 | 2016-10-27
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732001032/IF/IAY/37659 — Construction of IAY House -IAY REG. NO. MP-32-001-032-001/31 | Completed | 14310 | 13644 | 2016-01-05 | 2016-10-27
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/437114 — Construction of IAY House -IAY REG. NO. MP1445850 | Completed | 15030 | 15180 | 2017-01-31 | 2018-02-09
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/451687 — Construction of IAY House -IAY REG. NO. MP1585758 | Completed | 15030 | 15180 | 2017-01-31 | 2018-02-09
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/451691 — Construction of IAY House -IAY REG. NO. MP1585767 | Completed | 15030 | 10020 | 2017-01-31 | 2019-08-05
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/4534958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102315655 | Completed | 21870 | 21870 | 2024-11-18 | 2025-03-12
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5112287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145060763 | Completed | 23490 | 23490 | 2025-04-07 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5113740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146942641 | Ongoing | 27000 | 20097 | 2025-07-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5118702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143394212 | Completed | 23490 | 23490 | 2025-05-19 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5121645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150066363 | Ongoing | 27000 | 23229 | 2025-12-29
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5169848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146067964 | Completed | 23490 | 23229 | 2025-04-07 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5171109 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145070629 | Completed | 23490 | 21663 | 2025-05-19 | 2026-08-04
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5178519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148835199 | Completed | 23490 | 23490 | 2025-04-07 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5190689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151058245 | Ongoing | 27000 | 21924 | 2025-10-06
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5196182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148544469 | Completed | 23490 | 23490 | 2025-04-07 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5220287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151013375 | Ongoing | 27000 | 22968 | 2025-07-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5224484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148815358 | Completed | 23490 | 23490 | 2025-04-07 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5237121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148830849 | Completed | 23490 | 23490 | 2025-04-07 | 2026-05-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5238640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143052531 | Ongoing | 27000 | 20097 | 2025-07-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5529216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148821347 | Ongoing | 27000 | 22263 | 2025-07-28
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/5844211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118179663 | Approved | 27000 | 0 | 2025-05-05
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/659854 — Construction of IAY House -IAY REG. NO. MP1287776 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/659875 — Construction of IAY House -IAY REG. NO. MP1294402 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/680412 — Construction of IAY House -IAY REG. NO. MP3452525 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/680414 — Construction of IAY House -IAY REG. NO. MP3452528 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/681284 — Construction of IAY House -IAY REG. NO. MP3550433 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/681612 — Construction of IAY House -IAY REG. NO. MP3611683 | Completed | 15030 | 15480 | 2017-05-09 | 2018-02-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001032/IF/IAY/682365 — Construction of IAY House -IAY REG. NO. MP3753332 | Completed | 15030 | 15480 | 2017-05-09 | 2018-02-09
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732001032/PG/22012034311888 — खेल मैदान हाई स्कूल वघवाडा | Completed | 153600 | 11922 | 2017-05-23 | 2019-08-25
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/184 — P.P.C.C.road Nali nirman gour ke ghar se bhan ba | Completed | 77641 | 6731 | 2012-08-23 | 2019-05-05
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034267763 — सांसद निधी रोड रामभरोष प्रजापति के घर से खुटवासा मार्ग की ओर बघवाडा | Completed | 61168 | 54231 | 2015-07-28 | 2016-07-18
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034292918 — पंचपरमेश्‍वर रोड बस स्‍टेड से बल्‍लभ के घर की ओर बघवाडा | Completed | 72680 | 71455 | 2015-12-15 | 2017-02-02
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034303377 — cc road and nali 1 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034311241 — पंचपरमेश्वर रोड २ तरफ नाली एव सी.सी. रोड निर्माण कार्य होली चौक से स्कूल की ओर | Completed | 39643 | 38243 | 2016-04-19 | 2016-09-26
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034316610 — पंचपरमेश्‍वर रोड अरूण गौर के घर से नदी की ओर बघवाडा | Completed | 115661 | 111659 | 2016-11-22 | 2017-06-16
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034324169 — C C ROAD NIRMAN | Closed | 0 | 0 | 2017-04-01
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034327267 — पंचपरमेश्वर रोड लच्छीराम बघेल के घर से रोड की और सी सी रोड एव नाली निर्माण बघवाडा | Completed | 40125 | 17155 | 2017-02-14 | 2018-03-28
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034373199 — सी सी रोड व नाली नि‍मार्ण | Closed | 0 | 0 | 2018-04-01
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034438902 — c c road nirman karya | Closed | 0 | 0 | 2019-04-14
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034448327 — सी. सी. रोड निर्माण | Completed | 19200 | 17246 | 2019-03-05 | 2019-09-23
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034448342 — सी सी रोड निर्माण मंगल के घर से देवी सिंह के घर की और | Completed | 38590 | 20942 | 2019-03-05 | 2019-10-05
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034448359 — सी सी नाली निर्माण लाल सिंह के घर से जय प्रकाश के घर की और | Closed | 80850 | 0 | 2019-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Rpair & maint of brick/stone Kharanja Roads - Comm / Repair and maintenance of Kharanja (brick/stone) Roads for Community | Repair & maint of Road | 1732001032/RC/22012034515438 — cc road nirma radha jiji ke ghar se c.c road ki aur | Closed | 0 | 0 | 2019-10-02
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034533565 — सी सी रोड निर्माण कार्य हाई स्कूल परिसर में बघवाड़ा | Deleted | 0 | 0 | 2020-04-14
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034533568 — सी सी रोड निर्माण कार्य हाई स्कूल परिसर में बघवाड़ा | Completed | 42450 | 43890 | 2020-11-24 | 2021-01-28
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034574500 — सी सी रोड निर्माण कार्य शांति धाम बघवाड़ा पहुंच मार्ग | Completed | 19123 | 14861 | 2021-06-26 | 2023-01-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034574501 — सी सी रोड निर्माण कार्य शांति धाम बघवाड़ा पहुंच मार्ग | Deleted | 19123 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034576057 — सी सी रोड निर्माण गणेश गौर के घर से जीजलवाड़ा गोहा की और बघवाड़ा | Deleted | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034576058 — सी सी रोड निर्माण गणेश गौर के घर से जीजलवाड़ा गोहा की और बघवाड़ा | Completed | 57368 | 46706 | 2021-07-03 | 2022-07-28
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034601500 — पेवर ब्लॉक निर्माण कार्य हाई स्कूल परिसर में बघवड़ा | Closed | 77104 | 0 | 2021-08-15
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034607658 — CC ROAD NALI NIRMAN | Closed | 0 | 0 | 2022-04-01
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034614384 — सीसी रोड निर्माण खुठवासा रोड से नाले की और ग्राम पंचायत बघवाडा | Completed | 89000 | 48637 | 2022-05-21 | 2023-10-05
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034667767 — C C road nirmaan ram mandir se suresh thakur ke ghar ki or GP DHARAMKUDI | Closed | 65300 | 0 | 2023-04-01
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034669283 — C C Road ram mandi se suresh thakur ke ghar ki or GP DHARAMKUNDI | Closed | 63900 | 0 | 2023-08-17
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034826503 — सी सी रोड निर्माण राकेश लोवंशी के घर से महेश गौर के घर की और ग्राम पंचायत बघवाड़ा | Ongoing | 60891 | 51741.78 | 2024-11-18
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001032/RC/22012034826580 — सी सी रोड निर्माण संजय प्रजापति के घर के पास ग्राम पंचायत बघबाड़ा | Completed | 10773 | 8991 | 2024-11-04 | 2025-03-12
SEONI MALWA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001032/RC/58 — ग्रेवल रोड निमार्ण बघबाडा | Completed | 426493 | 1310 | 2008-09-24 | 2023-07-31
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001032/RS/22012034441885 — नाडेप निर्माण खुत्वासा मार्ग के बाजु में स्कूल के पीछे की ओर | Ongoing | 25036.58 | 760 | 2020-12-22
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001032/RS/22012034441886 — नाडेप निर्माण कोटला खेडी मार्ग के बाजु की ओर बगवाडा | Completed | 25013.8 | 16568.95 | 2020-12-22 | 2026-06-02
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034486966 — मंगल रघुवंशी के घर से संजय प्रजापति घर की और | Completed | 28433 | 29070 | 2020-07-14 | 2020-10-19
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034498502 — आर सी सी नाली कवर निर्माण बघवड़ा आनंद रघुवंशी के कोन से संजय प्रजापति के घर तक | Completed | 5128 | 4560 | 2020-10-06 | 2020-12-04
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732001032/RS/22012034499848 — सामुदायिक स्वछता परिसर बघवाड़ा | Completed | 43720 | 43320 | 2020-10-27 | 2021-01-28
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034505385 — सी सी नाली निर्माण कमल रघुवंशी के घर से मंगल रघुवंशी के घर की और | Completed | 7474 | 7980 | 2021-01-19 | 2021-02-12
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034507252 — आर सी सी नाली निर्माण मेन रोड सरपंच के घर से पंचायत भवन की और | Completed | 64436 | 66714 | 2021-02-16 | 2021-06-29
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001032/RS/22012034519251 — SLWM-नाडेप निर्माण कार्य (5 नाडेप ) UNIT -1 बघवाड़ा | Closed | 124378.73 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001032/RS/22012034529157 — कचरा शेड प्रथिकरण कार्य ग्राम पंचायत बघवाड़ा | Deleted | 100783 | 0 | 2021-06-26
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034529188 — RECHARGE PIT G P BAGWADA | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034533427 — सी सी नाली निर्माण सी सी रोड से जीजलवाड़ागोहा की और | Completed | 25248 | 18335 | 2021-07-03 | 2022-03-16
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034538737 — सी सी नाली निर्माण गणेश गौर के घर से जीजलवाड़ा गोहा की और बघवाड़ा | Ongoing | 55293 | 31266 | 2021-08-21
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012034656987 — आ.सी.सी. नाली निर्माण राजाराम लोवंशी के सामने से नाले की और | Completed | 60145 | 40137 | 2022-05-28 | 2024-01-29
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012035118722 — R C C NALI NIRMAN NANDLAL KE GHAR SE GP BAGHWADA | Closed | 38200 | 0 | 2023-04-01
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012035118733 — R C C NALI NIRMAN NANDLAL KE GHAR SE ramsevak ke ghar tak GP BAGHWADA | Closed | 38200 | 0 | 2023-10-07
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012035122336 — आर सी सी नाली निर्माण रामसेवक लोवंशी के घर से सुनील लोवंशी के घर की और | Closed | 0 | 0 | 2023-10-02
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001032/RS/22012035122338 — आर सी सी नाली निर्माण रामसेवक लोवंशी के घर से सुनील लोवंशी के घर की और | Ongoing | 59000 | 47619.04 | 2024-02-03
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001032/SK/2175 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BHADHWADA | Completed | 118101 | 114763 | 2014-02-18 | 2016-07-30
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001032/WC/22012034547992 — 5 RECHARGE PIT BAGHWADA | Closed | 31203.86 | 0 | 2020-04-14
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & Maint of Earthen graded Bund for Com / Repair and Maintenance of Earthen graded Bund for Community | Repair & Maint of Bund | 1732001032/WC/22012034553583 — Nala Gahrikaran baghwada | Closed | 100068.9 | 0 | 2020-04-14
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732001032/WC/22012034603181 — सी पी टी निर्माण बघवाड़ा | Completed | 19086.72 | 15960 | 2020-12-29 | 2023-09-05
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1732001032/WC/22012034721030 — CTR BAAD NIYTRN KARY KHUTWASA NALE SE KAKA JI KI PULIYA TAK | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732001032/WC/22012034721079 — CTR JAL NIKASHI HATU KACHHI NALI NIRMAN SCHOOL KE PASS SE JIJALWADA MARG TAK | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001032/WC/22012034724176 — CTR बाढ़ नियत्रण कार्य नाले के पास से पुलिया तक बघवड़ा | Completed | 43375.69 | 30108 | 2021-05-29 | 2023-09-05
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001032/WC/22012034724207 — CTR कच्ची नाली निर्माण कार्य स्कूल के पास से जिजलवाड़ा रोड तक बघवाड़ा | Closed | 67387.65 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1732001032/WC/22012034781371 — ROOF TOP WATER HARVASTINGH WORK AAGANWADI BHAVAN 03 OR E KASHA | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1732001032/WC/22012034781373 — ROOF TOP WATER HARVASTINGH WORK AAGANWADI BHAVAN 03 OR E KASHA | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001032/WC/22012035003207 — CTR कार्य जल निकासी हेतु कच्ची नाली कोटलाखेड़ी मार्ग के बाजू की ओर बगवाड़ा | Closed | 0 | 0 | 2022-08-15
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001032/WC/22012035003208 — CTR कार्य जल निकासी हेतु कच्ची नाली कोटलाखेड़ी मार्ग के बाजू की ओर बगवाड़ा | Closed | 0 | 0 | 2022-08-15
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001032/WC/22012035271980 — सोक पिट निर्माण कार्य ग्रामीण बैंक के पास वाले हेंडपंप पर ग्राम बघवाडा | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001032/WC/22012035271984 — सोक पिट निर्माण कार्य हरिजन मोहल्ला वाले हेंडपंप पर ग्राम बघवाडा | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001032/WC/22012035290180 — Khadapati mandir ke pass Recharge feet Nirman Karya Baghwada | Completed | 25899.46 | 5220 | 2025-05-01 | 2026-04-17
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1732001032/WC/22012035290200 — Shankar mandir ke pass Recharge feet Nirman kary Baghwada | Completed | 25899.46 | 5565 | 2025-05-02 | 2026-04-13
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001032/WC/22012035290248 — Saadh kuaa ke pass Recharge feet Nirman kary Baghwada | Completed | 25899.46 | 5406 | 2025-05-01 | 2026-04-13
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001032/WC/225 — कुपनिर्माण(निर्मलनीर) बघवाडा | Completed | 136383 | 77 | 2009-01-30 | 2023-07-31
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001032/WC/75 — कूप निमार्ण रामकरण / बाबूलाल बघवाडा | Completed | 75774 | 170 | 2008-09-24 | 2023-07-31