## Work List
Exported on: 2026-09-06 00:17:23
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: TILIAAWALI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1732001040/AV/22012034578160 — डायनिग टेवल एव व्रंच निर्माण कार्य माध्मिक शालाभवन के अतिरिकत कछ ग्राम चन्दाखड पंचयात तीली आंवली | Ongoing | 17593.2 | 0 | 2021-07-17
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1732001040/DP/22012034601080 — वशुधा वंदन अमृत वाटिका ग्राम पंचायत तीली आंवली | Ongoing | 55847.4 | 0 | 2023-09-23
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/3651835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105699100 | Ongoing | 27000 | 0 | 2022-07-23
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/4645136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142472785 | Ongoing | 27000 | 0 | 2024-09-25
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/4645138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142472797 | Ongoing | 27000 | 0 | 2024-10-02
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/4646213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142506730 | Ongoing | 27000 | 0 | 2024-11-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5095339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142339591 | Ongoing | 27000 | 0 | 2025-03-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5095349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142351403 | Ongoing | 27000 | 0 | 2025-03-19
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5158770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142852233 | Ongoing | 27000 | 0 | 2025-04-16
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5197530 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146538598 | Ongoing | 27000 | 0 | 2025-05-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5204211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105618205 | Completed | 23490 | 0 | 2025-04-09 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5207010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105700287 | Ongoing | 27000 | 0 | 2025-09-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5223165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142462698 | Ongoing | 27000 | 0 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5480612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105618674 | Ongoing | 27000 | 0 | 2025-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5629856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142471307 | Completed | 23490 | 0 | 2025-07-02 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5630517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126585807 | Completed | 23490 | 0 | 2025-09-17 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5630613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105618776 | Completed | 23490 | 0 | 2025-07-02 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5632027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148993445 | Ongoing | 27000 | 0 | 2025-11-05
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5632343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148497051 | Ongoing | 27000 | 0 | 2026-01-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5632639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142462711 | Ongoing | 27000 | 0 | 2025-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5662944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142464962 | Ongoing | 27000 | 4200 | 2026-01-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001040/IF/IAY/5691721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105618577 | Ongoing | 27000 | 0 | 2025-09-17
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001040/RC/22012034838783 — cc rod nirman kary mukhy marg se khel medan ki or naghjir | Ongoing | 61000 | 0 | 2025-03-19
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1732001040/RS/22012035133809 — आर सी सी नाली निर्माण कार्य ग्राम तीली आंवली | Approved | 0 | 0 | 2024-10-02
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Stabilization Pond for Community / Construction of Stabilization Pond for Community | Construction of Tank | 1732001040/RS/22012035133837 — c c nali nirman kary gram tili anwali | Approved | 39735 | 0 | 2024-11-13
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/202074 — Construction of IAY House -IAY REG. NO. MP-32-001-068-002/06 | Approved | 27000 | 0 | 2015-12-10