## Work List
Exported on: 2026-10-19 12:04:03
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: GURANJAGHAT
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Line Plantation of Forestry Trees for Community | Plantation | 1732001048/DP/22012034624035 — वृक्षारोपण कार्य रोड किनारे गुलाव पटेल के खेत से चंदू मुकाती के खेत कि और गुरंजघाट | Ongoing | 453563.17 | 185463.33 | 2024-07-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1732001048/IC/YD/22012034892591 — sarvjanik kup nirman kary Ajadnagar Paraswada | Ongoing | 605674.76 | 8700 | 2025-10-27
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732001048/IF/22012035175406 — KAPILDHARA KUP NIRMAN KARY GOURABAI JOGARAM PARASWADA | Ongoing | 304941.29 | 38700 | 2024-05-30
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732001048/IF/22012035238415 — कपिलधारा कूप निर्माण कार्य रामसेवक/रामभरोष परसवाड़ा गुरंजघाट | Ongoing | 316434.46 | 0 | 2024-10-15
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001048/IF/IAY/5600584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131828140 | Completed | 23490 | 0 | 2025-06-16 | 2026-08-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001048/IF/IAY/5813028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131830558 | Completed | 23490 | 0 | 2025-10-06 | 2026-08-19
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coast Line Plntation-Coastal Shelter Belt-Comm / Shelterbelt Plantation for Community | Plantation | 1732001048/WC/YD/22012035319673 — vraksha ropan kary shreeram ke khet se forest nake ki or paraswada | Approved | 0 | 0 | 2025-08-16