## Work List
Exported on: 2026-09-14 22:03:14
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: BARAKHADKALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001053/IF/22012035572625 — खेत तालाब निर्माण कार्य अशर्फी लाल लोवंशी ग्राम बराखड कला | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001053/IF/22012035572631 — खेत तालाब निर्माण कार्य ओम प्रकाश भारद्वाज ग्राम बराखड कला | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/3675654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114157909 | Ongoing | 27000 | 0 | 2026-06-08
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/3675664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114158233 | Approved | 27000 | 0 | 2022-04-27
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/3696459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102908444 | Approved | 27000 | 0 | 2022-04-27
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/3712450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101009856 | Approved | 27000 | 0 | 2022-04-27
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/3787002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134792645 | Ongoing | 27000 | 0 | 2024-09-23
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/3898856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149476211 | Approved | 27000 | 0 | 2022-04-27
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4180139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134793999 | Approved | 27000 | 0 | 2022-06-08
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4797787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149030284 | Approved | 27000 | 0 | 2024-09-13
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4800492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151138034 | Completed | 23490 | 0 | 2025-03-17 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4802826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151694654 | Completed | 23490 | 0 | 2025-01-27 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4860836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151693153 | Ongoing | 27000 | 0 | 2024-12-30
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4860837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151693229 | Completed | 23490 | 0 | 2025-02-03 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4869702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102358663 | Completed | 23490 | 0 | 2025-01-13 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/4912806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134792890 | Approved | 27000 | 0 | 2024-09-13
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5112794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102442338 | Completed | 23490 | 0 | 2025-03-21 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5113261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101009592 | Completed | 23490 | 0 | 2025-03-21 | 2026-08-03
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5113268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102350438 | Completed | 23490 | 0 | 2025-03-21 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5118977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134777696 | Completed | 23490 | 0 | 2025-04-14 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5118981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134792713 | Physically Completed | 23490 | 0 | 2025-06-16 | 2026-07-30
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5118982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134792959 | Completed | 23490 | 0 | 2025-03-21 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5120246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101009786 | Physically Completed | 27000 | 0 | 2025-03-21 | 2026-08-30
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5121685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151695837 | Ongoing | 27000 | 0 | 2025-06-09
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5123519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151688007 | Completed | 23490 | 0 | 2025-04-21 | 2026-08-17
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5124551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149033024 | Ongoing | 27000 | 0 | 2026-06-08
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5127219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119533567 | Completed | 23490 | 0 | 2025-04-14 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5127584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104935967 | Ongoing | 27000 | 0 | 2025-03-21
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5128256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149033872 | Completed | 23490 | 0 | 2025-03-24 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5128257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149034020 | Completed | 23490 | 0 | 2025-03-24 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5130105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100921543 | Ongoing | 27000 | 0 | 2025-03-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5130362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149226605 | Completed | 23490 | 0 | 2025-04-14 | 2026-08-19
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5130363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149227179 | Completed | 23490 | 0 | 2025-04-14 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5132451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114848741 | Ongoing | 27000 | 0 | 2025-03-21
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5132748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119090954 | Ongoing | 27000 | 0 | 2025-03-21
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5132968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149029763 | Ongoing | 27000 | 0 | 2026-07-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5133265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102361011 | Completed | 23490 | 0 | 2025-07-28 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5133586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149299198 | Physically Completed | 23490 | 0 | 2025-03-24 | 2026-07-30
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5133589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148988661 | Completed | 23490 | 0 | 2025-03-24 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5133846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119343081 | Completed | 23490 | 0 | 2025-03-21 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5166647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151692080 | Completed | 23490 | 0 | 2025-05-12 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5175358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149477849 | Completed | 23490 | 0 | 2025-04-21 | 2026-08-17
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5195100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151688132 | Approved | 27000 | 0 | 2025-03-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5217259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134794112 | Ongoing | 27000 | 0 | 2025-05-26
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5529823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151693580 | Ongoing | 27000 | 0 | 2025-07-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5630240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117909448 | Ongoing | 27000 | 9000 | 2026-02-02
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5630241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150222564 | Approved | 27000 | 0 | 2025-05-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5630928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149225828 | Approved | 27000 | 0 | 2025-05-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5631172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119533575 | Completed | 23490 | 0 | 2025-07-14 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5631321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149474306 | Completed | 23490 | 0 | 2025-11-17 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5631583 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148971096 | Approved | 27000 | 0 | 2025-05-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5631721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149032921 | Ongoing | 27000 | 4200 | 2026-02-02
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5632349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101009018 | Ongoing | 27000 | 0 | 2026-05-11
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5632350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148827722 | Completed | 23490 | 0 | 2025-09-01 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5717758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151693076 | Approved | 27000 | 0 | 2025-07-08
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5717804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100921623 | Ongoing | 27000 | 1800 | 2026-02-23
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5717952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102908273 | Completed | 23490 | 0 | 2025-09-29 | 2026-08-19
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134777719 | Approved | 27000 | 0 | 2025-06-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151696117 | Approved | 27000 | 0 | 2025-06-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151206116 | Completed | 23490 | 0 | 2025-09-15 | 2026-08-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP134791960 | Ongoing | 27000 | 2100 | 2025-09-15
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149033285 | Ongoing | 27000 | 0 | 2025-11-17
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149028646 | Approved | 27000 | 0 | 2025-07-01
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5718878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149225057 | Approved | 27000 | 0 | 2025-06-18
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5719036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149031685 | Approved | 27000 | 0 | 2025-07-01
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/5872781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100926365 | Ongoing | 27000 | 0 | 2026-04-28
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/664657 — Construction of IAY House -IAY REG. NO. MP1949051 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001053/IF/IAY/668117 — Construction of IAY House -IAY REG. NO. MP2186122 | Approved | 27000 | 0 | 2017-03-15
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001053/RC/22012034827502 — सी सी रोड निर्माण कार्य श्रीकिशन लोवंशी के घर से अग्यश तिवारी के घर की और ग्राम बराखड कला | Ongoing | 37900 | 0 | 2024-09-30
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001053/RC/22012034836817 — सी सी रोड निर्माण कार्य मनोहर तिवारी के घर से अमरा बाई लोवंशी के घर की और | Physically Completed | 20800 | 0 | 2025-04-21 | 2026-08-20
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001053/RC/22012034846247 — cc road nirman kary govind ke ghar se kaluram ke ghar ki or aajad nagar gram barakhad khurd | Ongoing | 60400 | 0 | 2025-10-27
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001053/RC/22012034853221 — cc road nirman kary amarsingh ke ghar se sunil lowanshi ke ghar tak aajad nagar barakhad khurd | Ongoing | 67700 | 0 | 2026-03-09
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001053/RS/22012035129257 — R C C नाली निर्माण कार्य युवराज लोवंशी के घर से दीपक गेदर के घर की ओर बराखड खुर्द | Ongoing | 81000 | 0 | 2024-07-12
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001053/RS/22012035133288 — RCC NALI NIRMAN KARY MANOHAR LOWANSHI KE GHAR SE JAGESHWAR THAKUR KE GHAR KI OR | Approved | 0 | 0 | 2024-09-02
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001053/RS/22012035133289 — RCC NALI NIRMAN KARY MANOHAR LOWANSHI KE GHAR SE JAGESHWAR THAKUR KE GHAR KI OR | Ongoing | 31700 | 0 | 2024-11-04
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Upland Bench Terrace Terrace for Comm / Construction of Upland Bench Terrace for Community | Terracing | 1732001053/WC/22012034669289 — C TR FOOD CONTROL कच्ची नाली निर्माण कार्य माता मंदिर से मेन रोड की ओर ग्राम पंचायत बराखड़ कलां ग्राम | Ongoing | 58203.93 | 0 | 2021-04-30