## Work List
Exported on: 2026-09-09 00:07:05
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: KEVKAJHIR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001068/AV/22012034509398 — shantidham gram narri | Ongoing | 194312.08 | 0 | 2020-09-10
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1732001068/AV/22012034541972 — KAMDHENU GOSHALA GOTA VARRI | Ongoing | 3804449.17 | 16820.13 | 2020-12-22
SEONI MALWA | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1732001068/AV/22012034577426 — डायनिंग टेबल निर्माण कार्य नर्री ग्राम पंचायत केवलाझिर | Ongoing | 18093.2 | 0 | 2021-09-17
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1732001068/AV/22012034668846 — पुलिया निर्माण कार्य ग्राम गोटावर्री में पुनेसिंह के घर के पास | New | 19671 | 0 | 2025-04-14
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001068/IF/22012035277100 — KAPILDHARA KOOP NIRMAN GHIRDHARILAL/SEVARAM GRAM NARRI | Ongoing | 185018.1 | 0 | 2025-02-19
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732001068/IF/22012035435378 — Recharge pit sukhdev/chhanulal/mohan kapil dhara koop ke pass kewlajhir | Approved | 25899.46 | 0 | 2025-04-01
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001068/IF/22012035556636 — Khet Talab Nirman Karya Chunnilal Magli Gram Narri Gram Panchayat Kevlajhir | Approved | 450885.64 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/3698849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102918247 | Ongoing | 27000 | 2100 | 2025-11-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/3705589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103427135 | Completed | 23490 | 0 | 2025-11-29 | 2026-08-20
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/38700 — Construction of IAY House -IAY REG. NO. MP-32-001-068-003/018 | Approved | 27000 | 0 | 2015-11-20
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/3902430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149649072 | Approved | 27000 | 0 | 2022-04-25
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/46655 — Construction of IAY House -IAY REG. NO. MP-32-001-068-003/0019 | Approved | 27000 | 0 | 2015-12-02
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5184477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149513334 | Ongoing | 27000 | 0 | 2025-08-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5189640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148369224 | Ongoing | 27000 | 0 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5206510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105984776 | Ongoing | 27000 | 0 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5216182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102918546 | Ongoing | 27000 | 0 | 2025-05-14
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5226478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105700120 | Ongoing | 27000 | 0 | 2026-06-03
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5237018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105698079 | Ongoing | 27000 | 0 | 2026-06-03
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5241248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148542421 | Ongoing | 27000 | 0 | 2025-11-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5472643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149605924 | Ongoing | 27000 | 0 | 2025-10-16
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5472811 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102933348 | Physically Completed | 23490 | 0 | 2025-11-28 | 2026-07-19
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5472864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115105336 | Ongoing | 27000 | 2100 | 2025-12-05
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5473759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151291611 | Ongoing | 27000 | 0 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5474361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150541978 | Ongoing | 27000 | 0 | 2025-05-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5661177 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103428995 | Ongoing | 27000 | 0 | 2025-11-26
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5663241 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149588424 | Ongoing | 27000 | 0 | 2026-06-03
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151279067 | Ongoing | 27000 | 0 | 2025-08-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106100065 | Ongoing | 27000 | 0 | 2025-12-05
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149590487 | Ongoing | 27000 | 0 | 2026-06-02
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150565274 | Ongoing | 27000 | 2100 | 2025-12-05
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103965787 | Ongoing | 27000 | 0 | 2025-11-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147173792 | Ongoing | 27000 | 0 | 2025-10-09
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147171803 | Ongoing | 27000 | 0 | 2025-11-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103426924 | Ongoing | 27000 | 0 | 2025-11-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149615975 | Ongoing | 27000 | 0 | 2025-11-29
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148503509 | Approved | 27000 | 0 | 2025-04-16
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5691948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151298768 | Ongoing | 27000 | 0 | 2025-11-26
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5692026 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149953889 | Ongoing | 27000 | 0 | 2025-11-29
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5692076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149598276 | Ongoing | 27000 | 0 | 2025-12-05
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5692098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149638235 | Ongoing | 27000 | 0 | 2026-06-10
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5717806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103467186 | Ongoing | 27000 | 0 | 2025-11-26
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5717888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102950886 | Ongoing | 27000 | 0 | 2025-11-29
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5718261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149961667 | Ongoing | 27000 | 0 | 2025-11-28
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5718360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150536135 | Ongoing | 27000 | 0 | 2025-10-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/5718942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114194494 | Ongoing | 27000 | 0 | 2025-11-28
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001068/IF/IAY/980885 — Construction of IAY House -IAY REG. NO. MP3917312 | Approved | 27000 | 0 | 2017-04-01
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001068/RC/22012034848757 — siyaram ke ghar se jourilal ke ghar ki or gotabarri | Approved | 50381 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001068/RC/22012034848759 — main road se haridas ke ghar ki or kevlajhir | Approved | 75570 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001068/RC/22012034851725 — c c road school mian get se aganwadi bhavan tak salai | Approved | 25189 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001068/RC/22012034851728 — c c road lakhan ke ghar se patiram ke ghar ki or | Approved | 75570 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001068/RC/22012034853497 — c c road nirman karye main road se kalu ram ke ghar ki or gotabarri | Approved | 50771 | 0 | 2025-04-14
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001068/RS/22012034483073 — samudayik nadep narri | Ongoing | 24300.51 | 0 | 2020-09-10
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001068/RS/22012034625425 — 4 NADEP NIRMAN KARY GRAM GOTAVARRI GRAM PANCHAYAT KEVLAJHIR | Ongoing | 98095.19 | 0 | 2021-12-03