## Work List
Exported on: 2026-10-20 05:02:56
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: RAVANPIPAL
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001072/AV/22012034373927 — आंगनवाडी भवन र्नि‍मार्ण कार्य रावनपीपल | Completed | 180000 | 169652 | 2018-09-19 | 2019-11-28
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001072/AV/22012034468035 — boundariball niraman parthmik shalmika/madhayamika shala raqvanpipal | Completed | 93000 | 96772 | 2019-09-04 | 2021-02-03
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732001072/AV/22012034512775 — Shantidham Nirman kary Rawanpipal | Completed | 194312.08 | 190606.51 | 2020-09-03 | 2021-05-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001072/AV/22012034578295 — P.S.RAWANPIPALMEDAININGTABLEKANIRMANKARY | Completed | 17093.2 | 8007.95 | 2021-10-28 | 2025-01-24
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001072/AV/22012034593282 — MSMEDAININGTABLENIRMANKARYRAWANPIPAL | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1732001072/DP/22012034532843 — SHANTIDHAM ME VRKSHAROPAN KARYRAVANPIPAL | Completed | 394489.84 | 86450 | 2021-09-09 | 2026-05-26
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1732001072/DP/22012034532845 — SHALA PARNGAN ME PLANTATIION KARY RAWANPIPAL | Completed | 195975.82 | 81725 | 2021-09-16 | 2026-04-08
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1732001072/DP/22012034532846 — SHALA PARNGAN ME PLANTATIION KARY RAWANPIPAL | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1732001072/DP/22012034543765 — Ma Ki bagiya kary G. M.S.Rawanpipal | Closed | 16976.64 | 0 | 2021-10-02
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Gov blding premises-Block Plantation-Horticulture / Block Plantation of Horticulture Trees in Government building premises for Community | Plantation | 1732001072/DP/22012034543828 — Ma Ki bagiya kary Govt.prathmik shala S.Rawanpipal | Closed | 16976.64 | 0 | 2021-10-02
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation-Horticulture-Community / Along the coast Block Plantation of Horticulture Trees for Community | Plantation | 1732001072/DP/22012034604039 — वसुधा वंदन अमृत वाटिका shala parishar gp ravanpipal | Closed | 55847.4 | 0 | 2023-04-14
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001072/FP/22012034629375 — बाड़ नियंत्रण हेतु नाला सफाई कार्य रावनपीपल | Completed | 55915.61 | 37754 | 2022-08-11 | 2024-12-03
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001072/IF/22012034343214 — main road se Rawanpipal ki aur | Completed | 335000 | 153368 | 2017-05-31 | 2023-02-14
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001072/IF/22012034347543 — Rawanpipal se Babadiya marg | Completed | 335000 | 129988 | 2017-06-14 | 2022-01-03
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001072/IF/22012034352383 — Banshropan karya Rawanpipal se faridpur nale kinare | Completed | 535000 | 20290 | 2017-06-28 | 2021-06-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line-coast Plntation-Farm Forstry Trees-Individual / Along the coast Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732001072/IF/22012034352410 — Banshropan karya nahar kinare Rawanpipal | Completed | 535000 | 17476 | 2017-06-21 | 2021-06-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001072/IF/22012034352417 — Banshropan nahar kinare chauki Marg Rawanpipal | Completed | 535000 | 17820 | 2017-06-21 | 2021-06-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001072/IF/22012034352429 — Banshropan karya nale kinare Rawanpipal | Completed | 535000 | 24660 | 2017-06-28 | 2021-09-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001072/IF/22012034377998 — khet med plantation ushabai /Narayan gram ravanpipal | Completed | 187600 | 4744 | 2017-10-11 | 2021-06-11
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1732001072/IF/22012035556552 — Koop Recharge Vimal / Shukhram ke khet pr Ravanpipal | Approved | 25899.46 | 0 | 2025-04-14
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001072/IF/9993667721 — पशुशेड रामक़ष्‍ण आत्‍माराम रावनपीपल | Completed | 88073 | 64033.98 | 2015-06-24 | 2018-04-10
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001072/IF/9993667722 — पशुशेड अमरसिंह कालूराम रावनपीपल | Completed | 88073 | 64147.98 | 2015-06-29 | 2018-04-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001072/IF/9993681008 — मेढ बंधान कार्य रामजीवन / मुल्चन्द रावनपीपल | Completed | 25502 | 15264 | 2015-10-14 | 2016-07-31
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001072/IF/9993685879 — मेढबंधान कार्य गोविन्द / श्रीराम रावनपीपल् | Completed | 25502 | 21306 | 2015-11-04 | 2016-08-02
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001072/IF/9993685881 — मेढबंधान कार्य कमलसिंह / सागर रावनपीपल् | Deleted | 25502 | 0 | 2015-11-04
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/1173436 — Construction of IAY House -IAY REG. NO. MP1004853 | Completed | 15480 | 15480 | 2017-07-26 | 2018-04-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/1175079 — Construction of IAY House -IAY REG. NO. MP1004344 | Completed | 15480 | 14448 | 2017-07-26 | 2018-08-23
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/3708139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105570254 | Completed | 18360 | 17748 | 2022-08-11 | 2023-09-27
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/37693 — Construction of IAY House -IAY REG. NO. MP-32-001-072-001/28 | Completed | 14310 | 14177 | 2015-12-23 | 2018-04-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/479416 — Construction of IAY House -IAY REG. NO. MP1977353 | Completed | 15030 | 15180 | 2017-02-01 | 2017-11-07
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/4798127 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148695061 | Completed | 23490 | 21870 | 2024-11-07 | 2026-08-21
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/4985414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105325124 | Ongoing | 27000 | 22977 | 2025-03-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5105143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149693684 | Ongoing | 27000 | 22977 | 2025-03-20
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5204837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146859855 | Completed | 23490 | 21873 | 2025-05-22 | 2026-08-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5206223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146874851 | Completed | 23490 | 23490 | 2025-07-31 | 2026-08-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5213916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146261383 | Ongoing | 27000 | 8874 | 2025-06-05
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5222354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149701175 | Completed | 23490 | 23490 | 2025-05-01 | 2026-08-21
SEONI MALWA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5244017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146901055 | Ongoing | 27000 | 8400 | 2025-03-03
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/53777 — Construction of IAY House -IAY REG. NO. MP-32-001-072-001/82 | Completed | 14310 | 9853 | 2016-11-23 | 2018-08-23
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001072/IF/IAY/544255 — Construction of IAY House -IAY REG. NO. MP3193392 | Completed | 15030 | 15180 | 2017-02-01 | 2017-11-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5606836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146880859 | Completed | 23490 | 23490 | 2025-05-22 | 2026-08-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732001072/IF/IAY/5607250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146895343 | Ongoing | 27000 | 23490 | 2025-11-06
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001072/LD/120 — Khel Main Sachool Ground Ravanpipal | Completed | 114324 | 55435 | 2011-11-23 | 2012-04-19
SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001072/LD/22012034371379 — medh bandhan | Closed | 0 | 0 | 2018-10-02
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1732001072/LD/22012034954101 — Dugwell रिचार्ज saskiy koop ke pass gp ravanpipal | Completed | 25899.46 | 15658.08 | 2025-05-24 | 2026-05-26
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/167 — P.P.C.C. road Nali Prem ke Ghar se School ki aur Ravanpipal | Completed | 119537 | 56352 | 2012-07-09 | 2012-10-15
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034158290 — पंच परमेश्‍वर रोड वार्ड नम्‍बर 12 में रावनपीपल | Completed | 90535 | 71737 | 2012-12-14 | 2013-03-07
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034169851 — पंच परमेश्‍वर रोड प्रेम के घर से सुधीर के घर की ओर | Completed | 41692 | 41745 | 2013-06-05 | 2014-01-07
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034196990 — पंच परमेश्‍वर रोड व नाली निर्माण बरकुर की चक्‍की | Completed | 175600 | 173535 | 2014-01-01 | 2014-07-14
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034217681 — पंच परमेश्‍वर रोड कुऐ से बंशी के घर की ओर रावनपीपल | Completed | 97192 | 96147 | 2014-05-14 | 2014-11-03
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034227115 — पंचपरमेश्‍वर रोड केवल साध के घर से स्‍कूल की ओर रावनपीपल | Completed | 187826 | 165695.73 | 2014-08-13 | 2018-08-11
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034227118 — पंचपरमेश्‍वर रोड जगदीश के खले से मेन रोड की ओर रावनपीपल | Deleted | 125217 | 0 | 2014-04-30
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034320244 — सी.सी.रोड एवं नाली निर्माण होलीचौक से बासनियाँ रोड की ओर रावनपीपल | Completed | 76336 | 44935 | 2017-01-18 | 2019-03-27
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034324901 — C C ROAD NIRMAN | Closed | 0 | 0 | 2017-04-01
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034327211 — सी.सी.रोड एवं नाली निर्माण स्कूल से मुख्य मार्ग की ओर | Completed | 52163 | 54610 | 2017-02-22 | 2018-08-29
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034374338 — सी सी रोड व नाली नि‍मार्ण | Closed | 0 | 0 | 2018-04-01
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034439058 — cc road | Closed | 0 | 0 | 2018-10-02
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034463113 — CC NALI NIRMAN - RAMESH KE GHAR SE RAMVILAS LOWANSHI KE GHAR KI OR ( GP RAVANPIPAL) | Completed | 17325 | 16014 | 2019-03-08 | 2021-08-10
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034463118 — CC NALI NIRMAN KARYA - KAMAL GURUDEV KE GHAR SE SANTOSH RAGHUWANSHI KE GHAR KI OR ( GP RAVANPIPAL) | Suspended | 5568 | 2454 | 2019-03-08
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034550038 — CC ROAD BADE KUA SE BASANTIBAI KE GHAR KI AUR RAVANPIPAL | Completed | 20097 | 14820 | 2020-12-09 | 2021-05-20
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034554342 — cc road avam nali nirman bade khuye se imali ki or ravanpipal | Completed | 16125 | 21786 | 2020-12-30 | 2021-08-10
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034614422 — cc rode nirman kary shantidham ki or rawanpipal | Completed | 44669 | 39680 | 2023-10-05 | 2024-09-03
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034630304 — पुलिया निर्माण कार्य शांतिधाम मार्ग पर रावनपीपल | Completed | 19650 | 19448 | 2023-05-18 | 2024-06-20
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034669219 — सी सी रोड निर्माण कार्य देवीसिंह रघुवंशी के घर से मुन्नालाल रघुवंशी के घर की और रावनपीपल | Completed | 8917 | 8400 | 2024-02-22 | 2024-09-17
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034679786 — राम मंदिर से राधेश्याम लोवंशी के घर तक उन्नयनीकरण कार्य रावनपीपल | Ongoing | 29968 | 28631.25 | 2024-03-14
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1732001072/RC/22012034822264 — सी सी सड़क निर्माण कार्य शासकिय हैंडपम से रमेश कोटवार की ओर | Ongoing | 20387 | 19187.16 | 2024-07-18
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Farm Roads for Community | Construction of Road and Culvert | 1732001072/RC/22012034822284 — सी सी सड़क निर्माण कार्य मुकेश चौहान के घर से रामविलाश पटेल के घर की ओर | Ongoing | 42031 | 39768.22 | 2024-07-18
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034835387 — सी सी रोड उन्नयनीकरण कार्य महेश नामदेव के घर से बसंत राजपूत के घर की और रावनपीपल | Ongoing | 26734 | 11100 | 2025-02-15
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732001072/RC/22012034835529 — सी सी रोड उन्नियंकरण कार्य राजेश सोंगर के घर से छगनलाल राजपूत के घर की और | Ongoing | 26734 | 13286 | 2025-02-12
SEONI MALWA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001072/RC/36 — ग्रेवल रोड निमार्ण रावण‍पीपल | Completed | 473181 | 4940 | 2008-09-20 | 2023-08-01
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001072/RS/22012034187656 — शौचालय नि‍र्माण मर्यादा अभि‍यान 2 रावनपीपल | Completed | 44000 | 45480 | 2013-12-25 | 2014-01-15
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001072/RS/22012034286703 — शाैचालय निर्माण मन्‍जूलाल / नन्‍हू रावनपीपल | Completed | 3180 | 3180 | 2015-10-07 | 2016-09-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001072/RS/22012034289628 — शोचालय निर्माण कार्य शंकरलाल /कल्लू | Completed | 3180 | 3180 | 2015-10-21 | 2016-09-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034441977 — Nadep nirman kary Basaniya rode kinare Rawanpipal | Closed | 24953.86 | 0 | 2019-04-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034479400 — आर सी सी नाली निर्माण हाइवे से प्राथमिक शाला की और | Completed | 31320 | 31540 | 2020-05-20 | 2020-11-07
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034479560 — आर सी सी नाली निर्माण कमल गुरुदेव के घर से विजय सिंह के घर तक रावनपीपल | Completed | 19931 | 19000 | 2020-05-20 | 2021-07-01
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034479789 — सी सी नाली निर्माण कार्य लक्ष्मन के घर से नाले की और | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Groups / Construction of Berkeley Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034479790 — सी सी निकास नाली लक्ष्मन के घर से नाले की और | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001072/RS/22012034501293 — C.C Nali Nirman Radheshyam ke Ghar Se Namdev Ke Ghar ki aur | Completed | 18426 | 18240 | 2020-12-09 | 2021-05-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001072/RS/22012034501971 — CC NALI RADHESHYAM KE GHAR SE NAMDEV KE GHAR KI AUR RAWANPIPAL | Closed | 0 | 0 | 2020-10-02
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034551031 — Nadep nirman basaniya marg kinare rawanpipal | Ongoing | 24245.25 | 1009 | 2021-09-09
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034551034 — Nadep nirman basaniya marg kinare rawanpipal2 | Closed | 26087.41 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034551038 — Nadep nirman faridpur marg kinare rawanpipal | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034551040 — Nadep nirman mukhya marg kinare rawanpipal | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001072/RS/22012034656810 — Rcc Nali Nirman kary Panchayat bhavan k Pichhe Rawanpipal | Closed | 26882 | 0 | 2022-05-19
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001072/RS/22012034657227 — Nadep nirman kary 5 nag ward no.5 aur ward no.11me rawanpipal | Closed | 118839.03 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1732001072/RS/22012034659563 — Shochalaya nirman kary panchayat bhavan k site me | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1732001072/RS/22012034659565 — Shochalaya nirman kary panchayat bhavan k site me | Deleted | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1732001072/RS/22012034659567 — Shochalaya nirman kary panchayat bhavan k site me | Deleted | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Anganwadi Multi Unit Toilets for Comm / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1732001072/RS/22012034659568 — Shochalaya nirman kary panchayat bhavan k site me Rawanpipal | Closed | 11348 | 0 | 2022-05-27
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001072/RS/22012034697166 — सी पी टी निर्माण बलराम रघुवंशी के खेत से संतोष के खेत तक रावनपीपल | Closed | 0 | 0 | 2023-04-01
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001072/RS/22012035116016 — आर सी सी नाली निर्माण कार्य शिवराज रघुवंशी के घर से फरीदपुर मार्ग की और | Completed | 9584 | 9391 | 2023-10-05 | 2024-09-03
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001072/RS/84002 — मर्यादा अभि‍यान शौचालय ि‍नर्माण रावनपीपल | Completed | 44000 | 42520 | 2013-11-27 | 2013-12-31
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001072/SK/1471 — Bharat Nirman Rajeev Gandhi Sewa Kendra,RAVANPIPAL | Completed | 118101 | 111978 | 2013-12-04 | 2017-11-05
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001072/WC/160 — कूपनिर्माण (कपिलधारा)सुख्‍ाराम/गुरूदयाल रावनपीपल | Completed | 96234 | 16529 | 2009-01-29 | 2009-06-30
SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001072/WC/22012034393871 — basaniya rord par hendpamp ka sokta gadda | Closed | 0 | 0 | 2018-04-14
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1732001072/WC/22012034607004 — पानी निकासी हेतु नाला गेहेरीकररावणपापिलण | Completed | 133217.7 | 85788 | 2021-01-06 | 2022-03-27
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001072/WC/22012034818394 — sokta gadda basaniya marg handpump k pas | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001072/WC/22012034818419 — sokta gadda Aanganbadi hendpupm ke pas | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001072/WC/22012034818423 — sokta gadda nandram k ghar k hendpump k pas | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001072/WC/22012034818426 — sokta gadda ramnath k ghar k pas | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001072/WC/22012034818442 — Roof top rain water harvesting gram panchayat rawanpipal | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732001072/WC/22012034978364 — CTR pani nikas hetu kachchi nali balram rahu k khet ki or | Completed | 47832.59 | 39420 | 2023-06-15 | 2024-07-15
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001072/WC/22012035080388 — पानी निकासी हेतु कच्ची नाली निर्माण बलराम रघुवंशी के खेत से संतोष रघुवंशी के खेत की ओर रावनपीपल | Completed | 25346.36 | 20566 | 2023-09-21 | 2025-01-24
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001072/WC/22012035211594 — नाला उपचार कार्य फरीदपुर मार्ग पुलिया से लक्ष्मण के घर के पीछे रावनपीपल | Approved | 0 | 0 | 2024-04-04
SEONI MALWA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001072/WC/319 — Nirmal Neer Koopnirman Ravanpipal | Completed | 143883 | 139360.93 | 2010-02-03 | 2010-11-10
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001072/WC/71 — कूप निमार्ण सुखराम / गुरूदयाल रावनपीपल | Completed | 75774 | 8272 | 2008-09-22 | 2015-03-31