## Work List
Exported on: 2026-09-14 21:54:13
Filters applied:
Data source: MGNREGA
District: NARMADAPURAM
Block: All
Panchayat: TINSIA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001075/AV/22012034467353 — PANCHAYAT BHAVAN PARISAD KI BAUNDRY WALL NIRMAN TINSYA | Completed | 212000 | 209088 | 2019-11-09 | 2020-09-10
SEONI MALWA | 2020-2021 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1732001075/AV/22012034507351 — aaganwadi nirman tinsya | Closed | 0 | 0 | 2020-04-14
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732001075/AV/22012034508885 — KHEL MAIDAN NIRMAN GRAM BERKHEDI GP TINSYA | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001075/AV/22012034511231 — ANGANWADI BHAVAN NIRMAN KARYA GP TINSYA | Completed | 180000 | 184480 | 2020-06-20 | 2021-02-07
SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001075/DP/22012034407275 — सार्वजनि‍क परि‍सर शांति‍धाम प्रांगण में ति‍नस्‍या | Closed | 0 | 0 | 2018-04-14
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732001075/DP/22012034492019 — KHEL MAIDAN KE CHARO TARAF BRAKCHHA ROPAN | Completed | 222907.7 | 131439.44 | 2020-08-29 | 2021-09-10
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1732001075/DP/22012034543102 — ma ki bagiya kary madhyamik school tinsya | Closed | 0 | 0 | 2021-10-02
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1732001075/DP/22012034603970 — basuda batika bankabedi road tinsya | Physically Completed | 55847.4 | 23852 | 2023-10-10 | 2026-06-29
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732001075/DP/22012034604006 — basuda batika bankabedi road tinsya | Closed | 0 | 0 | 2023-08-07
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1732001075/FP/22012034365480 — Nala Geharikaran Karya | Completed | 63581.1 | 37620 | 2020-07-04 | 2020-11-15
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001075/FP/22012034625059 — नाला गहरीकरण कार्य प्राथमिक शाला से जगदीश राजपूत के घर की ओर बेरखेडी ग्राम पंचायत तिन्सिया | Deleted | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & maint of coastal protection drain - Comm / Repair and maintenance of coastal protection Storm Water drain for Community | Works for Flood Control and Protection | 1732001075/FP/22012034625061 — नाला गहरीकरण कार्य विशना के घर के पास से गुठान की ओर तिन्सिया | Deleted | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001075/FP/22012034625202 — CTR नाला गहरीकरण कार्य प्राथमिक शाला से भरलाय की ओर बेरखेडी तिनस्या | Completed | 95332.33 | 97272 | 2021-06-01 | 2021-07-07
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001075/FP/22012034625203 — CTR नाला गहरीकरण कार्य बादामीलाल के घर से गुठान की ओर तिनस्या | Completed | 94923.41 | 98623 | 2021-05-25 | 2021-07-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034343453 — वृक्षारोपण कार्य GRAM PANCHAYAT TINSYA | Completed | 335000 | 130944 | 2017-05-27 | 2019-12-18
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034348555 — व्रक्षारोपण कार्य तिनस्या 2 tinsya se kanskhedi marg | Completed | 335000 | 277901 | 2017-06-17 | 2022-09-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034348601 — वृक्षा रोपण कार्य तिनस्या बेरखेड़ी 3 | Completed | 335000 | 69400 | 2017-06-17 | 2019-12-18
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034349073 — बेरखेड़ी से भरलाय पहुच मार्ग पर ब्रक्षारोपड़ कार्य 4 | Completed | 335000 | 36336 | 2017-06-24 | 2019-12-18
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034352239 — बेरखेड़ी नाले पर वसरोपन | Completed | 535000 | 80104 | 2017-07-01 | 2019-12-18
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034359479 — वास रोपण तिनस्या | Completed | 535000 | 288347 | 2017-07-01 | 2022-09-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034377677 — किसान की मेड़ पर ब्रक्षारोपड़ अभिताभ/महेस तिनस्या | Completed | 187600 | 5535.2 | 2017-10-07 | 2019-12-18
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012034378499 — जीवन के खेत कि मेड पर व्रछा रोपड् तिनस्या | Deleted | 273840 | 0 | 2017-04-10
SEONI MALWA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Biodrainage-Individuals / Wasteland Block Plantation of Biodrainage Trees for Individuals | Plantation | 1732001075/IF/22012035180939 — NADEP NIRMAN TINSYA | Deleted | 0 | 0 | 2023-10-02
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732001075/IF/22012035434496 — dugwell recharge sarbjanik kua nirbhay singh ke ghar ke paas berkhedi | Deleted | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1732001075/IF/22012035434633 — dugwell recharge sarbjanik kua nirbhay singh ke ghar ke paas berkhedi | Deleted | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001075/IF/22012035435338 — Dugwell recharge gansh prasad s/o hajarilal | Deleted | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001075/IF/22012035435495 — Dugwell recharge vishnu prasad s/o fattu gram tinsya | Deleted | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001075/IF/22012035435632 — khet talab kary nirman ganesh prasad s/o hajarilal berkhedi tinsya | Physically Completed | 55865.38 | 40453.8 | 2025-05-01 | 2026-04-29
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001075/IF/22012035435647 — khet talab kary nirman vishnu prasad s/o fattu gram tinsya | Completed | 55865.38 | 37845 | 2025-05-01 | 2026-03-26
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732001075/IF/22012035436611 — dugwell recharge sarbjanik kua nirbhay singh ke ghar ke paas berkhedi tinsya | New | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1732001075/IF/22012035556473 — richarge pit vinshnu prasad ke kua par gram tinsiya | Physically Completed | 25899.46 | 21788.09 | 2025-06-04 | 2026-04-09
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1732001075/IF/22012035556520 — richarge pit Ganesh prasad ke kua par gram berkhedi gp tinshya | Physically Completed | 25899.46 | 20744.09 | 2025-06-04 | 2026-04-28
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/22012035627012 — Ek Bagiya Maa Ke Name Kusum Bai Vishnu Prasad Dunge GP Tinsya | Ongoing | 184357.02 | 23076.46 | 2025-11-11
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001075/IF/9993666639 — पशुशेड भारतसिह रामकरन तिनस्‍या | Completed | 88073 | 77296 | 2015-06-20 | 2017-11-17
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001075/IF/9993666756 — पशुशेड धनराज राधेश्‍याम सोलंकी तिनस्‍या | Completed | 88073 | 76424 | 2015-06-20 | 2017-11-08
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001075/IF/9993679212 — मेढबंधान गणेश हजारीलाल बेरखेडी ितनस्‍या | Completed | 25502 | 3975 | 2015-10-10 | 2016-06-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001075/IF/9993679220 — मेढबंधान धनराज राधेश्‍याम तिनस्‍या | Completed | 25502 | 12243 | 2015-10-10 | 2016-06-24
SEONI MALWA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Recharge Pits / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1732001075/IF/9993720675 — med bandhan | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Recharge Pits / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1732001075/IF/9993720685 — med vandhan 7 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001075/IF/9993720694 — जीबन के खेत मे | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Recharge Pits / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1732001075/IF/9993720708 — medh vandhan | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1119789 — Construction of IAY House -IAY REG. NO. MP1867112 | Completed | 15480 | 13866 | 2017-06-03 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1146933 — Construction of IAY House -IAY REG. NO. MP1649645 | Completed | 15480 | 15552 | 2017-06-03 | 2018-06-05
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1147148 — Construction of IAY House -IAY REG. NO. MP1677727 | Completed | 15480 | 14874 | 2017-06-03 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1147282 — Construction of IAY House -IAY REG. NO. MP1690686 | Completed | 15480 | 13350 | 2017-07-08 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1147289 — Construction of IAY House -IAY REG. NO. MP1691378 | Completed | 15480 | 13374 | 2017-06-03 | 2018-09-27
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1147632 — Construction of IAY House -IAY REG. NO. MP1735930 | Completed | 15480 | 15516 | 2017-06-03 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1149329 — Construction of IAY House -IAY REG. NO. MP1966477 | Completed | 15480 | 14418 | 2018-01-13 | 2018-09-27
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1156526 — Construction of IAY House -IAY REG. NO. MP3234196 | Completed | 15480 | 13362 | 2017-06-03 | 2018-09-28
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1156609 — Construction of IAY House -IAY REG. NO. MP3252464 | Completed | 15480 | 14418 | 2017-06-03 | 2018-08-27
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1156783 — Construction of IAY House -IAY REG. NO. MP3295849 | Completed | 15480 | 15402 | 2017-06-03 | 2018-09-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1161221 — Construction of IAY House -IAY REG. NO. MP3676478 | Completed | 15480 | 15576 | 2017-06-03 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1161312 — Construction of IAY House -IAY REG. NO. MP3685276 | Completed | 15480 | 15540 | 2017-06-03 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1175537 — Construction of IAY House -IAY REG. NO. MP3183848 | Completed | 15480 | 14886 | 2017-07-22 | 2018-09-27
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1175550 — Construction of IAY House -IAY REG. NO. MP3295893 | Completed | 15480 | 15402 | 2017-07-22 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1175551 — Construction of IAY House -IAY REG. NO. MP3296017 | Completed | 15480 | 15390 | 2018-01-13 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1175610 — Construction of IAY House -IAY REG. NO. MP3624704 | Completed | 15480 | 14394 | 2017-07-22 | 2018-09-27
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/1898310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4200343 | Completed | 15660 | 14442 | 2018-08-18 | 2019-01-26
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/4219234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101005284 | Completed | 18360 | 18136 | 2022-07-26 | 2022-12-12
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/4539409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103595666 | Completed | 23490 | 21141 | 2024-10-31 | 2025-10-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/457436 — Construction of IAY House -IAY REG. NO. MP1655938 | Completed | 15030 | 15402 | 2017-06-03 | 2018-09-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/46657 — इन्दराआवास निर्मान मायाबाई पति सुमेर् सिह् तिनस्या | Completed | 14310 | 17034 | 2016-04-09 | 2017-07-19
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/46658 — इन्दराआवस निर्मान शारदाबाई पति प्रहलाद तिनस्य (बेरखेडी | Completed | 14310 | 13708 | 2015-12-26 | 2017-11-07
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/4987228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101011489 | Completed | 23490 | 21852 | 2025-03-20 | 2025-10-10
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/51050 — Construction of IAY House -IAY REG. NO. MP-32-001-075-001/10 | Completed | 14310 | 14472 | 2016-01-30 | 2017-07-25
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/592837 — Construction of IAY House -IAY REG. NO. MP1289035 | Completed | 15030 | 14382 | 2017-06-03 | 2018-12-26
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/593742 — Construction of IAY House -IAY REG. NO. MP1687041 | Completed | 15030 | 7740 | 2017-06-03 | 2020-05-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/593808 — Construction of IAY House -IAY REG. NO. MP1738425 | Completed | 15030 | 15414 | 2017-06-03 | 2018-08-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/593962 — Construction of IAY House -IAY REG. NO. MP1853006 | Completed | 15030 | 14508 | 2017-05-13 | 2019-01-26
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/594998 — Construction of IAY House -IAY REG. NO. MP3175987 | Completed | 15030 | 16512 | 2017-05-13 | 2018-05-03
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/650494 — Construction of IAY House -IAY REG. NO. MP3252436 | Completed | 15030 | 15600 | 2017-12-02 | 2018-09-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001075/IF/IAY/951089 — Construction of IAY House -IAY REG. NO. MP3070533 | Completed | 15480 | 15414 | 2018-01-13 | 2018-08-20
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001075/LD/141 — Khelmaidan Primery/Middle School Tinsiya | Completed | 363065 | 138496 | 2012-01-02 | 2015-05-18
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732001075/LD/22012034307599 — शांति धाम निर्मान तिनस्या | Completed | 180000 | 174038.5 | 2017-04-22 | 2019-07-19
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732001075/LD/22012034312919 — शांति धाम निर्माण बेरखेड़ी तिनस्या | Completed | 180000 | 176896.96 | 2017-05-20 | 2019-07-19
SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/LD/22012034371341 — medh bandhan | Deleted | 0 | 0 | 2018-10-02
SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/LD/22012034371342 — medh bandhan | Deleted | 0 | 0 | 2018-10-02
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/LD/22012034532102 — CPT-KHEL MAIDAN KE CHARO TARAF | Completed | 22940.7 | 17777 | 2021-06-08 | 2025-02-20
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/LD/22012034532103 — CPT-SHANTIDHAM KE CHARO TARAF | Deleted | 0 | 0 | 2020-10-02
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1732001075/LD/22012034943403 — CTR Plantetion Works Nahar Ke Pass Se Kanskhedi Ki Or GP Tinsya | Physically Completed | 453563.17 | 211050.31 | 2024-08-29 | 2026-05-29
SEONI MALWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001075/RC/03 — ग्रेवल रोड निमार्ण | Deleted | 473181 | 0 | 2011-03-23
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034169178 — पच परमेश्‍वर रोड फूलसि‍ह के घर से योगेश राजपूत के | Completed | 142988 | 115618 | 2013-06-01 | 2018-07-20
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034212764 — सांसद निधी रोड रपटे से श्री हरिसिह सवनेर के घर से | Completed | 24804 | 17568 | 2014-03-08 | 2016-09-07
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034212769 — सांसद निधी रोड श्रीराम जानकी मंदिर से सीता मौसी के | Completed | 33010 | 25614 | 2014-03-08 | 2018-07-18
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034212775 — पंचपरमेश्‍वर रोड हरिओम के घर से मंदिर की ओर ितनस्‍या | Completed | 59152 | 27803 | 2014-05-24 | 2017-06-22
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034223319 — पंचपरमेश्‍वर रोड प्राशाला भवन से रामबाबू के खले क | Completed | 179985 | 151111 | 2014-07-05 | 2016-09-12
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034304070 — सी सी रोड निर्माण नरेंद्र जलखरे के घर से श्रीराम के घर की और | Completed | 69376 | 65428 | 2016-03-19 | 2018-07-20
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034304946 — cc road and nali 2 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034304950 — CC ROAD V NALI NIRMAN 1st | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034304952 — (Rapte se Narendra Patel ke Ghar ki or)CC ROAD V NALI NIRMAN | Completed | 46255 | 46167 | 2017-02-04 | 2018-05-18
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034304954 — CC ROAD V NALI 4th | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034304957 — cc road v nali 5th | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034324187 — C C ROAD NIRMAN | Closed | 0 | 0 | 2017-04-01
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034336417 — RAMESH RAJPUT KE GHAR SE SHAITAN KE MAKAN KI OR ( GRAM BERKHEDI ) TINSIYA | Completed | 81951 | 95014 | 2017-05-06 | 2018-06-10
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001075/RC/22012034365568 — खेत सड्क योजना- बेरखेडी से मकडाई नहर कि और् | Completed | 210000 | 3440 | 2017-10-28 | 2019-08-23
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034374322 — सी सी रोड व नाली नि‍मार्ण | Closed | 0 | 0 | 2018-04-01
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034433644 — रामसिह के घर से धनराज के घर की और सी सी रोड निर्माण् | Completed | 30600 | 30450 | 2019-01-15 | 2019-07-20
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034438950 — cc road | Closed | 0 | 0 | 2018-10-02
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034445126 — दशरथ सिह के घर कि और से रमेश हरिजन के घर कि और सी रोड निर्माण | Closed | 38250 | 0 | 2018-12-29
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034515064 — C C ROAD NIRMAN LAKHAN KE GHAR SE RAJU BADE KE GHAR KI OUR | Completed | 33856 | 33540 | 2020-01-25 | 2020-06-05
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034516398 — C C ROAD NIRMAN guthan se rambabu ke khale ki our | Completed | 31050 | 33060 | 2020-05-09 | 2020-07-20
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034516691 — c c road nirman | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034516693 — c c road nirman | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034516696 — c c road nirman | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034516697 — c c road nirman | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001075/RC/22012034532690 — ग्रेवल मार्ग मुख्य मार्ग से शांतिधाम तक पहुच मार्ग तिनस्या | Completed | 610809.18 | 372001.53 | 2020-12-26 | 2022-04-14
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001075/RC/22012034551325 — SHANTI DHAM PAHUCH MARG | Closed | 0 | 0 | 2020-10-02
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034578296 — सी सी रोड निर्माण कार्य गुठान से सुभाष सरपंच / जीवन सरपंच के घर की ओर तिन्सिया ग्राम पंचायत तिन्सिंय | Completed | 82935 | 79902 | 2021-08-10 | 2022-01-26
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034630539 — C C CHOUK NIRMAN | Closed | 0 | 0 | 2022-11-15
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034630540 — C C CHOUK NIRMAN | Completed | 350042 | 347603 | 2023-06-06 | 2024-01-23
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034646202 — C C Road Nirman Mohan Yadav ke Ghar Se Mukhya Marg Ki Our Tinsya | Completed | 24485 | 23868 | 2023-07-18 | 2024-01-23
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001075/RC/22012034676280 — RCC NALA AND SADAK NIRMAN JASWANT KE GHAR SE MAIN ROAD KI OUR SHANKAR MANDIR KE PASS BERKHEDI | Completed | 37200 | 33150 | 2024-03-12 | 2024-11-11
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034835655 — C C ROAD OUR NALI NIRMAN RAMESH DAMADE KE GHAR SE MUKHYA MARG KI OUR GRAM BERKHEDI | Ongoing | 118572 | 114478 | 2025-02-06
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001075/RC/22012034852420 — shanti dham pahuch marg gram tinsya | Ongoing | 39263 | 15627.6 | 2026-01-29
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Bitumen Top Roads for Community / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1732001075/RC/22012034852732 — c c road nirman ramjanki mandir se ramvilash ke ghar ki our gram tinsya | Ongoing | 58959 | 30537 | 2026-02-12
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286645 — शोचालय निर्माण हरिसिह/ मदनलाल | Completed | 3180 | 2385 | 2015-10-03 | 2017-10-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286659 — शोचालय निर्माण श्रीराम/दल्लू तिनस्या | Completed | 3180 | 1590 | 2015-10-03 | 2017-10-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286677 — Shochalay Nirman Gangavishan/Hemraj Tinsya | Deleted | 3180 | 0 | 2015-10-03
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286679 — Shochalay Nirman Kachorilal s/o Ramgopal Tinsiya | Completed | 3180 | 2385 | 2015-10-03 | 2017-10-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286682 — Sochalay Nirman Rameshchandra Jhandulal Tinsia | Completed | 3180 | 2385 | 2015-10-03 | 2017-10-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286683 — Shochalay Nirman Bhujram s/o Jaganath Tinsiya | Completed | 3180 | 1590 | 2015-10-03 | 2017-10-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034286687 — Sochalay Nirman Anokhilal s/o Bhujram Tinsiya | Completed | 3180 | 2385 | 2015-10-03 | 2017-10-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287772 — Sochalay Nirman Lakhanlal/Radhelal Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287774 — Sochalay Nirman Ramsingh/Kallusingh Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287775 — Sochalay Nirman Pholsingh/Ramgopal Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287776 — Sochalay Nirman Rambabu/Ramesh Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287777 — Sochalay Nirman Ramsigh Gulabsingh Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287778 — Sochalay Nirman Santosh/Jhandulal Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287779 — Sochalay Nirman Shyamlal/Radhelal Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001075/RS/22012034287780 — Sochalay NIrman Vijay/Mishrilal Tinsiya | Deleted | 3180 | 0 | 2015-10-10
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012034579804 — CTR - RCC NALI NIRMAN KARYA SHYAM BABU K GHAR SE RAMBABU K KHALE KI OR TINSYA | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012034579810 — CTR - RCC NALI NIRMAN NARENDRA K GHAR SE SHANKAR MANDIR KI OR - BERKHEDI GP TINSYA | Closed | 0 | 0 | 2021-08-15
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012034653396 — CTR RCC NALI NIRMAN MULCHAND KE GHAR SE GUTHAN KI OUR TINSYA | Completed | 59875 | 23256 | 2022-05-03 | 2022-12-10
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012034655142 — CTR RCC NALI NIRMAN TINSY SHYAMBABU KE GHAR SE RAMBABU KE KHALE KI OUR | Completed | 39413 | 28856 | 2022-05-24 | 2022-12-12
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012034679183 — R C C NALI NIRMAN MARI MATA KE PAS BHUJARIYA GHAT NIRMAN | Completed | 216123 | 146241.37 | 2023-01-31 | 2024-06-21
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012034689240 — R C C NALI NIRMAN ANOKHILAL KE GHAR SE MUKHAY MARG KI OUR | Completed | 42458 | 31416 | 2023-02-07 | 2024-06-21
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012035130066 — R C C NAALI NIRMAN KISHOR RAGHUWANSHI KE GHAR SE SUNITA BAI KE GHAR KI OUR GRAM TINSY | Approved | 58959 | 0 | 2024-04-14
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012035130067 — R C C NAALI NIRMAN KISHOR RAGHUWANSHI KE GHAR SE SUNITA BAI KE GHAR KI OUR GRAM TINSY | Completed | 46394 | 43975.71 | 2024-09-05 | 2025-03-17
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001075/RS/22012035130068 — R C C NALI NIRMAN VIVEK KE GHAR SE KAILASH KE GHAR KI OUR GRAM TINSYA | Ongoing | 27571 | 16036.8 | 2024-08-29
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001075/SK/1536 — Bharat Nirman Rajeev Gandhi Sewa Kendra,TINSIA | Completed | 1018000 | 1007950.72 | 2013-12-14 | 2019-07-20
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732001075/WC/22012034783076 — CRT water diversion chenal holi chok se santi dham ki our dono our berkhedi tinsya | Completed | 50952.74 | 55584 | 2021-08-10 | 2021-10-25
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation-Biodrainage- Gov blding premises / Block Plantation of Biodrainage Trees in Government building premises for Community | Plantation | 1732001075/WC/22012034831458 — CTR- SHANTI DHAM ME PLANTETION GRAM TINSYA | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001075/WC/22012034970738 — ctr nala safai kary tinsya | Deleted | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Fisheries Ponds for Comm / Repair and maintenance of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1732001075/WC/22012034970762 — ctr nala safai kary berkhedi | Completed | 125690.3 | 104808 | 2022-05-31 | 2025-05-25
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/WC/22012034970785 — ctr pani nikasi kar cpt nirman berkhedi se tinsya ki ourt | Completed | 75343.44 | 64668 | 2022-05-31 | 2023-02-20
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/WC/22012034970786 — ctr pani nikasi kar cpt nirman berkhedi se tinsya ki ourt | Deleted | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Stone peripheral Bund for Community / Construction of Stone peripheral/farm/field Bund for Community | Construction of Bund | 1732001075/WC/22012034970787 — ctr pani nikasi kar cpt nirman berkhedi se tinsya ki ourt | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001075/WC/22012034970798 — ctr pani nikasi kar cpt nirman tinsya se berkhedi ki our | Completed | 148186.88 | 128520 | 2022-05-31 | 2023-02-20
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732001075/WC/22012034989938 — Brakchha ropan Shanti dham parisar tinsya | Physically Completed | 411318.19 | 296466.44 | 2022-09-13 | 2026-05-29
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001075/WC/22012035020045 — ctr duarka prasad ke khet se dhamaniya ki our tinsya | Completed | 122613.04 | 97104 | 2022-12-27 | 2023-09-11
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001075/WC/22012035027294 — ctr berkhedi se shanti dham ki our 1000 miter | Deleted | 0 | 0 | 2022-10-02
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001075/WC/22012035044070 — ctr- pani nikasi hetu kachchi nali nirman kary yogesh rajput ke khet se mohan rajput ke khet tak | Completed | 108438.22 | 91375 | 2023-05-23 | 2024-07-30
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001075/WC/22012035078784 — CTR pani nikasi kary kachhi nali nirman yogesh ke khet se tinsya ki aur | Completed | 76819.7 | 65430 | 2023-06-13 | 2025-05-28
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1732001075/WC/22012035086281 — CTR Our barkhedi of gold from CTR water drainage main road | Deleted | 0 | 0 | 2023-04-14
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001075/WC/22012035088919 — CTR Construction of raw drain for water drainage from Main Road to Ganesh farm Berkhedi tinsya | Completed | 94747.62 | 62985 | 2023-07-11 | 2023-09-11
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1732001075/WC/22012035133244 — PAWAN RAJPUT KE GHAR SE SHANKAR MANDIR KI OUR BERKHEDI | Completed | 24485 | 20506 | 2023-10-10 | 2024-06-21
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1732001075/WC/22012035133954 — VIKRAM RAGHUWANSHI KE KHET SE BANKABEDI KI OUR | Closed | 0 | 0 | 2023-05-16
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1732001075/WC/22012035133965 — RAJKUMAR DEVISINGH KE KHET SE BANKABEDI KI OUR TINSYA | Closed | 0 | 0 | 2023-05-16
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1732001075/WC/22012035133972 — AMAR SINGH KE KHET SE TINSYA KI OUR TINSYA | Deleted | 0 | 0 | 2023-05-16
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001075/WC/22012035175197 — CTR. PANI NIKASI RAJKUMAR DEVISINGH KE KHET SE BANKABEDI KI OUR GRAM TINSYA | Completed | 56968.31 | 44710.32 | 2024-06-25 | 2025-03-17
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001075/WC/22012035175199 — CTR. PANI NIKASI VIKRAM RAGHUWANSHI KE KHET SE BANKABEDI KI OUR GRAM TINSYA | Completed | 58825.39 | 45926.34 | 2024-06-18 | 2025-05-25
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001075/WC/22012035289812 — dugwell recharge sarbjanik kua nirbhay singh ke ghar ke paas berkhedi tinsya | Physically Completed | 25899.46 | 22832.99 | 2025-05-30 | 2026-04-09