## Work List
Exported on: 2026-09-13 06:24:54
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: JIRAVEH
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001081/AV/22012034374535 — ग्राम पंचायत भवन नि‍मार्ण कार्य जीरावेह | Completed | 514000 | 511494 | 2018-08-06 | 2020-02-10
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001081/AV/22012034465060 — ग्राम पंचायत भवन की बाउंड्री वाल निर्माण ग्राम पंचायत जीरावह | Completed | 135030 | 134464 | 2019-06-24 | 2019-12-10
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001081/AV/22012034505960 — AGANWADI NIRMAN DETHI | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001081/AV/22012034508790 — आँगन वाड़ी भवन निर्माण ग्राम डेठी गंजाल ग्राम पंचायत जीरावेह | Completed | 180000 | 176768 | 2020-03-16 | 2021-01-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732001081/AV/22012034511961 — शांति धाम निर्माण ग्राम डेठी ग्राम पंचायत जीरावेह | Closed | 194312.08 | 2850 | 2020-07-15
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1732001081/AV/22012034534650 — गौशाला निर्माण ग्राम डेठी ग्राम पंचायत जीरावेह | Closed | 0 | 0 | 2020-04-14
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1732001081/AV/22012034540019 — काम धेनु गौशाला निर्माण ग्राम पंचायत जीरावेह ग्राम डेठी | Completed | 3804449.17 | 3801952.32 | 2020-12-21 | 2026-08-27
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1732001081/AV/22012034541555 — PANCHAYAT BHWAN ME PEVAR BLOCK GRAM PANCHAYAT JIRAVEH | Completed | 12810 | 12540 | 2020-10-29 | 2020-11-30
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Construction of Road and Culvert | 1732001081/AV/22012034541558 — AGANWADI BHWAN ME PEVAR BLOCK GRAM PANCHAYAT JIRAVEH GRAM DETHI | Completed | 7123 | 6460 | 2020-10-29 | 2020-11-22
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001081/AV/22012034578035 — प्राथमिक शाला भवन में डाइनिंग टेवल निर्माण ग्राम जीरावेह | Completed | 17093.2 | 12217.31 | 2021-08-12 | 2026-04-11
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001081/AV/22012034578243 — मिडिल स्कूल मे डाइनिंग टेवल निर्माण ग्राम डेठी ग्राम पंचायत जीरावेह | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1732001081/AV/22012034583795 — श्री क्रष्ण गौशाला निर्माण ग्राम डेठी | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1732001081/AV/22012034583911 — SHREE KRISHNA GOUSHALA DETHI GRAM DETHI GP JERAVEH | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732001081/DP/22012034407222 — वृक्षा रोपण सडक कि‍नारे नदी से जामुनवाली पुलि‍या की ओर जीरावेह | Completed | 342000 | 103344 | 2018-09-06 | 2026-04-08
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1732001081/DP/22012034558062 — braksharopan amrat sarovar dethi | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001081/DP/22012034558077 — अमृत सरोवर बंड पर प्लांटेशन कार्य डेठी जीरावेह | Closed | 410718.19 | 0 | 2022-06-01
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732001081/DP/22012034565082 — VRAKSHAROPAN SADAK KINARE PULIYA KE PAS | Completed | 409718.19 | 64232.3 | 2022-09-08 | 2026-04-19
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732001081/DP/22012034565083 — VRAKSHAROPAN SADAK KINARE PULIYA KE PAS | Closed | 0 | 0 | 2022-08-16
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732001081/DP/22012034565084 — VRAKSHAROPAN SADAK KINARE PULIYA KE PAS | Closed | 0 | 0 | 2022-08-16
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732001081/DP/22012034595209 — वसुधा वंदन अमृत वाटिका तालाव के पास ग्राम डेठी | Closed | 55847.4 | 0 | 2023-08-01
SEONI MALWA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001081/DP/68 — Bas Ropan work Jiraveh | Completed | 417831 | 88753 | 2010-06-30 | 2015-03-23
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001081/FP/22012034366029 — WATERWAY CLEANING OF NALA GRAM PANCHAYAT JIRAVEH | Completed | 214539.55 | 119320 | 2020-06-18 | 2020-08-17
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034343548 — vraksharopan dethi nath mohalla unit 1 | Completed | 335000 | 58512 | 2017-05-29 | 2019-06-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034348523 — vraksharopan dethi nath mohallaunit 2 | Completed | 335000 | 53792 | 2017-06-12 | 2019-03-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034348588 — vraksharopan jirabeh main road unit 03 | Completed | 335000 | 50312 | 2017-06-12 | 2019-07-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034348596 — baas ropan nadi kinare jiraveh unit 4 | Completed | 535000 | 38308 | 2017-06-19 | 2017-10-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034349215 — baas ropan jiraveh nadi kinare unit 5 | Completed | 535000 | 36760 | 2017-06-19 | 2018-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034349219 — baas ropan jiraveh nadi kinare unit 6 | Completed | 535000 | 37152 | 2017-06-19 | 2018-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034349255 — baas ropan ganjal nadi kinare dethi unit 7 | Completed | 535000 | 38960 | 2017-06-19 | 2018-08-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034349259 — baas ropan ganjal nadi kinare dethi unit 8 | Completed | 535000 | 38308 | 2017-06-19 | 2017-10-30
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001081/IF/22012034377018 — kisan ke khet me med pr vraksha ropan unit 9 | Completed | 187600 | 7496 | 2017-10-09 | 2020-08-17
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1732001081/IF/22012034606319 — नन्दन फलोघान झंडू लाल पिता सेवाराम ग्राम देती ग्राम पंचायत जीरावेह | Completed | 139000 | 95422 | 2020-09-28 | 2024-02-21
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001081/IF/22012035301576 — nandan faludhdhan sureshjat pita ramesh jat gram dethi gram panchayat jiraveh | Approved | 0 | 0 | 2025-01-25
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001081/IF/22012035304382 — nandan faludhdhan 2 suresh jat pita ramesh jat gram dethi gram panchayat jiraveh | Physically Completed | 184136.38 | 57663.97 | 2025-03-10 | 2026-06-17
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1732001081/IF/22012035476332 — रिचार्ज पीठ निर्माण कार्य शिवप्रसाद पिता पन्नालाल ग्राम देठी ग्राम पंचायत जीरावेह | Physically Completed | 25899.46 | 24412.19 | 2025-05-12 | 2026-03-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001081/IF/22012035531237 — खेत तालाब निर्माण कार्य ओम प्रकाश पिता मांगीलाल ग्राम डेठी ग्राम पंचायत जीरावेह | Completed | 147621.16 | 77252.53 | 2025-05-20 | 2026-03-31
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001081/IF/22012035532878 — खेत तालाब निर्माण कार्य इमरत लाल कीर पिता भूरेलाल ग्राम डेठी ग्राम पंचायत जीरावेह | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001081/IF/22012035533179 — खेत तालाब निर्माण कार्य अशोक कुमार यादव पिता राम भरोस ग्राम डेठी ग्राम पंचायत जीरावेह | Completed | 147621.16 | 38104.28 | 2025-06-14 | 2026-04-15
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035588655 — एक बगिया माँ के नाम POOJA KAHAR GP JIRAVEH | Ongoing | 269386.03 | 26112.73 | 2025-09-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607585 — EK BAGIYA MA KE NAME LALI BAI KEER / IMRAT LAL KEER KE KHET ME DETHI | New | 0 | 0 | 2025-08-01
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607587 — EK BAGIYA MA KE NAME LALI BAI KEER / IMRAT LAL KEER KE KHET ME DETHI | Approved | 0 | 0 | 2025-08-01
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607594 — EK BAGIYA MA KE NAME LALATA BAI KEER KE KHET ME DETHI | Ongoing | 269386.03 | 27908.8 | 2025-09-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732001081/IF/22012035607598 — EK BAGIYA MA KE NAME POOJA KAHAR KE KHET ME DETHI | New | 0 | 0 | 2025-08-01
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001081/IF/9993666625 — मेढबंधान हरभजन हरिसिंह जीरावेह | Completed | 26136 | 21465 | 2015-06-15 | 2015-12-28
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001081/IF/9993668554 — पशु शेड निर्माण विष्‍णु प्रसाद भुजराम | Completed | 87844 | 84328 | 2015-07-02 | 2016-06-24
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001081/IF/9993668562 — पशु शेड निर्माण महेश प्रसाद राम भाउ | Completed | 87844 | 84150 | 2015-07-02 | 2016-06-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001081/IF/9993678644 — मेड वंधान अशाेक लक्षमीनारायण जीरावेह | Completed | 25502 | 25281 | 2015-10-05 | 2015-12-28
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001081/IF/9993678645 — मेड वंधान रमेश / रामभाऊ जीरावेह | Completed | 25502 | 24168 | 2015-10-05 | 2015-12-28
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001081/IF/9993695630 — मेड बंधान हरनारायण\ हजारीलाल डेठी | Completed | 25502 | 22737 | 2015-12-14 | 2016-01-23
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1206788 — Construction of IAY House -IAY REG. NO. MP1982719 | Completed | 15480 | 15660 | 2018-05-07 | 2018-11-05
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1207282 — Construction of IAY House -IAY REG. NO. MP3532268 | Completed | 15480 | 15660 | 2018-05-07 | 2018-09-10
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1207286 — Construction of IAY House -IAY REG. NO. MP3546034 | Completed | 15480 | 15660 | 2018-04-30 | 2018-08-21
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1342302 — Construction of IAY House -IAY REG. NO. MP3543759 | Completed | 15480 | 15660 | 2018-05-07 | 2018-09-10
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1883398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4701379 | Completed | 15660 | 15312 | 2018-08-27 | 2018-12-20
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1883887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4679346 | Completed | 15660 | 15312 | 2018-08-27 | 2018-12-20
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1884067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5099180 | Completed | 15660 | 15660 | 2018-08-27 | 2018-12-02
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/1909296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4735563 | Completed | 15660 | 15486 | 2018-08-20 | 2018-12-11
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/2126838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4711993 | Completed | 15840 | 15488 | 2019-07-01 | 2019-12-08
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/2128377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4751479 | Completed | 15840 | 15488 | 2019-07-09 | 2019-12-08
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/2130023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4762743 | Completed | 15840 | 16596 | 2019-07-01 | 2020-06-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/361357 — Construction of IAY House -IAY REG. NO. MP1151031 | Completed | 15030 | 14612 | 2017-02-06 | 2018-01-13
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/383155 — Construction of IAY House -IAY REG. NO. MP1160988 | Completed | 15030 | 15076 | 2017-02-27 | 2018-01-16
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/383209 — Construction of IAY House -IAY REG. NO. MP1161205 | Completed | 15030 | 15420 | 2017-02-06 | 2018-01-16
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/389453 — Construction of IAY House -IAY REG. NO. MP1186917 | Completed | 15030 | 15300 | 2017-02-06 | 2018-01-16
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/3904810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149770025 | Completed | 18360 | 15912 | 2022-07-01 | 2022-11-29
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/3913526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151097654 | Completed | 18360 | 18360 | 2022-06-16 | 2022-11-29
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/3914469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151273596 | Completed | 18360 | 17136 | 2022-07-28 | 2022-11-29
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/399244 — Construction of IAY House -IAY REG. NO. MP1209520 | Completed | 15030 | 15360 | 2017-02-06 | 2018-01-17
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/399466 — Construction of IAY House -IAY REG. NO. MP1209976 | Completed | 15030 | 14328 | 2017-02-27 | 2018-01-17
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/399504 — Construction of IAY House -IAY REG. NO. MP1210020 | Completed | 15030 | 15016 | 2017-02-06 | 2017-11-08
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/404313 — Construction of IAY House -IAY REG. NO. MP1227268 | Completed | 15030 | 15300 | 2017-02-06 | 2018-01-17
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732001081/IF/IAY/40710 — Construction of IAY House -IAY REG. NO. MP-32-001-081-001/73सुशीला बाई /रामाधार | Completed | 14310 | 15124 | 2015-12-28 | 2017-11-08
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/409759 — Construction of IAY House -IAY REG. NO. MP1258302 | Completed | 15030 | 14896 | 2017-01-30 | 2017-11-08
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/416294 — Construction of IAY House -IAY REG. NO. MP1302976 | Completed | 15030 | 15120 | 2017-01-30 | 2018-01-19
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/419010 — Construction of IAY House -IAY REG. NO. MP1320508 | Completed | 15030 | 14028 | 2017-01-30 | 2018-01-19
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4206753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150914026 | Completed | 18360 | 18360 | 2022-07-28 | 2022-12-28
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4381429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151098866 | Completed | 18360 | 18360 | 2022-11-24 | 2023-05-16
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4664032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149769959 | Completed | 23490 | 21870 | 2024-10-28 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4664033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149769990 | Completed | 21870 | 21832.2 | 2024-10-28 | 2025-03-10
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4668317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150912537 | Completed | 21870 | 20169 | 2024-10-09 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4728187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149770001 | Completed | 21870 | 21870 | 2024-10-09 | 2025-03-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/476361 — Construction of IAY House -IAY REG. NO. MP1920545 | Completed | 15030 | 15150 | 2017-01-30 | 2018-01-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/4914989 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151274468 | Completed | 23490 | 23400 | 2025-03-21 | 2026-08-20
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/51055 — Construction of IAY House -IAY REG. NO. MP-32-001-081-001/39कांति बाई/हरि प्रसाद | Completed | 14310 | 14639 | 2016-02-01 | 2017-11-08
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/51056 — Construction of IAY House -IAY REG. NO. MP-32-001-081-001/95 उषा बाई /दयाराम | Completed | 14310 | 14138 | 2016-02-15 | 2017-11-08
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732001081/IF/IAY/51058 — Construction of IAY House -IAY REG. NO. MP-32-001-081-002/13सारदा बाई /रामलाल | Completed | 14310 | 14472 | 2015-12-28 | 2017-11-08
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5118671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106743948 | Ongoing | 27000 | 23139 | 2025-03-26
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5124610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125351403 | Completed | 23490 | 23202 | 2025-03-20 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5126067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150910122 | Completed | 23490 | 23202 | 2025-03-20 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5126108 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106155974 | Completed | 23490 | 23463 | 2025-03-20 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5129160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149770012 | Completed | 23490 | 23463 | 2025-03-20 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5130473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151273805 | Completed | 23490 | 23463 | 2025-03-20 | 2026-08-19
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5130474 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151273954 | Ongoing | 27000 | 22617 | 2025-03-26
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5131700 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151280941 | Completed | 23490 | 23094 | 2025-03-20 | 2026-08-20
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5131806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118073131 | Completed | 23490 | 23202 | 2025-03-20 | 2026-08-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5630340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115204235 | Completed | 23490 | 20097 | 2025-06-21 | 2026-08-22
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5630850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149983124 | Completed | 23490 | 21924 | 2025-07-05 | 2026-08-22
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/5729502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100858710 | Completed | 23490 | 18270 | 2025-08-18 | 2026-08-22
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/609622 — Construction of IAY House -IAY REG. NO. MP1208503 | Completed | 15030 | 15188 | 2017-02-27 | 2018-01-19
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/636146 — Construction of IAY House -IAY REG. NO. MP1602651 | Completed | 15030 | 15188 | 2017-02-27 | 2017-11-08
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/846764 — Construction of IAY House -IAY REG. NO. MP1448084 | Completed | 15480 | 16512 | 2017-05-08 | 2017-11-08
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/877419 — Construction of IAY House -IAY REG. NO. MP1828175 | Completed | 15480 | 14964 | 2017-05-08 | 2017-11-08
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/883457 — Construction of IAY House -IAY REG. NO. MP1910087 | Completed | 15480 | 15480 | 2017-07-17 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/883826 — Construction of IAY House -IAY REG. NO. MP1915165 | Completed | 15480 | 15308 | 2017-05-08 | 2017-11-08
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/885274 — Construction of IAY House -IAY REG. NO. MP1935114 | Completed | 15480 | 15480 | 2017-08-28 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/886024 — Construction of IAY House -IAY REG. NO. MP1944990 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/886223 — Construction of IAY House -IAY REG. NO. MP1948333 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/886362 — Construction of IAY House -IAY REG. NO. MP1949873 | Completed | 15480 | 15480 | 2017-06-05 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/911407 — Construction of IAY House -IAY REG. NO. MP2294974 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/913620 — Construction of IAY House -IAY REG. NO. MP2327616 | Completed | 15480 | 15480 | 2017-06-12 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/937008 — Construction of IAY House -IAY REG. NO. MP2763686 | Completed | 15480 | 15480 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/937628 — Construction of IAY House -IAY REG. NO. MP2776235 | Completed | 15480 | 15136 | 2017-05-15 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/945501 — Construction of IAY House -IAY REG. NO. MP2930013 | Completed | 15480 | 15480 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/945734 — Construction of IAY House -IAY REG. NO. MP2935949 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/945911 — Construction of IAY House -IAY REG. NO. MP2939497 | Completed | 15480 | 15136 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/946179 — Construction of IAY House -IAY REG. NO. MP2945170 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/946190 — Construction of IAY House -IAY REG. NO. MP2945476 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/946626 — Construction of IAY House -IAY REG. NO. MP2956824 | Completed | 15480 | 15136 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/946630 — Construction of IAY House -IAY REG. NO. MP2956921 | Completed | 15480 | 15480 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/948536 — Construction of IAY House -IAY REG. NO. MP3008339 | Completed | 15480 | 15480 | 2017-05-08 | 2018-01-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/948538 — Construction of IAY House -IAY REG. NO. MP3008393 | Completed | 15480 | 14964 | 2017-05-08 | 2018-01-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/948756 — Construction of IAY House -IAY REG. NO. MP3014765 | Completed | 15480 | 14792 | 2017-05-08 | 2018-01-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/948831 — Construction of IAY House -IAY REG. NO. MP3016210 | Completed | 15480 | 14964 | 2017-05-08 | 2018-01-21
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/967776 — Construction of IAY House -IAY REG. NO. MP3492565 | Completed | 15480 | 15136 | 2017-07-17 | 2018-01-21
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/967781 — Construction of IAY House -IAY REG. NO. MP3492649 | Completed | 15480 | 15480 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/969086 — Construction of IAY House -IAY REG. NO. MP3527302 | Completed | 15480 | 15480 | 2017-05-08 | 2017-11-11
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001081/IF/IAY/969494 — Construction of IAY House -IAY REG. NO. MP3537316 | Completed | 15480 | 15136 | 2017-05-08 | 2018-01-19
SEONI MALWA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001081/LD/22012034295047 — SHANTI DHAM JIRAVEH | Completed | 180000 | 162127 | 2016-12-19 | 2018-04-11
SEONI MALWA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001081/LD/22012034309613 — शन्तिधाम निर्माण | Closed | 180000 | 0 | 2017-04-01
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732001081/LD/22012034313229 — shanti dham dethi | Completed | 18000000000 | 1376 | 2017-05-15 | 2018-10-21
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001081/LD/22012034943919 — चारागाह निर्माण गौशाला के पास डेठी ग्राम पंचायत जीरावेह | Approved | 0 | 0 | 2024-08-16
SEONI MALWA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001081/RC/125 — grabal road Balkishan ke makan se magilal ke khet tak(Jiraveh) | Completed | 305751 | 317950.35 | 2010-05-29 | 2010-05-29
SEONI MALWA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001081/RC/130 — Mahesh Gurjar ke Makan se Golgaon Marg per nahar t | Completed | 419671 | 385262 | 2011-10-29 | 2016-06-27
SEONI MALWA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001081/RC/132 — Graval Road Rikhiram ke Makan se Choukigawa ki Nah | Completed | 419671 | 344042 | 2011-11-19 | 2016-06-27
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/200 — P.P.C.C. road Nali Ramvilas ke ghar se ramesh ka | Completed | 186277 | 126556 | 2012-10-27 | 2016-06-27
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034154895 — P.P.C.C.road Nali Kishan Patil ke ghar se Main r | Completed | 77458 | 58104 | 2013-01-16 | 2015-03-26
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034181628 — पंच परमेश्‍वर रोड मेन रोड से ि‍वरेन्‍द्र जाट के घर | Completed | 61168 | 45718 | 2013-09-09 | 2014-03-28
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034223223 — सांसदनिधी रोड बांकेजी के घर के सामने से जीरावेह | Completed | 22593 | 18081 | 2014-07-07 | 2016-03-31
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034227043 — पंचपरमेश्‍वर रोड रामविलास बांके के घर से रामबाबू के घर की ओर जीरावेह | Deleted | 123126 | 0 | 2014-08-11
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034295357 — सी. सी. रोड से गाव की और सी.सी. रोड एवं नाली निर्माण ग्राम -डेठी | Completed | 79287 | 75425 | 2016-01-04 | 2016-08-20
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034303377 — ccroad1 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034303378 — ccroad2 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034307014 — सी. सी. रोड एव नाली निर्माण हरिजन मोह्हला जीरावेह | Deleted | 0 | 0 | 2016-03-18
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001081/RC/22012034307024 — ग्रेवल रोड जीरावेह से निरखी पहुच मार्ग | Deleted | 0 | 0 | 2016-03-18
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034314562 — सी. सी. रोड व नाली निर्माण श्याम बांके के घर से राम बाबू के घर कि और जिरावेह | Completed | 79287 | 57092 | 2016-11-14 | 2017-12-01
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034321821 — सी सी रोड एवं नाली निर्माण रामेश्वर की दुकान से सुशीला बाई के घर की और ग्राम जीरवेह | Completed | 10422000000 | 56663 | 2017-02-13 | 2017-11-08
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034324904 — सी सी रोड एवं नाली निर्माण मंदिर से होलो चौक की और ग्राम जीरावेह | Completed | 62386 | 61952 | 2019-07-23 | 2019-11-20
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Culvert / Construction of Culvert / cross drainage structues for Community | Culvert | 1732001081/RC/22012034344603 — sansad nidi se puliya nirman jiraveh jamun bale nale par | Deleted | 0 | 0 | 2017-06-30
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034344606 — sansad nidi se puliya nirman jiraveh jamun bale nale par | Completed | 105803 | 110112 | 2017-07-17 | 2018-10-12
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034371417 — सी सी रोड व नाली निर्माण मेन रोड से रेल्वे स्टेशन कि ओर ग्राम डेठी ग्रा.पं जीरावेह | Completed | 49500 | 49068 | 2018-09-17 | 2018-11-10
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034385419 — सांसद नीधी से सी. सी. रोड निर्माण नदी से जामून वाले नाले कि आेर ग्राम पंचायत जीराबेह | Completed | 32479 | 32016 | 2018-04-02 | 2018-10-12
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034391423 — सी.सी. रोड निर्माण गुर्जर मोहळला जीरावेह | Completed | 20718 | 20706 | 2018-07-23 | 2018-08-31
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034393050 — सांसद निधि से सी सी रोड निर्माण जामुन वाले नाले से आम वाले नाले कि ओर ग्राम जीरावेह | Completed | 33856 | 33408 | 2018-08-27 | 2018-10-12
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034441424 — Cc road | Closed | 0 | 0 | 2018-10-02
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034471021 — सांसद निधि से सी सी रोड निर्माण जामुन वाले नाले से आगे की ओर ग्राम जीरावेह | Completed | 32649 | 32560 | 2019-07-23 | 2019-09-10
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034546550 — PANCHAYAT BHWAN ME PEVAR BLOCK GRAM PANCHAYAT JIRAVEH | Closed | 0 | 0 | 2020-10-02
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001081/RC/22012034571672 — grewal road nirman mukhya marg se goushala ki our gram dethi gram panchayat jiraveh | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034672900 — सी सी रोड निर्माण समोता बाई के घर से कैलाश नाथ के घर कि और | Completed | 58623 | 48672 | 2024-02-15 | 2025-03-10
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034673012 — सी सी रोड निर्माण रामनाथ के घर से राजकुमार आदिवासी के घर कि और ग्राम जीरावेह | Closed | 0 | 0 | 2023-08-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034673013 — सी सी रोड निर्माण रामनाथ के घर से राजकुमार आदिवासी के घर कि और ग्राम जीरावेह | Closed | 0 | 0 | 2023-08-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034673014 — सी सी रोड निर्माण रामनाथ के घर से राजकुमार आदिवासी के घर कि और ग्राम जीरावेह | Completed | 35875 | 24572 | 2024-03-16 | 2024-10-04
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034679400 — सांसद निधि से सी सी रोड निर्माण आम वाले नाले के पास ग्राम जीरावेह ग्राम पंचायत जीरावेह | Completed | 38485 | 38463 | 2024-03-16 | 2024-10-18
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034823919 — सी सी रोड निर्माण शंकर सेठ के घर से रमेश ठाकुर के घर कि और ग्राम जीरावेह | Completed | 35297 | 35201.43 | 2024-09-16 | 2025-03-10
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034823987 — सी सी रोड निर्माण रामकृष्णा रात्रे के टप्पर से पुलिया कि और ग्राम जीरावेह | Completed | 36480 | 36033.01 | 2024-09-02 | 2025-03-10
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034825983 — सी सी रोड निर्माण महेश के घर से ओमप्रकाश के खले कि और ग्राम जीरावेह | Ongoing | 36480 | 36238.78 | 2024-12-30
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034826005 — सी सी रोड निर्माण अनिल के घर से रामविलाश के खले कि और ग्राम जीरावेह | Completed | 55539 | 55270.29 | 2024-11-25 | 2025-03-10
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034849539 — सी सी रोड निर्माण मानु पटेल के घर से बजरंग मंदिर कि और ग्राम जीरावेह | Approved | 50381 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034849868 — सी सी रोड कि साइड पट्टी निर्माण मानु पटेल के घर से बजरंग मंदिर कि और ग्राम जीरावेह | Ongoing | 50381 | 17598.7 | 2026-02-16
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001081/RC/22012034851604 — सी सी रोड निर्माण चंदू के घर से गुलाब के घर कि और ग्राम डेठी | Ongoing | 30228 | 15107.87 | 2026-02-02
SEONI MALWA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001081/RC/64 — ग्रेवल रोड निमार्ण जीरावेर | Completed | 426493 | 496199.41 | 2008-09-20 | 2011-06-29
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034261642 — मर्यादा अभ्‍िायान जिरावेह 1 | Completed | 32400 | 32400 | 2014-08-18 | 2015-03-25
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034261645 — मर्यादा अभियान जिरावेह डेटी 2 | Completed | 21600 | 21600 | 2014-08-18 | 2015-03-25
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034286089 — शौचालय निर्माण रमेश नाथ /शंकर नाथ डेठी | Completed | 3180 | 3180 | 2015-10-05 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034286458 — शौचालय निर्माण विष्णु / झबबू लाल डेठी | Completed | 3180 | 3180 | 2015-10-05 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034286461 — शौचालय निर्माण प्रकाश नाथ /सरवन नाथ डेठी | Completed | 3180 | 3180 | 2015-10-05 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034286730 — शौचालय निर्माण महेश/शुंदर लाल जीराबेह | Completed | 3180 | 3180 | 2015-10-05 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034286754 — शौचालय निर्माण मांगीलाल /आमरया जीराबेह | Completed | 3180 | 3180 | 2015-10-05 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034286755 — शौचालय निर्माण दयाराम/अधारीलाल डेठी | Completed | 3180 | 3180 | 2015-10-05 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034290425 — शौचालय निर्माण श्यामबाई/कल्लु डेठी | Completed | 3180 | 3180 | 2015-10-26 | 2015-10-31
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034290512 — शौचालय निर्माण रामेश्चंद्र/शिवचरण जीराबेह | Completed | 3180 | 3180 | 2015-10-26 | 2015-10-31
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001081/RS/22012034290530 — शौचालय निर्माण इमरतलाल/भूरेलाल डेठी | Completed | 3180 | 3180 | 2015-10-26 | 2015-10-31
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034476991 — सी सी नाली निर्माण नदी से रमेश के घर की और ग्राम पंचायत जीरावेह | Completed | 129000 | 128766 | 2019-12-02 | 2020-05-08
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034478604 — सी सी नाली निर्माण होलिचोक से हरिजन वार्ड की ओर ग्राम जीरावेह | Completed | 23875 | 23750 | 2021-01-11 | 2021-02-20
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034478605 — सी सी नाली निर्माण रामेश्वर की दुकान से रिखीराम के घर की ओर ग्राम जीरावेह | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034478606 — सी सी नाली निर्माण संतोष के घर से स्कूल कि और ग्राम जीरावेह | Completed | 50787 | 50730 | 2020-12-10 | 2021-01-10
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034498401 — water ve claining birj no 694/01 | Completed | 6596 | 5700 | 2020-10-29 | 2021-02-04
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034498829 — drean killing poll no 694/11-696/30 | Completed | 49468 | 42940 | 2020-10-26 | 2021-02-04
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034498830 — water ve killing birj no 694/02 | Completed | 6599 | 6270 | 2020-11-23 | 2021-02-04
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732001081/RS/22012034507992 — सामुदायिक स्वच्छता परिसर निर्माण ग्राम पंचायत जीरावेह | Completed | 72833 | 43657 | 2021-02-15 | 2022-03-17
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034530753 — आर सी सी नाली निर्माण रामेश्वर की दुकान से रिखीराम के घर की ओर ग्राम जीरावेह | Completed | 69666 | 66028 | 2021-07-08 | 2022-12-30
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001081/RS/22012034532135 — नाडेप निर्माण नदी के पास ग्राम जीरावेह | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034596722 — आर सी सी नाली निर्माण बालकिशन के घर से नाले की और ग्राम जीरावेह | Completed | 15494 | 18335 | 2021-11-04 | 2021-12-25
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034596766 — आर सीसी नाली निर्माण भिलाला मोहल्ला ग्राम जीरावेह | Completed | 20130 | 14111 | 2021-12-09 | 2024-02-21
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034659671 — सी सी नाली निर्माण हेंडपंप से दीपक के घर की ओर ग्राम देठी ग्राम पंचायत जीरावेह | Closed | 21347 | 0 | 2022-05-27
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034698702 — आर सी. सी .नाली निर्माण प्रकाश जाट के घर से राजू कहार के घर की ओर ग्राम देठी ग्राम पंचा. जीरावेह | Closed | 0 | 0 | 2023-04-14
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034700612 — आर सी. सी .नाली निर्माण प्रकाश जाट के घर से राजू कहार के घर की ओर ग्राम देठी ग्राम पंचा. जीरावेह | Completed | 20090 | 19448 | 2023-09-15 | 2024-02-21
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012034700641 — आर सी. सी .नाली निर्माण पूनम जाट के घर से पुलिस चौकी की ओर ग्राम देठी ग्राम पंचा. जीरावेह | Completed | 27817 | 26299 | 2023-08-03 | 2024-02-21
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001081/RS/22012035121931 — आर सी सी नाली निर्माण हेंड पंप से वीरेंद्र पटेल के घर कि और ग्राम डेठी | Completed | 34905 | 34599 | 2024-02-01 | 2024-07-17
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001081/SK/1131 — Bharat Nirman Rajeev Gandhi Sewa Kendra,JIRAVEH | Completed | 118101 | 117651 | 2013-09-30 | 2016-12-09
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1100 — Nirmalvatika Budhusingh Gopal Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1101 — Nirmalvatika Durgaprasad Gopal Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1102 — Nirmalvatika Kamlabai Jageshwar Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1103 — Nirmalvatika Shriram Tilsiram Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1104 — Nirmalvatika Rajaram Bhagirath Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1105 — NIrmalvatika Vishnu Mangilal Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1106 — Nirmalvatika Sunil Ramsingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1107 — Nirmalvatika Rameshchand Harisingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1108 — NIrmalvatika Bhimsingh Vishram Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1109 — Nirmalvatika Gabbulal Mangalsingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1110 — Nirmalvatika Devkibai Gambhirsingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1111 — Nirmalvatika Mangilal Amaraya Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1112 — Nirmalvatika Shantabai Kamalsingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1113 — NIrmalvatika Ajabsingh Gambhira Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1114 — NIrmalvatika Mansingh Alamsingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-11-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1115 — NIrmalvatika Jaikishan Bholu Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-07-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1116 — NIrmalvatika Sharvansingh Amarya Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1117 — Nirmalvatika Ramkishore Rambharos Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1118 — NIrmalvatika Mohan Harisingh Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/1119 — NIrmalvatika Ramkrishna Govind Jiraveh | Completed | 2825 | 2700.95 | 2012-05-28 | 2012-08-10
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001081/WC/132 — निर्मल नीर कूप निर्माण (ढैठी) | Completed | 136383 | 315277.67 | 2009-02-08 | 2015-03-23
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1732001081/WC/22012034554909 — payjal koop dethi | Completed | 242453.87 | 185462.44 | 2020-06-01 | 2022-12-20
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1732001081/WC/22012034607638 — sokta gadda nath mohalla kuye ke paas gram dethi | Completed | 16283.77 | 9457 | 2021-04-08 | 2024-02-21
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001081/WC/22012034607639 — sokta gadda nath mohalla hendpump ke paas gram dethi | Completed | 7142.15 | 3860 | 2021-04-08 | 2024-02-21
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001081/WC/22012034607645 — sokta gadda aganvadi ke paas gram dethi | Completed | 7142.15 | 2316 | 2021-04-08 | 2025-05-16
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1732001081/WC/22012034783526 — सी टी आर बाढ़ नियत्रण कार्य रिखीराम के घर से नदी की ओर ग्राम जीरवेह | Completed | 46003.28 | 39758 | 2021-07-08 | 2022-03-27
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001081/WC/22012034785898 — रूफ वाटर हार्वेस्टिंग पंचायत भवन जीरावेह | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001081/WC/22012034785911 — रूफ वाटर हार्वेस्टिंग माध्यमिक शाला भवन देती ग्राम पंचायत जीरावेह | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732001081/WC/22012034797162 — ग्राम पंचायत भवन में वाटर हार्वेस्टिंग कार्य ग्राम जीरावेह | Closed | 0 | 0 | 2021-05-25
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001081/WC/22012034922947 — सी पी टी कच्ची नाली निर्माण पुलिया के पास ग्राम पंचायत जीरावेह | Completed | 31698.68 | 28302 | 2022-03-17 | 2022-05-17
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1732001081/WC/22012034958031 — अमृत सरोवर निर्माण कार्य ग्राम डेठी | Deleted | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1732001081/WC/22012034958032 — अमृत सरोवर निर्माण कार्य गौ शाला के पीछे ग्राम डेठी ग्राम पंचायत जीरावेह | Completed | 1161000 | 1153597.28 | 2022-05-13 | 2025-05-16
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001081/WC/22012035027962 — सी पी टी कच्ची नाली निर्माण ग्राम जीरावेह मे गोविंद के घर से रमन बाँके के खेत तक | Completed | 48065.74 | 38600 | 2023-06-08 | 2025-04-24
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1732001081/WC/22012035027963 — सी पी टी कच्ची नाली निर्माण ग्राम जीरावेह मे गोविंद के घर से रमन बाँके के खेत तक | Closed | 0 | 0 | 2022-08-16
SEONI MALWA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001081/WC/22012035203604 — सी पी टी कच्ची नाली निर्माण राजाराम के खेत से नहर कि और ग्राम जीरावेह | Completed | 49880.84 | 41238.52 | 2024-07-11 | 2025-04-24
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001081/WC/67 — कूप निर्माण विष्‍णुप्रसाद / भुजराम | Completed | 75774 | 3765 | 2008-09-22 | 2023-08-01