## Work List
Exported on: 2026-09-03 13:10:31
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: PIPALTHAUN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001083/IF/22012035390555 — khet talab nirman kary anita bai /shivprasad pipalthon | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732001083/IF/22012035572512 — खेत तलाब निर्माण कार्य श्यामवती /छन्नू लाल खकरापूरा पीपलठोन | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001083/IF/IAY/929174 — Construction of IAY House -IAY REG. NO. MP2593778 | Approved | 27000 | 0 | 2017-04-15
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001083/IF/IAY/960187 — Construction of IAY House -IAY REG. NO. MP3293039 | Approved | 27000 | 0 | 2017-04-15
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001083/IF/IAY/960189 — Construction of IAY House -IAY REG. NO. MP3293089 | Approved | 27000 | 0 | 2017-04-15
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001083/IF/IAY/976797 — Construction of IAY House -IAY REG. NO. MP3753359 | Approved | 27000 | 0 | 2017-04-15
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001083/RC/22012034853312 — cc rode nirman kary berakhedi me hedpam se mukesh ke ghar kin or | Approved | 31019 | 0 | 2025-08-12
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001083/RC/22012034853315 — cc rode nirman kary chandra shekhar ke ghar se makhan ke ghar ki or khakharapura | Approved | 31700 | 0 | 2025-12-26
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001083/RC/22012034853348 — cc rode nirman kary shantidham phuch marg khakrapura piplthon | Approved | 50600 | 0 | 2025-12-26
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001083/RC/22012034853542 — cc rode nirman kary sanjay ke ghar se dhramveer ke ghar ki or | Approved | 4821 | 0 | 2025-12-26
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001083/RS/22012035133204 — R CC Nali nirman jagdish ke ghar se men rode ki or bendripura | Approved | 43380 | 0 | 2024-10-22
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001083/WC/22012034718577 — CTR Braksha ropan kary umesh ke ghar ke aage se sadak kinare khakrapura pipalthon | Ongoing | 394459.68 | 1200 | 2021-06-04