## Work List
Exported on: 2026-09-10 15:38:01
Filters applied:
Data source: MGNREGA
District: NARMADAPURAM
Block: All
Panchayat: GHANA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034392524 — aganwadi bandarkho | Completed | 180000 | 173280.95 | 2018-10-27 | 2020-05-24
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001086/AV/22012034505473 — पंचायत भवन परिसर में बॉऊंड्रीबॉल निर्माण कार्य़ ग्राम घाना | Completed | 46300 | 47124 | 2020-02-15 | 2021-03-04
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732001086/AV/22012034507619 — बाऊंड्रीबाँल निर्माण कार्य प्राथमिक शाला भवन शेटेलाइट परिसर,घानाघाट,घाना | Closed | 98496 | 0 | 2019-11-23
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001086/AV/22012034508487 — SHANTIDHAM NIRMAN KARY BANDARKHO | Closed | 0 | 0 | 2020-03-01
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732001086/AV/22012034508888 — KHEL MAIDAN NIRMAN GRAM BANDARKHO GP GHANA | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034509405 — shantidham bandarkho gp ghana | Completed | 194312.08 | 176861.2 | 2020-05-30 | 2026-05-23
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513682 — govt.kuye ke pass ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513684 — school ke pas ghanaghat | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513685 — matamohla ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513686 — ompraksha ke ghar ki or | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513687 — school ke pass ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513688 — jhandachouk bandarho | Closed | 0 | 0 | 2020-04-04
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513689 — chopal ke pass | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513690 — bich mohla bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513692 — jhiriya mohla bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513693 — nadef bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034513694 — nadef bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515392 — nadef nirman ghana school ke pass ghana | Completed | 30025.06 | 23674.6 | 2020-08-15 | 2022-01-25
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515393 — nadef nirman school ke pass bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515394 — nadef nirman setlight ke pas ghanaghat tola ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515395 — nadef nirman mata mahala ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515396 — nadef nirman jhanda ghouk bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515397 — nadef mandir ke aage ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515399 — nadef panchayat bhavan ke pass ghana | Completed | 81890.63 | 69351.63 | 2020-08-30 | 2022-01-25
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034515400 — nadef nirman bich moholla bandarkho | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034579229 — MSBANDARKHOMEDAININGTABLEKANIRMANKARY | Closed | 17093.2 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034579243 — PSDHANAMEDAININGTABLEKANIRMANKARY | Closed | 0 | 0 | 2021-04-14
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732001086/AV/22012034579972 — PSGHANAMEDRININGTABLENIRMANKARY | Closed | 17093.2 | 0 | 2021-04-01
SEONI MALWA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/DP/22012034485251 — तालाब निर्माण कार्य राधेश्याम/रामप्रसाद,घाना | Closed | 38000 | 0 | 2020-01-26
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1732001086/DP/22012034531661 — VRAKSHAROPEN KARY PANCHAYAT BHUVAN PRISAR GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732001086/DP/22012034531664 — VRAKSHAROPEN KARY GHANAGHAT ROAD SE NAHAR KI OR GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coast Line Plantation of Forestry Trees for Comm / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1732001086/DP/22012034537595 — C.T.R. vraksharopan work nirman ghanaghat se nahar ki or ghana gp ghana | Completed | 394489.84 | 194312 | 2021-09-23 | 2026-05-27
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001086/DP/22012034544061 — prathamik school ghana ma ki bagiya gp ghana | Closed | 0 | 0 | 2021-10-26
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001086/DP/22012034544062 — pms school bandarkho gp ghana | Closed | 0 | 0 | 2021-10-26
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732001086/DP/22012034555743 — vrakasha ropan karay road se shantidham ki or ghana | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732001086/DP/22012034555744 — vrakasha ropan karay road se shantidham ki or ghana | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732001086/DP/22012034555745 — vrakasha ropan karay road se shantidham ki or ghana | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001086/DP/22012034595896 — vasuda bandan amrit vatika gp ghana | Completed | 55847.4 | 20345 | 2023-09-14 | 2026-05-27
SEONI MALWA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001086/DP/80 — Nandanphalodhan Jamvati/Gulabsingh Ghana | Completed | 147922 | 7599.94 | 2010-07-04 | 2015-03-23
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732001086/DP/93 — Nandanphalodhan Sumersingh Ramgopal Ghana | Completed | 95927 | 2800 | 2011-08-25 | 2015-03-23
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732001086/FP/22012034369027 — nadigahrikaran ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732001086/FP/22012034624198 — nadi gahrikaran ghana | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1732001086/FP/22012034624424 — CTR NADI GAHRIKARAN GRAM GHANA GP GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732001086/FP/22012034625345 — CTR NALI NIRMAN KARY GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732001086/FP/22012034625346 — CTR NALI NIRMAN KARY BANDARKHO | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732001086/FP/22012034625347 — CTR NALI NIRMAN KARY GHANA{GHANAGHAT} GP GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Renovation of minor Canal for Community / Renovation of minor Canal for Community | Renovation of Canal | 1732001086/IC/22012034890163 — vanshi lal / hira kapildhara kuup niran kary bandarkho gp ghana | Approved | 327631.47 | 0 | 2025-04-14
SEONI MALWA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/1000020163 — कपि‍लधारा कूप गंगू छोटू घाना | Completed | 204052 | 121976.31 | 2013-06-15 | 2017-01-20
SEONI MALWA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/1000020179 — कपि‍लधारा कूप गेंदालाल ताराचंद बादरखौ घाना | Completed | 204052 | 98348 | 2013-06-15 | 2017-01-20
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034343120 — व़क्षारोपण कार्य नहर से घाना रोड पर घाना | Completed | 335000 | 267784 | 2017-05-27 | 2022-05-17
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034348543 — VRAKSHAROPEN GHANA SE SURESH KE KHET TAK GHANA | Completed | 335000 | 264663 | 2017-06-17 | 2022-08-17
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034349619 — vraksharopan SADAK KINARE PIPAL BABA SE BANDERKHO TAK bandarkho | Completed | 335000 | 48048 | 2017-06-24 | 2019-11-16
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034349622 — VRAKSHAROPEN SADAK KINARE SURESH KE KHET SE PIPAL BABA TAK GHANA | Completed | 335000 | 70680 | 2017-06-17 | 2019-11-16
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034351269 — VANSROPAN NAHAR KINARE GHANAGHAT TOLA GHANA 1 | Completed | 535000 | 34548 | 2017-06-17 | 2019-05-18
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034351279 — VANSROPAN NAHAR KINARE GHANA GHANA 2 | Completed | 535000 | 80582 | 2017-06-17 | 2019-11-16
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034352103 — vraksharopen pul ke age nahar kinare ghana | Deleted | 0 | 0 | 2017-04-14
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034352108 — vraksharopan Bans Roped pul ke aage ghana | Completed | 535000 | 45768 | 2017-06-24 | 2019-11-02
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034352364 — VRAKSHA ROPAN Bans Ropan NALE ME GHANA | Completed | 535000 | 54272 | 2017-06-24 | 2019-11-02
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034352377 — VANSROPAN Bans Ropan NALE Kinare BANDARKHO GHANA | Deleted | 535000 | 0 | 2017-06-17
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732001086/IF/22012034352387 — VANSROPAN NALE DHAKNIPURA KI OR GHANA | Completed | 535000 | 17052 | 2017-06-24 | 2019-11-02
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034387594 — kapildhara koop | Closed | 0 | 0 | 2018-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732001086/IF/22012034552336 — premsingh manohar khet talab ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732001086/IF/22012034554197 — khet talab anokhi bandarkho gp ghana | Completed | 108814.67 | 78660 | 2020-06-06 | 2021-03-04
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732001086/IF/22012034554201 — khet talab radheshyam bandarkho gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732001086/IF/22012034555535 — khet talab shyamlal sukharam ghana gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034555537 — kapildhara koop nirman sarvan jageswar ghana gp ghana | Deleted | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732001086/IF/22012034555553 — radhabai premsingh khet talab bandarkho gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732001086/IF/22012034555554 — khetb talab lachiya bai bandarkho gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732001086/IF/22012034555557 — foolwati bai khet talab ghana gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732001086/IF/22012034555558 — sudha bai khet tabal ghana gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732001086/IF/22012034555560 — vimla bai khet talab ghana gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1732001086/IF/22012034586495 — nandanfaloudhyan ajabsingh | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1732001086/IF/22012034598324 — nandan faloudhan ajabsingh panna lal bandarkho | Ongoing | 115000 | 3792 | 2020-09-19
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034624034 — kapildhara koopnirman sarvan /jageswar ghana | Completed | 267788.18 | 227718.84 | 2020-10-24 | 2021-09-20
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034624038 — kapildhara koop nirman jokhilal bandarkho gp ghana | Completed | 267788.18 | 259098.84 | 2020-10-24 | 2022-01-25
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1732001086/IF/22012034631655 — medbandahn sukhalal | Closed | 0 | 0 | 2020-10-02
SEONI MALWA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of earthen contour bunds for individuals / Construction of Earthen contour Bund for Individuals | Construction of Bund | 1732001086/IF/22012034668807 — khet talab pankaj bhatti bandarkho | Deleted | 0 | 0 | 2021-01-01
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034671602 — kapildhar koop nirman manohar lal bandarkho gp ghana | Deleted | 0 | 0 | 2021-01-01
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034671603 — kapildhara koopnirman nanuram bandarkho | Deleted | 0 | 0 | 2021-01-01
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034674009 — kapildhara koopnirman balaram ghana | Deleted | 0 | 0 | 2021-01-01
SEONI MALWA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034674010 — kapildhara koopnirman balaram ghana | Closed | 0 | 0 | 2021-01-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732001086/IF/22012034687147 — kapildhara koop nirman manohar bandarkho | Deleted | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732001086/IF/22012034687148 — kapildhara koop nirman manohar bandarkho | Deleted | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034687152 — kapildhara koop nirman manohar bandarkho | Deleted | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034687153 — kapildhara koop nirman manohar bandarkho | Deleted | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Brushwood Check Dam for Individuals / Construction of Brushwood Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1732001086/IF/22012034687156 — khet talab nirman pankaj bandarkho | Deleted | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034687162 — balaram kapildhara koop nirman kary ghana | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034687170 — nanuram kapirdhara koopnirman kary bandarkho | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034695453 — CTR-KAPILDHARA KOOP NIRMAN MANOHAR/GORELAL GRAM BANDERKHOH | Completed | 269355.3 | 237452.68 | 2021-04-15 | 2025-04-30
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1732001086/IF/22012034695533 — CTR-KHET TALAB NIRMAN PANKAJ/HARIRAM BANDERKHOH | Completed | 110516.06 | 52862 | 2021-04-15 | 2025-01-22
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034702748 — CTR KAPILDHARA KOOP NIRNAM NANURAM BANDARKHO GP GHANA | Completed | 269355.3 | 173773 | 2021-12-10 | 2026-05-23
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012034704571 — CTR KAPILDHARA KOOPNIRMAN BALARAM GHANA GP GHANA | Closed | 269355.3 | 0 | 2021-04-01
SEONI MALWA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012035175595 — kapildhara koop nirman kary ghana shankar lal | Ongoing | 304941.29 | 53436 | 2023-10-12
SEONI MALWA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035303108 — vanshi lal / hira kapildhara koop nirman kary bandarkho gp ghana | Approved | 0 | 0 | 2025-01-25
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732001086/IF/22012035385378 — vanshi lal / hira kapildhara kuup niran kary bandarkho gp ghana | Ongoing | 327631.47 | 2610 | 2025-05-13
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035434002 — Dugwell recharge santosh / buddu gram bandarkho gp Ghana | New | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035434009 — Dugwell recharge santosh / buddu gram bandarkho gp Ghana | New | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035434017 — Dugwell recharge santosh / buddu gram bandarkho gp Ghana | Completed | 25899.46 | 15660 | 2025-05-03 | 2026-04-02
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035434159 — Dugwell recharge jokhi / हिरा gram bandarkho gp Ghana | Completed | 25899.46 | 15660 | 2025-05-03 | 2026-04-02
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035434250 — Dugwell recharge suresh / chhagan gram Ghana gp Ghana | Physically Completed | 25899.46 | 23876.99 | 2025-05-09 | 2026-04-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035439563 — Dugwell recharge sarvan/ jageswar gram ghana gp Ghana | New | 0 | 0 | 2025-04-14
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035439569 — Dugwell recharge sarvan/ jageswar gram ghana gp Ghana | Physically Completed | 25899.46 | 24659.99 | 2025-05-12 | 2026-04-07
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035442914 — khet talab nirman kary maheshsid bandarkho | Completed | 55865.38 | 32882.03 | 2025-05-08 | 2026-04-21
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035529347 — गुलाब गंगाराम खेत तालाब bandarkho gp ghana | Completed | 55865.38 | 30272 | 2025-05-29 | 2026-05-09
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/22012035533276 — Khet तालाब रामबिलास gp ghana | Completed | 55865.38 | 30272.3 | 2025-05-23 | 2026-05-03
SEONI MALWA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Earthen peripheral bund for indiv / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1732001086/IF/22012035533337 — सुनीता खेत तालाब gp ghana | Approved | 0 | 0 | 2025-04-14
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993667216 — मेढबंधान अर्जुनसिंह रामगोपाल बादरखौ घाना | Completed | 44955 | 29415 | 2015-06-20 | 2016-03-12
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732001086/IF/9993667223 — पशुशेड अमरसिंह कुंजीलाल बादरखौ घाना | Completed | 88073 | 61695.97 | 2015-06-20 | 2018-08-22
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993678114 — मेड बंधन शेर सिंह राम चरण | Completed | 30602 | 19398 | 2015-10-03 | 2015-11-18
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/9993678121 — मेड़वधान राम बिलास कुंजीलाल घाना | Deleted | 0 | 0 | 2015-04-01
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993678125 — रामविलास कुंजीलाल मेढबंधान निर्माण | Completed | 36591 | 18444 | 2015-10-03 | 2015-12-05
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993678424 — मेड बंधन श्रीराम /कोमलराम | Deleted | 35702 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993678431 — मेड बंधन सुंदरलाल /नंदराम | Closed | 35702 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993678439 — मेड बंधन बादामी लाल /मगू | Deleted | 35702 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993678449 — मेड बंधन मथरा बाई /रामदाश | Deleted | 35702 | 0 | 2015-10-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993686807 — मेढबंधान िशवकुमार रामाधार बादरखौ घाना | Completed | 30602 | 25281 | 2015-11-07 | 2015-12-16
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993686812 — मेढबंधान गुलाबसिंह गंगू बादरखौ घाना | Completed | 35702 | 28302 | 2015-11-07 | 2015-12-16
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/9993689071 — मेडबंधान ईमारत लाल / मांगीलाल बंदरखोह | Completed | 44955 | 15264 | 2015-11-21 | 2016-06-27
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/9993689074 — मेडबंधान मनोहर / गोरेलाल बंदरखोह | Deleted | 0 | 0 | 2015-08-15
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993689077 — मेडबंधान मनोहर / गोरेलाल बंदरखोह | Completed | 30602 | 28779 | 2015-11-21 | 2016-03-12
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993689080 — मेडबंधान जोखि लाल / हिरा बंदरखोह | Completed | 30602 | 28620 | 2015-11-28 | 2016-03-12
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993690555 — मेढ बंधान निर्माण वंशीलाल हीरालाल बाद बांदरख़ो | Completed | 30602 | 29256 | 2015-11-28 | 2016-06-27
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993691093 — मदन/रामकरण मेढ़बंधन बांदरखोह | Completed | 35702 | 32118 | 2015-12-05 | 2016-06-27
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993691100 — रामेश्वर / मुन्ना मेढ़बंधन बांदरखोह | Deleted | 35702 | 0 | 2015-08-15
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993691106 — रामदास / सुखदेव मेढ़बंधन बांदरखोह | Deleted | 35702 | 0 | 2015-08-15
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Reclamation of Land / Drainage of chaur or waterlogged areas Land for Individuals | Land Development | 1732001086/IF/9993691111 — तुलसीराम /प्रताप मेढ़बंधन बांदरखोह | Completed | 42500 | 38955 | 2015-12-05 | 2016-06-27
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732001086/IF/9993721335 — medbhandhan karya 2 | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/1878910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4033146 | Completed | 17100 | 15392 | 2018-08-18 | 2020-12-18
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/1879338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4007791 | Completed | 15660 | 15660 | 2018-08-18 | 2019-01-10
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/1921965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4033204 | Completed | 15660 | 15324 | 2018-08-25 | 2019-05-30
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/1922429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4033170 | Completed | 15660 | 15486 | 2018-09-16 | 2019-01-07
SEONI MALWA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/1922443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4043940 | Completed | 15660 | 15486 | 2018-09-16 | 2019-01-07
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/2093672 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4021104 | Completed | 15840 | 14886 | 2019-08-10 | 2020-05-16
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/2093744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4021933 | Completed | 15840 | 15840 | 2019-08-10 | 2020-03-11
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/2093759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4022186 | Completed | 15840 | 15840 | 2019-07-20 | 2019-10-04
SEONI MALWA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/2093762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4022228 | Completed | 15840 | 15840 | 2019-08-10 | 2019-12-02
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3223649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4362046 | Completed | 17370 | 16812 | 2021-08-26 | 2024-02-20
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4013871 | Completed | 17370 | 17299 | 2021-08-19 | 2024-02-20
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4021918 | Completed | 17370 | 16931 | 2021-08-19 | 2024-02-20
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4022295 | Completed | 17370 | 17088 | 2021-08-26 | 2024-06-27
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4022324 | Completed | 17370 | 17189 | 2021-11-25 | 2024-06-06
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4026515 | Completed | 17370 | 17266 | 2021-08-19 | 2024-07-01
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4026696 | Completed | 17370 | 17060 | 2021-12-02 | 2023-09-27
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4044541 | Completed | 17370 | 15773 | 2021-08-26 | 2024-02-20
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4044560 | Completed | 17370 | 16791 | 2021-08-19 | 2023-09-27
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3224435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4045105 | Completed | 17370 | 16159 | 2021-08-19 | 2024-02-20
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3226472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4033141 | Completed | 17370 | 17125 | 2022-01-21 | 2024-02-20
SEONI MALWA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/3227654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4022306 | Completed | 17370 | 14708 | 2021-08-19 | 2024-02-20
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/40717 — Construction of IAY House -IAY REG. NO. MP-32-001-086-001/043 | Completed | 14310 | 12024 | 2016-04-16 | 2017-01-07
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/40718 — Construction of IAY House -IAY REG. NO. MP-32-001-086-001/36 | Completed | 14310 | 10384 | 2016-04-16 | 2019-08-23
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/40719 — Construction of IAY House -IAY REG. NO. MP-32-001-086-001/052 | Completed | 14310 | 14948 | 2016-04-16 | 2017-07-25
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/410749 — Construction of IAY House -IAY REG. NO. MP1268729 | Completed | 15030 | 15051 | 2017-01-28 | 2018-04-10
SEONI MALWA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/46667 — Construction of IAY House -IAY REG. NO. MP-32-001-086-001/055 | Completed | 14310 | 12166 | 2016-01-23 | 2018-09-25
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/482963 — Construction of IAY House -IAY REG. NO. MP2026435 | Completed | 15030 | 15138 | 2017-01-28 | 2018-04-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/484122 — Construction of IAY House -IAY REG. NO. MP2046268 | Completed | 15030 | 14191 | 2017-01-28 | 2018-09-25
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/568781 — Construction of IAY House -IAY REG. NO. MP4022810 | Completed | 15030 | 15486 | 2017-01-28 | 2019-01-02
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/568812 — Construction of IAY House -IAY REG. NO. MP4026656 | Completed | 15030 | 15486 | 2017-01-28 | 2019-02-05
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/568831 — Construction of IAY House -IAY REG. NO. MP4029605 | Completed | 15030 | 15486 | 2017-01-28 | 2019-01-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/568866 — Construction of IAY House -IAY REG. NO. MP4033031 | Completed | 15030 | 15486 | 2017-01-28 | 2019-01-02
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/621864 — Construction of IAY House -IAY REG. NO. MP2590490 | Completed | 15030 | 15248 | 2017-03-04 | 2018-04-10
SEONI MALWA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/640211 — Construction of IAY House -IAY REG. NO. MP1005959 | Completed | 15030 | 14684 | 2017-03-03 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/666226 — Construction of IAY House -IAY REG. NO. MP2045471 | Completed | 15030 | 14792 | 2017-05-27 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/666576 — Construction of IAY House -IAY REG. NO. MP2069346 | Completed | 15030 | 14620 | 2017-09-30 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/673245 — Construction of IAY House -IAY REG. NO. MP2589251 | Completed | 15030 | 15480 | 2017-05-27 | 2018-04-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/673271 — Construction of IAY House -IAY REG. NO. MP2590494 | Completed | 15030 | 15136 | 2017-05-06 | 2018-04-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/674105 — Construction of IAY House -IAY REG. NO. MP2669248 | Completed | 15030 | 14792 | 2017-05-27 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/674233 — Construction of IAY House -IAY REG. NO. MP2685008 | Completed | 15030 | 14792 | 2017-09-30 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/674353 — Construction of IAY House -IAY REG. NO. MP2702375 | Completed | 15030 | 15136 | 2017-05-27 | 2018-04-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/682975 — Construction of IAY House -IAY REG. NO. MP3875702 | Completed | 15030 | 15308 | 2017-09-30 | 2018-04-10
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/683132 — Construction of IAY House -IAY REG. NO. MP3917578 | Completed | 15030 | 14792 | 2017-05-27 | 2018-05-09
SEONI MALWA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732001086/IF/IAY/683178 — Construction of IAY House -IAY REG. NO. MP3923642 | Completed | 15030 | 15148 | 2017-10-28 | 2018-05-03
SEONI MALWA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001086/LD/22012034301935 — shantidham nirman gram ghana | Completed | 183600 | 179684.76 | 2017-02-11 | 2018-12-17
SEONI MALWA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732001086/LD/22012034309618 — शन्तिधाम निर्माण | Closed | 0 | 0 | 2017-04-01
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1732001086/LD/22012034314419 — शांति‍धाम नि‍मा्र्ण कार्य बांदरखौ घाना | Completed | 180000 | 1032 | 2017-05-27 | 2019-06-30
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Waterlogged Land for Community / Reclamation of Community Waterlogged Land | Land Development | 1732001086/LD/22012034593633 — basuda bandan amrit vatika gp ghana | Closed | 0 | 0 | 2023-04-14
SEONI MALWA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732001086/PG/22012034312111 — खेल मैदान नि‍मार्ण कार्य घाना | Completed | 153600 | 1032 | 2017-05-27 | 2019-06-30
SEONI MALWA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/148 — P.P.C.C. road Nali Durpal ke ghar se jhanda chouk ki aur Ghana | Completed | 99309 | 44339 | 2012-03-14 | 2012-09-03
SEONI MALWA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034162011 — पंच परमेश्‍वर रोड सुरेश/मथुराप्रसाद के घर से माता | Completed | 142988 | 115086 | 2012-12-27 | 2014-05-21
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034214446 — पंच परमेश्‍वर रोड बुददू के घर से शेरसिह के घर की ओ | Completed | 123010 | 121520.99 | 2014-04-26 | 2016-06-24
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034214447 — पंचपरमेश्‍वर रोड बरजोर के घर से रामचंद के घर की ओर | Completed | 109225 | 104833.99 | 2014-04-05 | 2016-06-24
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034297052 — Panch parmeshwar cc road&nali Norman champalal ke ghar se Mukesh ke ghar ki our dhana | Completed | 52846 | 3498 | 2016-01-23 | 2016-08-10
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034305439 — CC ROAD | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034305456 — cc road nirman | Deleted | 0 | 0 | 2016-01-26
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034318287 — CC ROAD AND NALI NIRMA PM ROAD SE BALRAM KE GHAR TAK BANDARKHO | Completed | 52846 | 42949 | 2016-12-24 | 2019-07-16
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034324639 — सी सी रोड ऍव नाली निर्माड premsingh se ghar se shanti ram ke ghar ki aur ghana | Closed | 41962 | 0 | 2017-01-26
SEONI MALWA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034326573 — CC ROAD & NALI NIRMAN RAMCHANDRA KE GHAR SE GOVT KOOP KI OR | Completed | 50000 | 21724 | 2017-02-11 | 2019-05-24
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034374386 — सी सी रोड व नाली नि‍मार्ण | Closed | 0 | 0 | 2018-04-01
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034439030 — c c road nirman karya | Closed | 0 | 0 | 2019-04-14
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034462551 — cc road shersing ke ghar se school ki or bandarkho | Closed | 0 | 0 | 2019-01-26
SEONI MALWA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034462861 — CC ROAD & NALI NIRMAN SHERSINGH KE GHAR SE SCHOOL KI OUR BANDARKHOH,GHANA | Closed | 0 | 0 | 2018-12-29
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034512990 — cc road and nali nirman ghanaghtat tola ghana | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034522990 — cc road nirman shankar ke ghar se school ki or ghana gp ghana | Closed | 0 | 0 | 2020-04-01
SEONI MALWA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034608025 — CC ROAD NALI NIRMAN | Closed | 0 | 0 | 2022-04-01
SEONI MALWA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034654011 — rahul ke ghar se ramfal ke ghar ki or bandarkho gp ghana | Completed | 47970 | 47864 | 2024-01-11 | 2024-08-02
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034825059 — cc road nirman kary rajesh ke ghar se shankar ke ghar ki or | Completed | 11716 | 11419.8 | 2024-11-18 | 2025-03-24
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732001086/RC/22012034825061 — CC ROAD NIRMAN KARY RAMFAL KE GHAR SE ASHOK KE GHAR KI OR BANDARKHOH | Completed | 14068 | 13635.03 | 2024-10-14 | 2025-03-24
SEONI MALWA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732001086/RC/22012034839887 — krisna ke ghar se nanu ke ghar ki or bandarkho gp ghana | Ongoing | 51887 | 46969.15 | 2025-11-03
SEONI MALWA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732001086/RC/98 — ग्रेवल रोड निमार्ण घाना | Completed | 450000 | 50014 | 2008-09-19 | 2015-03-23
SEONI MALWA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732001086/RS/22012034252046 — मर्यादा अभि‍यान घाना 1 | Completed | 54000 | 53650 | 2014-07-19 | 2015-04-30
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034478619 — 2 nadef nirman kary ghana | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034478669 — nadef nirman bandarkho | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034479565 — 4नाडेप निर्माण कार्य ग्राम घाना | Closed | 0 | 0 | 2020-01-26
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001086/RS/22012034531521 — C.T.R.C.C NALI NIRMAN PRAHLAD KE GHAR SE SCHOOL KI OR GHANA {GHANAGHAT} | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001086/RS/22012034531522 — C.T.R.C.C NALI NIRMAN PRAHLAD KE GHAR SE SCHOOL KI OR GHANA {GHANAGHAT} | Closed | 20199 | 0 | 2021-07-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034531619 — C.T.R.NADEF NIRMAN SETLIGHT SCHOOL KE PASS GHANA{GHANAGHAT} GP GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034531620 — C.T.R.NADEF NIRMAN SETLIGHT SCHOOL KE PASS GHANA{GHANAGHAT} GP GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034531621 — C.T.R.NADEF NIRMAN SETLIGHT SCHOOL KE PASS GHANA{GHANAGHAT} GP GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034531622 — C.T.R.NADEF NIRMAN SETLIGHT SCHOOL KE PASS GHANA{GHANAGHAT} GP GHANA | Ongoing | 121234.96 | 570 | 2021-09-16
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732001086/RS/22012034531627 — C.T.R.NADEF NIRMAN GHANA MATAMADIR KE PASS GHANA GP GHANA | Closed | 0 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001086/RS/22012034531631 — C.T.R. SOKTA GADDA SARVJANIK STHAL GHANA GP GHANA | Completed | 91916.92 | 62725 | 2021-07-15 | 2025-01-22
SEONI MALWA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001086/RS/22012034531636 — C.T.R. SOKTA GADDA SARVJANIK STHAL JBANDARKHO GP GHANA | Ongoing | 91916.92 | 39001 | 2025-02-03
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732001086/RS/22012034531638 — C.T.R. SOKTA GADDA SARVJANIK STHAL JBANDARKHO GP GHANA | Closed | 91916.92 | 0 | 2021-04-01
SEONI MALWA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Multi Unit Toilets for School / Construction of Multi Unit Toilets for School | Construction of Toilets | 1732001086/RS/22012034642128 — स्वछता परिसर निर्माण कार्य घाना | Completed | 44390 | 46177 | 2022-02-10 | 2023-02-01
SEONI MALWA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732001086/SK/533 — Bharat Nirman Rajeev Gandhi Sewa Kendra,GHANA | Completed | 452000 | 446359.9 | 2013-09-07 | 2020-01-12
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/103 — निर्मलनीर | Deleted | 134178 | 2300 | 2009-01-28
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1732001086/WC/1097 — Kapildhara Koop Anokhilal Shivlal Ghana | Completed | 135959 | 89802.76 | 2012-05-10 | 2014-01-27
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1732001086/WC/1098 — Kapildhara Koop Suresh Chhaganlal Ghana | Completed | 135959 | 55915.93 | 2012-05-10 | 2017-03-30
SEONI MALWA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1732001086/WC/1099 — Kapildhara Koop Buddusingh Sukhlal Ghana | Completed | 135959 | 89313.98 | 2012-04-25 | 2014-01-27
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/163 — क‍ूप निर्माण (कपिल धारा) | Completed | 115987 | 82616.1 | 2009-01-15 | 2009-08-03
SEONI MALWA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Embankment for community / Construction of Embankment for community | Construction of Embankment | 1732001086/WC/22012034606349 — Trench nirman karya ghana se ghana ghat ki or | Closed | 0 | 0 | 2020-12-02
SEONI MALWA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732001086/WC/22012034790094 — C.T.R. NALA UPCHAR KARY NIRMAN GHANA GP GHANA | Completed | 40034.23 | 30108 | 2021-07-16 | 2025-05-16
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/22012034953273 — CTR STRENCH NIRNAM KARY ROAD SE ASHOK KE KHET KI OR GHANA | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/22012034953278 — CTR STRENCH KARY SHIVPRASAD KE KHET SE SHANTIDHAM KI OR GHANA | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1732001086/WC/22012034953281 — CTR STRENCH KARY RAOD SE RAMDAS KE KHET KI OR GHANA | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1732001086/WC/22012034953285 — CTR KARY WORK RAMDAS KE KHET KE AAGE SE NADI KI OR GHANA | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732001086/WC/22012034989717 — vraksha ropen kary hanuman road se shantidham ki or ghanaghat tola gp ghana | Completed | 409718.19 | 147627.59 | 2022-08-25 | 2026-05-28
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1732001086/WC/22012035019627 — khet sadak midial schoo se gangiya road bandarkho gp ghana | Closed | 0 | 0 | 2022-04-14
SEONI MALWA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/22012035021051 — pani nikasi kachi nali nirman kary school se gangiya marg ki or bandarkho gp ghana | Closed | 49124.06 | 0 | 2022-04-14
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/251 — कुपनिर्माण(कपिलधारा) बाबूलाल/कन्‍नी घाना | Completed | 115986 | 94797.2 | 2009-03-01 | 2010-01-07
SEONI MALWA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/252 — कुपनिर्माण(कपिलधारा)नंदलाल /सुखराम घाना | Completed | 115904 | 62601.1 | 2009-03-01 | 2009-07-23
SEONI MALWA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/289 — Kapil Dara (Sulochana / Shivkumar) Badarkhoo(Ghana) | Completed | 79924 | 100167 | 2009-05-26 | 2010-02-10
SEONI MALWA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/320 — Kapildhra kupnirman radhuraj s/o mishrilal badarkho dhana | Completed | 115900 | 115520.93 | 2010-02-17 | 2010-11-07
SEONI MALWA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732001086/WC/345 — Sumer singh s/o Ramgopal kapildara koop nirman badarkhown(ghana) | Completed | 115900 | 84851 | 2010-05-11 | 2011-06-18
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/929 — Nirmalvatika Madanlal Atmaram Ghana | Completed | 2710 | 1816 | 2011-05-29 | 2012-06-17
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/930 — Nirmalvatika Premsingh Mangilal Ghana | Completed | 2710 | 1816 | 2011-05-29 | 2012-06-17
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/931 — Nirmalvatika Rambhau Kallu Ghana | Completed | 2710 | 1816 | 2011-05-29 | 2012-06-15
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/932 — Nirmalvatika Ramsingh Kunjilal Ghana | Completed | 2710 | 1816 | 2011-05-29 | 2012-06-15
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/933 — Nirmalvatika Uttamsingh Ramcharan Ghana | Completed | 2710 | 1882 | 2011-05-29 | 2012-06-13
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/934 — Nirmalvatika Satyanarayan Banshilal Ghana | Completed | 2710 | 1948 | 2011-05-29 | 2012-06-13
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/935 — Nirmalvatika Sukhram Bukhariya Ghana | Completed | 2710 | 2073 | 2011-05-29 | 2012-06-11
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/936 — Nirmalvatika Balram Mishrilal Ghana | Completed | 2710 | 1941 | 2011-05-29 | 2012-06-18
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/937 — Nirmalvatika Mangalsingh Kaliram Ghana | Completed | 2710 | 2073 | 2011-05-29 | 2012-06-11
SEONI MALWA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732001086/WC/938 — Nirmalvatika Ramnarayan Durpal Ghana | Completed | 2710 | 1941 | 2011-05-29 | 2012-06-19