## Work List
Exported on: 2026-09-04 16:48:40
Filters applied:
Data source: MGNREGA
District: NARMADAPURAM
Block: All
Panchayat: NITAYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034466908 — NITAYA P.S. ME BAUNDRIWALL NIRMAN | Completed | 25251 | 25344 | 2019-07-17 | 2019-09-18
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034467478 — P.S. SCHOOL BHAVAN ME BAUNDRIWALL NIRMAN | Completed | 31245 | 30800 | 2019-08-10 | 2019-09-28
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair and maintenance of GP building / Repair and Maintenance of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1732003011/AV/22012034470367 — NITAYA PS SCHOOL CHANDRAPURA ATIRIKT KAKSH ME CHAT FARSH NIRMAN | Completed | 7639 | 7392 | 2019-10-19 | 2019-11-26
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034503302 — Bondry wall with Gate प्राथमिक शाला चंद्रपुरा में 30 मीटर | Completed | 19590 | 19536 | 2019-11-10 | 2020-03-09
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1732003011/AV/22012034503307 — p.s bhavan me farsh nimaran chatt kary | Completed | 7539 | 7392 | 2019-11-10 | 2020-03-09
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1732003011/AV/22012034503309 — nitaya aganbadi bhavan ki chatt pr rcc nirman karya | Completed | 5024 | 4928 | 2019-11-09 | 2019-12-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034505080 — boundarywall nriman panachayat bhawan nitaya | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034505497 — Bajrang mandir ke pas boundryball nirman kary | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732003011/AV/22012034505500 — Boundryball niman karya aanganbabi bhavan me | Closed | 0 | 0 | 2019-11-14
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732003011/AV/22012034508792 — Shantidham type 1 chandrapura | Closed | 0 | 0 | 2020-01-26
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034508975 — boundriwall nirman panchayat bhavan nitaya | Closed | 51821 | 0 | 2019-11-14
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034508976 — Nitaya boundarywall nirman aaganwadi bhawan | Physically Completed | 15388 | 176 | 2020-03-21 | 2021-02-28
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003011/AV/22012034508977 — boundarywall nirman Panchayat bhawan nitya | Completed | 51821 | 53186 | 2020-03-21 | 2020-09-29
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732003011/DP/22012034541725 — Maa ki bagiya GMS Nitaya | Closed | 0 | 0 | 2021-08-15
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1732003011/DP/22012034541726 — Maa ki bagiya GPS Nitaya | Closed | 0 | 0 | 2021-08-15
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732003011/DP/22012034549139 — Gram nitaya me plantation e kaksh ke pass | Closed | 0 | 0 | 2022-01-24
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732003011/DP/22012034549141 — Gram chandrapura me nale ke pass plantation | Closed | 0 | 0 | 2022-01-24
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732003011/DP/22012034549142 — Gram chandrapura me nale ke pass plantation | Closed | 0 | 0 | 2022-01-24
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732003011/DP/22012034549143 — Gram chandrapura me nale ke pass plantation | Closed | 0 | 0 | 2022-01-24
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1732003011/DP/22012034549144 — gram tarondadhana me plantation mangal bhavan ke pass | Closed | 0 | 0 | 2022-01-24
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003011/DP/22012034563896 — CTR-Plantation managl bhawan ke pass taronddhana | Ongoing | 409718.19 | 112856 | 2022-08-26
HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1732003011/DP/22012034588294 — vasudha vandan-amrit vatika nitaya Bhero baba ke pass | Completed | 55847.4 | 27801 | 2023-09-29 | 2026-04-08
HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1732003011/DP/22012034618736 — plantation panchayat campus nitaya | Approved | 0 | 0 | 2024-04-14
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1732003011/FP/22012034365191 — harishankar ke ghar ke pass se nale tak jal bharav nikashi hetu kachhi nali nirman | Completed | 57358.96 | 45600 | 2020-06-06 | 2020-09-04
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Works for Flood Control and Protection | 1732003011/FP/22012034365192 — lokendar ke ghar se girls hostel ki aurharishankar ke ghar ke pass se nale tak jal bharav nikashi | Completed | 49307.68 | 42180 | 2020-05-23 | 2020-07-11
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Diversion Storm Water Drain for Comm / Construction of Diversion Storm Water Drain for Community | Works for Flood Control and Protection | 1732003011/FP/22012034368361 — Drain nirrman vandan thakur ke ghar se ravi ke ghar ke pass nitaya | Completed | 49807.68 | 41015 | 2020-12-26 | 2021-09-13
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732003011/FP/22012034624903 — CTR - shantidam se beniparsad ke khet ki aur kacchi nali nriman | Completed | 40756.13 | 38214 | 2021-05-23 | 2021-09-13
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732003011/FP/22012034624904 — CTR- four road se gram ki aur kacchi nali nirman | Completed | 44681.74 | 34740 | 2021-05-23 | 2021-10-14
HOSHANGABAD | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003011/IF/1000010792 — Nitaya Kapil Dhara Koop Krishna Bai/Kanhiyalal | Completed | 120711 | 16056 | 2013-05-18 | 2015-03-22
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034348902 — GP NITAYA ROAD SIDE PLANTAION | Completed | 335000 | 221466 | 2017-06-17 | 2022-04-18
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034349673 — GP NITAYA SARVAJANIC PARISER | Deleted | 335000 | 0 | 2017-06-13
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034350072 — GP NITAYA PLANTATION PUBLIC PLACE | Completed | 335000 | 249728 | 2017-06-17 | 2021-12-29
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034350094 — NITAYA ME NEHAR KINARE PLANTATION | Completed | 300000 | 235007 | 2017-06-17 | 2022-04-18
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034351321 — GP NITAYA GOVIND RAM NEHAR KINARE PLANTATION RINJA VALI PULIYA NEHAR KINARE | Completed | 335000 | 12690 | 2017-06-17 | 2021-01-04
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034351326 — GP NITAYA FULCHAND NEHAR KINARE BANS PLANTATION NIMSADIYA ROAD NDI KINARE | Completed | 335000 | 11794 | 2017-06-17 | 2021-01-04
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034351329 — GP NITAYA JITENDRA NEHAR KINARE PLANTATION NALE KINARE | Completed | 335000 | 9880 | 2017-06-17 | 2021-01-04
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034351333 — GP NITAYA ARUN KUMAR NEHAR KINARE BANS PLANTATION NITAY SE CHANDRAPURA NEHAR SIDE | Completed | 335000 | 13218 | 2017-06-22 | 2021-01-04
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034351338 — GP NITAYA DEVENDRA BANS PLANTATION NEHAR SIDE NITAYA SE CHANDRAPURA VALI NEHAR | Completed | 335000 | 11282 | 2017-06-17 | 2021-01-04
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003011/IF/22012034351878 — GP NITAYA JAMNA PRASAD KE KHET KI MED PE | Closed | 187600 | 0 | 2017-06-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003011/IF/22012034379370 — GP NITAYARAJENDRA KE KHET KI MED PE PLANTATION 2 | Closed | 187600 | 0 | 2017-04-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003011/IF/22012034379374 — GP NITAYA MEBHAGVATI KE KHET ME PLANTATION KHET KI MED PE | Closed | 187600 | 0 | 2017-04-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003011/IF/22012034393773 — GP NITAYA KE CHANDRAPURA ME MANMOHAN KE KHET ME KI MED PE PLANTATION | Closed | 187600 | 0 | 2017-04-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003011/IF/22012034393775 — GP NITAYA ME NRENDRA KHET KI MED PE PLANTATION | Closed | 187600 | 0 | 2017-04-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012034393784 — GP NITAYA ME MANISH KE KHET KI MED PE PLANTATION | Closed | 187600 | 0 | 2017-04-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003011/IF/22012034393796 — GP NITAYA ME RAMKUMAR KR KHRT KI MED PE PLANTATION | Closed | 187600 | 0 | 2017-04-17
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1732003011/IF/22012034541929 — Nadep Mayaram s/0 shyam ki jamin per | Closed | 0 | 0 | 2020-01-26
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732003011/IF/22012035568144 — PMAYG ASHOK / BHAGIRATH MP116572866 | Completed | 23490 | 23490 | 2025-07-04 | 2025-12-02
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732003011/IF/22012035568186 — PMAYG NANDKISHORE CHOUREY/REWARAM MP 116569038 | Completed | 23490 | 23490 | 2025-07-04 | 2025-12-02
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003011/IF/22012035594107 — Ek Bagiya Maa Ke Naam Radha Bai | Closed | 159032.95 | 261 | 2025-11-07
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003011/IF/9993667369 — निटाया पशु शेड निर्माण गरीबदास चौरे | Completed | 123000 | 122937 | 2015-06-19 | 2016-01-20
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003011/IF/9993668235 — निटाया पशुशेड निर्माण ब्रजेश/भूरेलाल | Deleted | 123000 | 0 | 2015-06-27
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003011/IF/9993668272 — निटाया पशुशेड निर्माण महेश/इमरतलाल | Completed | 123000 | 122937 | 2015-06-19 | 2016-01-20
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993678503 — NITAYA MEDBANDHAN CHIRONGILAL/MENGHULAL | Completed | 52200 | 51039 | 2015-10-10 | 2016-01-20
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993678511 — NITAYA MED BANDHAN KUBJABAI/HARLAL | Completed | 52200 | 52629 | 2015-10-10 | 2016-01-20
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993678516 — NITAYA MEDBANDHAN SAGARBAI/CHOTELAL | Completed | 52200 | 51039 | 2015-10-10 | 2016-01-20
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993679788 — NITAYA MED BANDHAN MANMOHAN/SEETARAM | Completed | 48888 | 46905 | 2015-10-10 | 2016-01-22
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993680396 — NITAYA MEDBANDHAN RATIRAM/GULABDAS | Completed | 48888 | 9540 | 2015-10-17 | 2016-01-22
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993680635 — NITAYA MED BANDHAN CHAUAA/NATHU | Completed | 48888 | 40863 | 2015-10-17 | 2016-01-20
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003011/IF/9993688860 — NITAYA MEDBANDHAN CHAGANLAL/BHURELAL | Completed | 48888 | 43248 | 2015-11-21 | 2016-01-22
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1156219 — Construction of IAY House -IAY REG. NO. MP3164643 | Completed | 15480 | 15480 | 2017-06-17 | 2018-04-05
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1165067 — Construction of IAY House -IAY REG. NO. MP1739130 | Completed | 15480 | 15480 | 2017-06-17 | 2018-04-05
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1166052 — Construction of IAY House -IAY REG. NO. MP3153872 | Completed | 15480 | 15480 | 2017-06-17 | 2018-02-18
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1206739 — Construction of IAY House -IAY REG. NO. MP1822067 | Completed | 15480 | 15486 | 2018-05-05 | 2018-09-19
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1210368 — Construction of IAY House -IAY REG. NO. MP1739358 | Completed | 15480 | 15486 | 2018-05-05 | 2018-09-19
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1307296 — Construction of IAY House -IAY REG. NO. MP3150968 | Completed | 15480 | 15660 | 2018-05-26 | 2018-09-20
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1345808 — Construction of IAY House -IAY REG. NO. MP3657937 | Completed | 15480 | 15706 | 2018-06-09 | 2019-11-26
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1880027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4330977 | Completed | 15660 | 15660 | 2018-09-08 | 2019-01-06
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1881573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5267215 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-01
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1881663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5353999 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-01
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1882055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5337306 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-13
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1883773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5375590 | Completed | 15660 | 15660 | 2018-09-08 | 2019-01-06
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1884131 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5266921 | Completed | 15660 | 15660 | 2018-09-10 | 2018-12-13
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1889302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5279995 | Completed | 15660 | 15660 | 2018-09-08 | 2019-01-06
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1889333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5297078 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-13
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1889802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5295392 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-01
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1907788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5346718 | Completed | 15660 | 15660 | 2018-09-08 | 2019-01-06
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1907789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5348313 | Completed | 15660 | 15312 | 2018-09-08 | 2019-03-14
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1911251 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5297065 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-13
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1926203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4358753 | Completed | 15660 | 15660 | 2018-09-08 | 2018-12-19
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1926508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5279951 | Completed | 15660 | 15660 | 2018-09-08 | 2019-02-04
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/1926531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5356919 | Completed | 15660 | 15660 | 2018-09-08 | 2019-03-14
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/229855 — Construction of IAY House -IAY REG. NO. MP1302772 | Completed | 15030 | 15120 | 2017-01-28 | 2018-04-05
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/230247 — Construction of IAY House -IAY REG. NO. MP1309573 | Completed | 15030 | 15090 | 2017-01-28 | 2018-04-05
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/247584 — Construction of IAY House -IAY REG. NO. MP1774584 | Completed | 15030 | 15090 | 2017-01-28 | 2018-02-18
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/263220 — Construction of IAY House -IAY REG. NO. MP3065948 | Completed | 15030 | 15090 | 2017-01-28 | 2018-04-05
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/263445 — Construction of IAY House -IAY REG. NO. MP3164429 | Completed | 15030 | 14746 | 2017-01-28 | 2018-02-18
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/263446 — Construction of IAY House -IAY REG. NO. MP3164605 | Completed | 15030 | 14966 | 2017-01-28 | 2018-08-19
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/273750 — Construction of IAY House -IAY REG. NO. MP3101180 | Completed | 15030 | 15110 | 2017-01-28 | 2018-02-18
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3707603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103452663 | Completed | 18360 | 18156 | 2022-05-27 | 2022-12-17
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3742100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118145669 | Completed | 18360 | 17952 | 2022-05-27 | 2022-12-17
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3893441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148951093 | Completed | 18360 | 18156 | 2022-05-27 | 2023-01-04
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3893522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148966289 | Completed | 18360 | 18156 | 2022-05-27 | 2022-12-17
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3898467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149338731 | Completed | 18360 | 18360 | 2022-05-27 | 2022-12-17
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3912385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150863238 | Completed | 18360 | 17748 | 2022-05-27 | 2022-12-22
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3913207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150987384 | Completed | 18360 | 16932 | 2022-05-27 | 2023-05-04
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/3913294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151019925 | Completed | 18360 | 17952 | 2022-05-27 | 2022-12-22
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4339459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105330458 | Completed | 18360 | 18156 | 2022-09-23 | 2022-12-22
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4539029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105531089 | Completed | 21870 | 21870 | 2024-10-25 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4542073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105332232 | Completed | 21870 | 21870 | 2024-11-08 | 2025-03-18
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4580198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118143974 | Completed | 21870 | 21870 | 2024-10-11 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4660192 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148908611 | Completed | 21870 | 21870 | 2024-10-25 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4664276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150066894 | Completed | 23490 | 18351 | 2024-10-25 | 2026-05-26
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4986577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103711144 | Completed | 23490 | 23310 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4986582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103715889 | Completed | 23490 | 23382 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/4986592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103737629 | Completed | 23490 | 23310 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5002872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118113259 | Completed | 23490 | 23490 | 2025-05-23 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5002896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118119875 | Completed | 23490 | 23382 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5003281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116086631 | Completed | 23490 | 21555 | 2025-03-21 | 2026-05-26
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5004825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118158312 | Completed | 23490 | 23382 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5004835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118162268 | Completed | 23490 | 23382 | 2025-03-21 | 2026-04-09
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5104286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149331545 | Completed | 23490 | 23310 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5108158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151226468 | Completed | 23490 | 23310 | 2025-03-21 | 2025-12-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5248110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151126524 | Completed | 23490 | 23490 | 2025-06-20 | 2025-12-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5251906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116561625 | Completed | 23490 | 23490 | 2025-04-11 | 2025-12-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5458569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116579862 | Completed | 23490 | 23490 | 2025-05-09 | 2025-12-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5458881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116106621 | Completed | 23490 | 21924 | 2025-06-27 | 2026-05-26
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5460395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151129888 | Completed | 23490 | 23490 | 2025-06-06 | 2025-12-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5461814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116098657 | Completed | 23490 | 23490 | 2025-05-23 | 2025-12-24
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/585195 — Construction of IAY House -IAY REG. NO. MP1739103 | Completed | 15030 | 15120 | 2017-02-18 | 2018-04-05
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5903319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116103234 | Ongoing | 23490 | 12267 | 2026-04-23
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5903405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118158389 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5905138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118120489 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5908779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116579627 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5910933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102381785 | Ongoing | 23490 | 12789 | 2026-04-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5913259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103733174 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5917748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116571804 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5921955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116579671 | Ongoing | 23490 | 16443 | 2026-04-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5923141 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118120714 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5926911 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118736854 | Ongoing | 23490 | 5481 | 2026-05-29
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5928064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103715165 | Ongoing | 23490 | 12789 | 2026-05-16
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/5931723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118158637 | Approved | 23490 | 0 | 2026-01-19
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/877114 — Construction of IAY House -IAY REG. NO. MP1824424 | Completed | 15480 | 15480 | 2017-05-20 | 2018-02-18
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/950231 — Construction of IAY House -IAY REG. NO. MP3050741 | Completed | 15480 | 15480 | 2017-05-20 | 2018-02-18
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/950272 — Construction of IAY House -IAY REG. NO. MP3051652 | Completed | 17100 | 4002 | 2018-07-21 | 2021-02-21
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/950294 — Construction of IAY House -IAY REG. NO. MP3051976 | Completed | 15480 | 15480 | 2017-05-06 | 2018-04-05
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/950305 — Construction of IAY House -IAY REG. NO. MP3052139 | Completed | 15480 | 15480 | 2017-05-06 | 2018-02-01
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/950307 — Construction of IAY House -IAY REG. NO. MP3052192 | Completed | 15480 | 15480 | 2017-05-06 | 2018-02-18
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/950823 — Construction of IAY House -IAY REG. NO. MP3063941 | Completed | 15480 | 15480 | 2017-05-06 | 2018-04-05
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/951018 — Construction of IAY House -IAY REG. NO. MP3068243 | Completed | 15480 | 15480 | 2017-05-13 | 2018-01-31
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/951864 — Construction of IAY House -IAY REG. NO. MP3091959 | Completed | 15480 | 15480 | 2017-05-06 | 2018-04-05
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/952040 — Construction of IAY House -IAY REG. NO. MP3096477 | Completed | 15480 | 15480 | 2017-05-20 | 2018-04-05
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/952442 — Construction of IAY House -IAY REG. NO. MP3106836 | Completed | 15480 | 15480 | 2017-05-20 | 2018-01-31
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/954281 — Construction of IAY House -IAY REG. NO. MP3153921 | Completed | 15480 | 15480 | 2017-05-06 | 2018-01-31
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003011/IF/IAY/954307 — Construction of IAY House -IAY REG. NO. MP3154634 | Completed | 15480 | 15308 | 2017-05-06 | 2018-02-18
HOSHANGABAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003011/LD/22012034295444 — निटाया में शातिधाम निर्माण | Completed | 180000 | 177996.48 | 2016-12-24 | 2018-12-03
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003011/LD/22012034585807 — land deveopment campus school | Completed | 24076.55 | 17297 | 2022-12-30 | 2024-01-17
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003011/LD/22012034585808 — land deveopment campus school | Closed | 0 | 0 | 2022-08-15
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003011/LD/22012034587238 — land deveopment campus e-kash,aganwadi bhawan | Closed | 0 | 0 | 2022-08-15
HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003011/LD/22012034600255 — land levelling PB campus | Completed | 92849.25 | 53078 | 2024-03-08 | 2025-03-01
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1732003011/PG/9425893163 — निटाया खेल मैदान निर्माण | Closed | 0 | 0 | 2017-04-14
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034168998 — निटाया चंदपुरा रघुनंदन के घर से कामता के खेत की ओर | Completed | 64095 | 64098 | 2013-06-01 | 2014-03-31
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034172441 — निटाया चंदपुरा रतिराम के घर सामने से सी०सी० रोड व | Completed | 39813 | 26760 | 2013-06-22 | 2014-01-28
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034173133 — निटाया चंदपुरा पा०शा० भवन से मदन के घर तक सी०सी० र | Completed | 34760 | 25063 | 2013-06-29 | 2014-01-28
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034200683 — निटाया वीधायक निधि आश्रम नाले के पास से बाबा के पी | Completed | 31725 | 31635 | 2014-01-25 | 2014-09-04
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034200689 — निटाया रामभरोस के घर के आगे से शंकरलाल के खलियान त | Completed | 12560 | 12551.99 | 2014-01-25 | 2014-07-05
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034202031 — निटाया वीधायक निधि ब्‍यावरा रोड से गांव तरफ पीछे क | Completed | 31387 | 31389 | 2014-02-01 | 2014-09-04
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034203550 — निटाया राजेश के घर से मंगलसिंह के घर तक सी.सी. रोड | Completed | 40232 | 39452 | 2014-02-08 | 2014-07-05
HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034227837 — निटाया पंच पर. वीधायक निधि रोड से आगे बिहारीदास के | Completed | 79292 | 78600 | 2014-08-23 | 2015-03-22
HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034227839 — निटाया मुख्‍य मार्ग से ग्‍यारसी बार्इ के घर तक सी. | Completed | 106488 | 85803 | 2014-08-23 | 2015-03-22
HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732003011/RC/22012034294790 — निटाया ग्रेवल रोड निर्माण निटाया पांजरा मार्ग राजेन्‍द्र सिंह के खेत तक | Completed | 1418699 | 135271 | 2016-01-02 | 2018-09-25
HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034294795 — निटाया पंच पर. स्‍वराज भवन से अांगनवाडी भवन तक सी.सी. रोड निर्माण | Completed | 35658 | 31323 | 2016-01-02 | 2016-08-30
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034310697 — निटाया कन्‍छेदी यादव के घ्‍र के सामने सी.सी. रोड नाली निर्माण | Completed | 4082 | 3841 | 2016-04-09 | 2016-08-30
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034310704 — निटाया गिरधर चौधरी के घ्‍र से संतोष चौधरी के घ्‍र तक सी.सी. रोड व नाली निर्माण | Completed | 9273 | 9018 | 2016-04-09 | 2016-08-30
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034310725 — निटाया भांगिया बाा के चारो तरफ सी.सी. रोड एवं नाली निर्माण | Completed | 15923 | 15865 | 2016-04-09 | 2016-08-27
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034337401 — NITAYA CHANDRAPURA ME RAGHUNANDAN KE GHAR SE KOTWAR VALE KHET TK CC ROAD & NALI NIRMAN | Completed | 74081 | 63812 | 2017-05-13 | 2018-07-25
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034341440 — निटाया ग्‍यारसीबाई के घर से हेण्‍डपंप तक सी सी रोड व नाली निर्माण | Completed | 98775 | 77400 | 2017-06-17 | 2018-07-25
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034375543 — NITAYA BHARU BABA SE HEND PUMP TAK C.C. ROAD NIRMAN | Closed | 0 | 0 | 2017-10-02
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034380227 — NITAYA MATA MANDIR SE KUNWA TAK C.C. ROAD & NALI NIRMAN | Deleted | 52587 | 0 | 2016-10-02
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034381006 — NITAYA SANSAD NIDHI CHANDRAPURA PANCH PARMESHWAR ROAD SE AGE NIMSADIYA MARG TAK C.C. ROAD NIRMAN | Completed | 62644 | 62323 | 2018-01-10 | 2018-10-20
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034439329 — cc road | Closed | 0 | 0 | 2019-04-01
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034439330 — cc road | Closed | 0 | 0 | 2019-04-01
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034439975 — cc road | Closed | 0 | 0 | 2019-04-01
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034448118 — NITAYA OMPRAKASH KE GHAR SE MATA MANDIR TAK C.C. ROAD & EAK AUR NALI NIRMAN | Completed | 42387 | 41832 | 2019-03-05 | 2019-09-17
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034449135 — NITAYA (SANSAD NIDHI) PW ROAD LS GRAM KI AUR C.C. ROAD C.C. ROAD NIRMAN | Completed | 22100 | 22044 | 2019-03-05 | 2019-05-09
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034449139 — NITAYA (PAR. ZP) GAYAPRASAD PATEL KE GHAR SE KAMAL YADAV KE GHAR KI AUR C.C. ROAD NIRMAN | Completed | 30100 | 30372 | 2019-03-05 | 2019-05-09
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034468594 — NITAYA P.S. SCHOOL KE PASS SE NEELESH KE GHAR TAK C.C. ROAD NIRMAN | Completed | 11400 | 15840 | 2019-07-06 | 2019-09-04
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034510066 — cc road managal ke ghar se chaggan ke ghar tak | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034511406 — Mata mandir se cheenda tk cc road nirman | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034511407 — Mukesh ke ghar se kuaa tk cc road nirman | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003011/RC/22012034511410 — kamal ke ghar se meghraj ke ghar tk cc road niirman kary | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003011/RC/22012034511411 — puneet ke ghar se ps tk cc road nirman karya | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003011/RC/22012034511412 — Dharamshala se khile tk cc road nirman karya | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003011/RC/22012034511413 — lala ke ghar se bhagatji ke ghar tk cc road repairing karya | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003011/RC/22012034511414 — bbhangiya baba ke pas cc road karya | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034511419 — cc road &nali nirman karya kunjilala ke ghar se raja ke ghar ki taraf | Completed | 22323 | 23408 | 2020-01-04 | 2020-03-09
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034553925 — NITAYA PS SCHOOL SE BAMULA VALE BABA TAK C C ROAD (RINUVAL COTE) & NALI NIRMAN | Physically Completed | 45184 | 2280 | 2021-03-05 | 2026-04-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034586084 — NITAYA RISHI KE GHAR SE HEND PUMP K AUR C C ROAD NIRMAN | Completed | 18119 | 16212 | 2021-10-01 | 2021-12-15
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034587424 — NITAYA MANGAL KE GHAR SE CHAGAN KE GHAR TAK C C ROAD & NALI NIRMAN | Physically Completed | 27647 | 4902 | 2021-11-26 | 2026-04-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034607543 — shukhnandan ke ghar se deepak ke ghar tak cc road or nali nirmann kary | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034607544 — Rambharosh ke ghar se kunaa tk cc road or nali nirman kary | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034607545 — Rambharosh ke ghar se kunaa tk cc road or nali nirman kary | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034607546 — MATA MANDIR SE RAJA KE GHAR TAK CC ROAD OR NALI NIRMANN KARY | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034646025 — श्री मंगल के घर से फोरलेन की ओर सीमेंट सड़क निर्माण | Closed | 37600 | 0 | 2023-09-29
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034646031 — Paver block kary middle school | Completed | 8500 | 8398 | 2023-10-06 | 2024-01-17
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034662300 — NITAYA MATA MANDIR SE GIRDHAR PATEL KE MAKAN KI AUR C C ROAD NALI NIRMAN | Completed | 23058 | 22542 | 2023-10-06 | 2024-01-17
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034662304 — NITAYA SHREE MANGAL KE GHAR SE FOURLEN KI AUR C C ROAD NIRMAN | Completed | 37600 | 37570 | 2023-10-06 | 2024-01-16
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034670601 — NITAYA PANCHAYAT BHAVAN PARISAR SE MUKHYA SADAK TAK C C ROAD | Completed | 12665 | 12340 | 2024-01-05 | 2024-02-05
HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034823928 — cc road purshotam patel ke ghar se giridhar patel ke ghar ki aur nitaya | Completed | 42300 | 41310 | 2024-08-22 | 2024-11-15
HOSHANGABAD | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034843703 — cc road sunderlal patel ke ghar se koop ki oar | Completed | 10500 | 9135 | 2025-06-06 | 2026-04-08
HOSHANGABAD | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/22012034843705 — cc road pitu ke ghar se fourlane ki oar | Completed | 20900 | 20358 | 2025-07-18 | 2026-04-08
HOSHANGABAD | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003011/RC/43 — निटाया (पंच परमेश्‍वर) कुब्‍जाबाई के मकान से खूटिया बाबा की ओर सी.सी. रोड निर्माण | Completed | 78013 | 39502 | 2012-03-25 | 2012-07-23
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Compost Pit / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034309962 — निटाया ४ सार्व‍जनिक नाडेप निर्माण | Completed | 37540 | 36642 | 2016-12-08 | 2017-10-25
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034330023 — NITAYA TIOLET ROHANI/DHRUV KUMAR | Completed | 12000 | 11847 | 2017-03-18 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034332875 — NITAYA TOILET GOPENDRA /RADHACHARAN | Completed | 12000 | 11847 | 2017-03-18 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334137 — NITAYA Toilet Mishrabai/babulal | Completed | 12000 | 11847 | 2017-03-25 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334175 — NITAYA Toilet Radheshyam/Garibdas | Completed | 12000 | 11847 | 2017-03-25 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334204 — NITAYA TOILET SIYASARAN SARATHE | Completed | 12000 | 11847 | 2017-03-25 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334208 — NITAYA TOILET RAMVILAS/ IMRATLAL CHANDRAPURA | Completed | 12000 | 11877 | 2017-03-25 | 2018-08-05
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334722 — NITAYA Toilet JUGALKISHORE/CHAMPALAL | Completed | 12000 | 11937 | 2017-05-27 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334747 — NITAYA Toilet Chandramohan/Rabuda chandrpura | Completed | 12000 | 11877 | 2017-03-25 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334749 — NITAYA Toilet JAYNARAYAN/GANGARAM chandrapura | Completed | 12000 | 11847 | 2017-03-25 | 2017-10-12
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034334854 — NITAYA Toilet Jagdish/ramdayal chandrapura | Completed | 12000 | 11937 | 2017-04-29 | 2017-10-12
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034336869 — NITAYA Toilet Sharad Kumar /Jagdish | Completed | 12000 | 11937 | 2017-04-08 | 2017-10-12
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034336888 — NITAYA Toilet Arun/Chotelal patel | Completed | 12000 | 11937 | 2017-04-08 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003011/RS/22012034337122 — NITAYA Toilet Heeralal/ramprasad chandrapura | Deleted | 12000 | 0 | 2017-02-28
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440500 — NADEP NIRMAN BAJRANG MANDIR KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440501 — NADEP NIRMAN SHANKAR MANDIR KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440502 — NADEP NIRMAN MATA MANDIR, NAVEEN MANGAL BHAWAN KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440503 — NADEP NIRMAN YOGENDRA KE GHAR KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440504 — NADEP NIRMAN PANCHAYAT BHAWAN KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440505 — NADEP NIRMAN KASTURBA AADARSH BALIKA ASHRAM GATE KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440506 — NADEP NIRMAN SURESH KAHAR KE GHAR KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034440508 — NADEP NIRMANMANGAL SINGH KE GHAR KE PAAS | Closed | 0 | 0 | 2019-01-26
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034478926 — Nitaya me nadep nirman karya panchayat ke pass | Completed | 22082.26 | 19095 | 2020-02-22 | 2020-12-05
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034478927 — Nitaya me nadep nirman karya hanuman mandir ke pass | Completed | 22082.26 | 19226 | 2020-03-21 | 2021-04-22
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034478928 — Nitaya me nadep nirman karya bhero baba ke pass | Completed | 22082.26 | 7398 | 2020-03-20 | 2022-04-18
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & Maint of NADEP Compost for Community / Repair and Maintenance of NADEP Compost structure for Community | Repaire and Maint of NADEP/Vermi Compost Pit | 1732003011/RS/22012034478929 — Tarondadhana me nadep Norman karya Mangal bhavan ke pass | Completed | 22082.26 | 19248 | 2020-02-22 | 2021-04-22
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034478930 — tarondadhana me nadep nirman karya chotelal ke ghar ke pass | Completed | 22082.26 | 19150 | 2020-02-22 | 2021-04-22
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732003011/RS/22012034510300 — Samudayik swachhata parisar nriman e-kash ke pass nitaya | Completed | 72833 | 43590 | 2021-03-05 | 2022-05-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034621819 — Nitaya - Samudayik Nadep - D.P. ke pass | Completed | 4239 | 3474 | 2021-11-26 | 2022-01-15
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034621851 — gram tarondadhana nadep nirman puliya ke pass | Closed | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034621852 — gram tarondadhana nadep nirman puliya ke pass | Completed | 4239 | 3474 | 2021-11-26 | 2022-01-15
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034621856 — gra nitaya nadep nirman aashram ke pass | Completed | 4239 | 3474 | 2021-11-26 | 2022-01-15
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034643728 — nadep nirman nale ke pass | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034643730 — nadep nirman nale ke pass | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034643738 — nadep nirman main road side | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003011/RS/22012034643747 — nadep nirmann kary school ke pass | Closed | 0 | 0 | 2021-10-02
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003011/RS/22012034685413 — CTR-rcc nali nirman rammohan ke ghar se CSC ki aur | Completed | 4138 | 3867.5 | 2023-06-09 | 2023-06-27
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003011/RS/22012034685415 — CTR-rcc nali nirman babuji patel ke ghar se puliya ki aur | Completed | 18244 | 18011.5 | 2023-06-09 | 2023-07-21
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003011/SK/1066 — Bharat Nirman Rajeev Gandhi Sewa Kendra,NITAYA | Completed | 120193 | 118789 | 2013-09-28 | 2016-04-05
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003011/WC/22012034521025 — Rain water harvesting panchayat bhavan nitaya | Completed | 31352.13 | 28478 | 2020-03-18 | 2020-12-05
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003011/WC/22012034521026 — gp nitaya rain water harvesting in e kaksh | Completed | 31352.13 | 28516 | 2020-02-15 | 2020-12-05
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003011/WC/22012034521027 — gp nitaya rain water harvesting in aaganbadi bhavan | Closed | 13427.24 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003011/WC/22012034521028 — rain water harvesting in PS school gp nitaya | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003011/WC/22012034521029 — gp nitaya rain water harvesting in Mangal bhavan | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003011/WC/22012034521032 — gp nitaya rain water harvesting in PS school chandrapura | Closed | 0 | 0 | 2019-10-02
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003011/WC/22012034551511 — recharge pit managal bhawan ke pass taronddhana | Closed | 14283.77 | 0 | 2020-05-01
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003011/WC/22012034551512 — recharge pit bhairav baba ke nitaya pass | Completed | 14283.77 | 9690 | 2020-06-06 | 2022-03-12
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003011/WC/22012034691709 — CTR-recharge pit handpump ke pass mangal bhawan taronddhana nitaya | Completed | 14467.3 | 4014 | 2021-11-26 | 2023-06-04
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003011/WC/22012034691713 — CTR-recharge pit primary school nitaya | Closed | 14467.3 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012034878435 — puliya nirman men get ke pass | Closed | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012034878436 — puliya nirman men get ke pass | Completed | 16125 | 15826 | 2021-11-26 | 2021-12-29
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012034878443 — puliya nirman school ke pass | Completed | 16125 | 15826 | 2021-11-26 | 2022-01-15
HOSHANGABAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012034960606 — CTR-Flood channel for community mangal singh ke ghar se piche se csc ki aur nitaya | Completed | 47680.3 | 30600 | 2022-05-13 | 2024-01-17
HOSHANGABAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012034983600 — CTR- Flood channel for community hanuman ji ke mandir ke pass se bade nale ki aor | Completed | 72039.12 | 58680 | 2022-06-03 | 2025-03-01
HOSHANGABAD | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012034983603 — CTR- Flood channel for community main road se nale ki aor chandrapura | Closed | 53367 | 0 | 2022-04-14
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003011/WC/22012035183947 — CTR-Rcc nali nriman gangabai ke ghar se shivnath ke ghar ki oar | Completed | 22400 | 22047 | 2024-03-08 | 2024-11-15
HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003011/WC/22012035207433 — CTR plantation panchayat campus nitaya | Completed | 453563.17 | 116640 | 2024-07-12 | 2026-05-22
HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003011/WC/22012035280477 — CTR samudayik sok pit nirmaan panchayat bhavan nitaya | Completed | 5274 | 4437 | 2025-04-25 | 2025-07-08
HOSHANGABAD | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Gabions / Construction of Gabion Check Dam for Individuals | Constr of Gabion | 1732003011/WC/25 — निटाया निर्मल नीर | Completed | 210000 | 62276.2 | 2009-01-28 | 2010-03-31