## Work List
Exported on: 2026-09-13 04:15:03
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: MEHRAGAON
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/112264 — Construction of IAY House -IAY REG. NO. MP-32-003-013-001/17 | Approved | 27000 | 0 | 2015-11-09
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/112265 — Construction of IAY House -IAY REG. NO. MP-32-003-013-001/2 | Approved | 27000 | 0 | 2015-11-09
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3652899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118082035 | Approved | 27000 | 0 | 2022-04-20
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3705178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115973708 | Approved | 27000 | 0 | 2022-05-01
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3731531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118077907 | Approved | 27000 | 0 | 2022-04-26
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3736494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118090790 | Approved | 27000 | 0 | 2022-05-01
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3757221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118363390 | Approved | 27000 | 0 | 2022-05-01
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3759030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118367449 | Approved | 27000 | 0 | 2022-05-01
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3840714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117807645 | Ongoing | 27000 | 0 | 2022-06-16
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3840732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117809779 | Approved | 27000 | 0 | 2022-04-26
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/3840736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117810049 | Approved | 27000 | 0 | 2022-05-01
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4024649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147731046 | Approved | 27000 | 0 | 2022-05-07
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4369864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118068012 | Ongoing | 27000 | 0 | 2022-11-10
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4560364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115356830 | Ongoing | 27000 | 0 | 2025-01-23
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4564716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115948152 | Ongoing | 27000 | 0 | 2025-01-09
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4566113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116139695 | Ongoing | 27000 | 0 | 2025-01-09
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4570347 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117306072 | Ongoing | 27000 | 0 | 2024-12-19
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4574334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117432050 | Ongoing | 27000 | 0 | 2025-08-25
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4699799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115814562 | Ongoing | 27000 | 0 | 2024-12-19
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/4861898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116062415 | Completed | 23490 | 0 | 2025-09-05 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5112596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118301389 | Ongoing | 27000 | 0 | 2025-09-09
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5114556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115356809 | Ongoing | 27000 | 0 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5114609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116153568 | Ongoing | 27000 | 0 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5114722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115957402 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5116223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118310641 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5116502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116320958 | Completed | 23490 | 0 | 2025-09-05 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5117203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117458412 | Physically Completed | 23490 | 2100 | 2025-08-21 | 2026-08-16
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5117594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117810981 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5117917 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117458637 | Ongoing | 27000 | 6300 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5118770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118545977 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5118874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117596732 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5120390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117294019 | Ongoing | 27000 | 4200 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5120610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117450754 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5121326 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116141945 | Ongoing | 27000 | 10500 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5121670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116546299 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5121919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117296044 | Ongoing | 27000 | 6300 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5121922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117298942 | Completed | 23490 | 0 | 2025-09-05 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5122744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117799815 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5122896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117814755 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5125158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116327888 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5125416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118558656 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5126419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117304514 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5127193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115958355 | Completed | 23490 | 0 | 2025-04-10 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5127460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116566117 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5128002 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118297042 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5128003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118299027 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5129660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116141086 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5129997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117428216 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5131738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117431076 | Ongoing | 27000 | 0 | 2025-10-30
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5132472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117287926 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5316423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117444487 | Ongoing | 27000 | 8400 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5320069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116555333 | Ongoing | 27000 | 6300 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5458256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118568970 | Ongoing | 27000 | 4200 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5458669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116256561 | Ongoing | 27000 | 5700 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5458717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116134028 | Completed | 23490 | 0 | 2025-08-14 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5459599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117641709 | Ongoing | 27000 | 0 | 2025-10-30
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5460145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118146478 | Completed | 23490 | 0 | 2025-09-18 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5460725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116336342 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5465879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122518875 | Ongoing | 27000 | 4200 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5466166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114860200 | Ongoing | 27000 | 0 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5518648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115978111 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5519913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146241158 | Approved | 27000 | 0 | 2025-03-28
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5521735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117445415 | Ongoing | 27000 | 8400 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5529678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116320872 | Ongoing | 27000 | 14700 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5532053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118112901 | Ongoing | 27000 | 0 | 2025-09-11
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5579434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116329859 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5580300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117426438 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116310809 | Completed | 23490 | 0 | 2025-07-31 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106516949 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116558736 | Completed | 23490 | 0 | 2025-09-08 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116146200 | Ongoing | 27000 | 1500 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116316821 | Ongoing | 27000 | 14700 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117798631 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5600817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118567349 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5620243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116131174 | Ongoing | 27000 | 2100 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5620276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116310374 | Ongoing | 27000 | 14700 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5620318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122516633 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5653246 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117662568 | Ongoing | 27000 | 8400 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5653375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116533038 | Ongoing | 27000 | 1500 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5653607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116150392 | Completed | 23490 | 0 | 2025-08-25 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116548724 | Ongoing | 27000 | 6300 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116152035 | Ongoing | 27000 | 12300 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116541689 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126318108 | Ongoing | 27000 | 0 | 2025-08-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115953368 | Ongoing | 27000 | 1500 | 2025-08-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118075777 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122517696 | Ongoing | 27000 | 7800 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117807756 | Ongoing | 27000 | 0 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043208 | Ongoing | 27000 | 0 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117819089 | Ongoing | 27000 | 0 | 2025-09-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117458306 | Completed | 23490 | 0 | 2025-08-21 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5687859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116324239 | Ongoing | 27000 | 14700 | 2025-08-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5730778 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147290554 | Ongoing | 27000 | 0 | 2025-09-08
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5861426 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116322393 | Approved | 27000 | 0 | 2025-02-25
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5862501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118295804 | Approved | 27000 | 0 | 2025-04-09
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/5862549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116059360 | Ongoing | 27000 | 0 | 2026-05-28
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6073628 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115954190 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6074218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116276678 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6074286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116307240 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6074301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116312203 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6074648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116547524 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6075941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117420516 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6075950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117427003 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6075958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117432942 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6075999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117449601 | Approved | 27000 | 0 | 2026-01-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6129555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116137010 | Approved | 27000 | 0 | 2026-03-11
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6130763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118067924 | Approved | 27000 | 0 | 2026-03-11
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003013/IF/IAY/6173179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115963618 | Approved | 27000 | 0 | 2026-03-11
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034547226 — MEHRAGAON BALRAM MISHRA SE VINOD KE GHAR KI AUR C C ROAD NIRMAN | Ongoing | 24673 | 0 | 2020-11-09
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034596994 — MEHRAGOAN MISHIRLAL KE GHAR SE MONTI KE GHAR KI UAR C C ROAD NIRMAN | Ongoing | 12364 | 0 | 2021-11-16
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034597011 — MEHRAGOAN SHILENDRA BHISARE KE GHAR SE BHATIYA JI KE GHAR KI UAR C C ROAD | Ongoing | 12364 | 0 | 2021-11-16
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665098 — Mehragaon - Gori masab ke ghar se mukesh mehra ke ghar ki or ccroad nirman | Ongoing | 13376 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665109 — Mehragaon - Tiwari ji ke ghar se bourasi ji ke ghar ki or ccroad nirman | Ongoing | 7876 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665118 — Mehragon - Mahesh ji ke ghar se borkar dada ke ghar ki or ccroad nirman | Ongoing | 12003 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665149 — Mehragaon - Aanand pachlaniya ke ghar se taronda medha ki or cc road nirman | Ongoing | 41262 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665157 — Mehragaon - Atish ke makan se nale ki or cc road nirman | Ongoing | 9753 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665173 — Mehragaon - Jitendra sahu ker ghar se pramod nimaniya ke ghar ki or cc road nirman | Ongoing | 11253 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665185 — Mehragaon - Rakesh hanotiya ke ghar se premlal ke ghar ki or cc road nirman | Ongoing | 11147 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003013/RC/22012034665206 — Mehragaon - Premdash choure ke ghar se devisinh ke ghar ki or cc road nirman | Physically Completed | 18762 | 0 | 2023-10-06 | 2026-08-02
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003013/WC/22012035140989 — Mehragaon - Pritam yadav ke ghar se tronda medhe ki or rcc nali nirman | Ongoing | 128347 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003013/WC/22012035141087 — Mehragaon - Ramfal ji ke ghar se madan barsare ke ghar ki or cc nali nirman | Ongoing | 4333 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003013/WC/22012035141106 — Mehragaon - Santosh rohre ke ghar se dolariya road ki or rcc nali nirman | Ongoing | 23176 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003013/WC/22012035141119 — Mehragaon - Yuvne ji ke ghar se kochekar ji ke ghar ki or cc nali nirman | Ongoing | 12225 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003013/WC/22012035141217 — Mehragaon - Bablu mehra ke ghar se rammohan patel ke khale ki or cc nali nirman | Ongoing | 11556 | 0 | 2023-10-06
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003013/WC/22012035141234 — Mehragaon - sanjay yadav ke ghar se banti raikwar ke ghar ki or cc nali nirman | Ongoing | 7222 | 0 | 2023-10-06
HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003013/WC/22012035209353 — लीचपिट निर्माण शासकीय हाईस्‍कूल में हैंडपंप के पास | Approved | 4868 | 0 | 2024-06-08