## Work List
Exported on: 2026-10-21 06:24:31
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: MISROD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
HOSHANGABAD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1732003006/WC/186 — मिसरौद सार्वजनिक कूप निमार्ण निर्मलनीर | Completed | 210000 | 134514.44 | 2009-02-03 | 2011-05-11
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732003048/AV/22012034464745 — Misrod - Play Ground Nirman | Closed | 219315.8 | 0 | 2019-05-26
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003048/AV/22012034466870 — Mishrod - Aanganwadi and panchayat bhavan parisar me Boundrywall Nirman | Completed | 37956 | 37840 | 2019-07-22 | 2019-09-18
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003048/AV/22012034467249 — Mishrod - Upswasthaya kendra bhavan parisar me Boundarywall Nirman | Completed | 59391 | 59136 | 2019-08-12 | 2019-10-19
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003048/AV/22012034470464 — Mishrod - M.S. and P.S. school parisar me Boundary wall nirman | Completed | 68116 | 67584 | 2020-01-20 | 2020-04-01
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003048/AV/22012034470465 — Mishrod - Anganwadi get se prayogshakla bhavan parisar v maidan ki boundary wall nirman | Completed | 224657 | 223872 | 2019-10-14 | 2020-02-08
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732003048/AV/22012034511935 — Men road ke paas aanganwadi parisar me boundriwall nirman | Completed | 4836 | 5130 | 2020-08-24 | 2020-10-12
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of SHG/Fed building for Groups / Construction of SHG/Federation Building for Groups | Construction of building/workshed for SHG | 1732003048/AV/22012034551099 — Mishrod - SHG Sangh Bhavan Nirman | Closed | 0 | 0 | 2020-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1732003048/AV/22012034577835 — Construction of Desk (size - 1.20x0.45m.) Bench (size - 1.20x0.30m.) in Dining Hall - P.S.Mishrod | Closed | 20955.37 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1732003048/AV/22012034577838 — Construction of Desk (size - 1.80x0.45m.) Bench (size - 1.80x0.30m.) in Dining Hall - M.S.Mishrod | Closed | 31116.12 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003048/AV/22012034613370 — Boundarywall Nirman - Hat Bazar parisar me | Completed | 6244 | 5404 | 2022-01-25 | 2022-05-23
HOSHANGABAD | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732003048/AV/22012034632922 — Hai School Parisar me Khel Maidan | Closed | 0 | 0 | 2023-01-26
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732003048/AV/22012034632979 — Misrod-Hai School parisar me khail maidan nirman | Closed | 778850.86 | 0 | 2023-04-01
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732003048/AV/740 — Aanganbadi Bhavan Nirman Sewa Kendra,HOSHANGABAD | Completed | 180000 | 168542 | 2014-02-24 | 2017-09-04
HOSHANGABAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003048/DP/22012034241339 — Mishrod, Plantation of Shantidham parisar and Near of road | Deleted | 335000 | 0 | 2017-05-14
HOSHANGABAD | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003048/DP/22012034241340 — Mishrod, Plantation of Mishrod to dolariya 2 lan road kinare | Deleted | 335000 | 0 | 2017-05-14
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Drought Proofing | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003048/DP/22012034444468 — Chek Dam Nirman Mishrod - Mishrod Temla road, nadi per | Closed | 608434.76 | 0 | 2019-01-26
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1732003048/DP/22012034568929 — MISROD KHEL MAIDAN ME VRAKSHAROPAN KARYA | Ongoing | 407825.29 | 53110 | 2022-09-21
HOSHANGABAD | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1732003048/DP/22012034595280 — Misrod - Vasudha Vandan - Amrit Vatika - higher Secondary School parisar me | Physically Completed | 55847.4 | 18138 | 2023-08-09 | 2026-06-25
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732003048/FP/22012034624582 — CTR - Mishrod - Jhukriya Nala Sudradikaran Kary | Deleted | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Construction of Embankment for community / Construction of Embankment for Community | Construction of Embankment | 1732003048/FP/22012034625396 — Mishrod - Jhukriya Nala Sudradikaran Kary | Ongoing | 929663.72 | 42846 | 2021-06-01
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003048/IF/22012034341711 — MIshrod, PLantation, Mishrod se Dolariya 2 len Road kinare | Completed | 335000 | 232026 | 2017-05-22 | 2022-06-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003048/IF/22012034350022 — PANTION SALA PARISAR MISROD | Completed | 335000 | 173412 | 2017-06-17 | 2022-06-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plntation-Farm Forestry Trees(Individual) / Boundary Line Plantation of Farm Forestry Trees for Individuals | Plantation | 1732003048/IF/22012034351826 — MISROD PLANTION SELA/CHAGANLAL | Closed | 187600 | 0 | 2017-06-17
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732003048/IF/22012034377815 — मिसरोद मेढ बसंत ॰आनद, अजेन्द PLANTION | Closed | 187600 | 0 | 2017-04-14
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003048/IF/22012034379147 — MISROD PLANTION ,HARIOM. MANMOHAN ,SHRI KISHAN | Ongoing | 187600 | 17772 | 2018-06-05
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003048/IF/22012034481433 — Misrod - Farm Pond - Amit gour/Kamlesh gour | Completed | 101865.53 | 75240 | 2020-05-04 | 2023-05-20
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003048/IF/22012034555712 — Misrod - Khet Talab Nirman - Liladhar / Ginnu Yadav | Completed | 41993.55 | 45600 | 2020-05-18 | 2020-07-10
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034555716 — Misrod - Nandan falodhyan - Liladhar / Ginnu yadav | Physically Completed | 137244.99 | 49890 | 2020-10-12 | 2026-06-25
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003048/IF/22012034556448 — Misrod - Khet Talab Nirman - Kamalkishor / Munnalal | Completed | 332572.21 | 137484 | 2020-06-01 | 2026-04-01
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034556449 — Misrod - Nandan falodhyan - Kamalkishor / Munnalal | Completed | 137244.99 | 65506 | 2020-07-13 | 2026-05-28
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034560892 — Misrod - Nandan falodhyan - Amit gour / Kamlesh gour | Completed | 137244.99 | 71968 | 2020-07-13 | 2026-05-10
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034583181 — Misrod - Nandan falodhyan - Hari om gour / shree chanra bhushan | Completed | 137244.99 | 69902 | 2020-07-20 | 2026-05-10
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034583252 — Mishrod - Nandan flodhyan - Rambharosh gour / ramlishan gour | Completed | 137244.99 | 41503 | 2020-07-20 | 2026-05-28
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034583253 — Mishrod - Nandan flodhyan - Surekha gour / sunil gour | Completed | 137244.99 | 88864 | 2020-07-13 | 2026-05-10
HOSHANGABAD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1732003048/IF/22012034603393 — Mishrod Nandanflodhyan - Krishan kumar/Shreekishan | Completed | 116265.03 | 84231 | 2020-08-31 | 2025-05-04
HOSHANGABAD | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003048/IF/22012034718171 — CTR - Misrod - Khet Talab Hari om ke khet me | Deleted | 0 | 0 | 2021-04-14
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/22012035024521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118091006 Babulal Choudhari | Completed | 18360 | 17136 | 2022-11-24 | 2023-04-28
HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732003048/IF/22012035546666 — CTR-JGSA-Jitendra/Narmadaprasad ke kup ke pash recharge Pit | Completed | 17843 | 4437 | 2025-05-26 | 2026-04-28
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732003048/IF/22012035555925 — CTR JGSA Pushpa Bai / Chandra Bhushan Gour ke khet me Khet Talab Nirman | Completed | 55865.38 | 18009 | 2025-06-01 | 2026-04-29
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003048/IF/22012035589570 — Ek Bagiya Ma Ke Naam Savitri bai / Pyarelal gour Misrod | Approved | 0 | 0 | 2025-08-01
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732003048/IF/22012035589589 — Ek Bagiya Ma Ke Naam Sapana / Sachin Gour Misrod | Ongoing | 269386.03 | 1044 | 2025-09-17
HOSHANGABAD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003048/IF/85 — मिसरौद कूप निर्माण नर्मदा प्रसाद / शिवदीन | Completed | 94000 | 80295.62 | 2009-02-05 | 2011-03-31
HOSHANGABAD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1732003048/IF/86 — मिसरौद कूप निर्माण वंसत कुमार / रवशिंकर | Completed | 94000 | 81273.99 | 2009-02-05 | 2011-03-31
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003048/IF/9993666593 — मिसरौद पशुशेड निर्माण सदशिव गौर | Closed | 0 | 0 | 2015-04-14
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003048/IF/9993667257 — मिसरौद पशुशेड निर्माण सदाशिव गौर | Completed | 123000 | 120348.9 | 2015-06-28 | 2017-01-30
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003048/IF/9993667260 — मिसरौद पशुशेड निर्माण मदनमोहन/महेशप्रसाद | Completed | 123000 | 108094 | 2015-06-22 | 2017-01-30
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003048/IF/9993667377 — मिसरौद पशुशेड निर्माण रघुवीरप्रसाद गौर | Deleted | 123000 | 0 | 2015-06-22
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003048/IF/9993667378 — मिसरौद पशुशेड निर्माण राजेश/नर्मदाप्रसाद | Completed | 123000 | 109048 | 2015-06-22 | 2017-01-30
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732003048/IF/9993667380 — मिसरौद पशुशेड निर्माण लख्‍नलाल/बोंदरप्रसाद | Completed | 123000 | 119632 | 2015-06-22 | 2017-01-30
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993678453 — MISROD MEDH BANDHAN ARVIND/CHAGANLAL | Completed | 48888 | 31482 | 2015-10-05 | 2016-08-08
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993678463 — MISROD MEDH BANDHAN RAGHUVEER/MAKDUPRASAD | Completed | 48888 | 15567 | 2015-10-05 | 2016-08-08
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993678475 — MISROD MEDH BANDHAN CHAGAN/NARMADAPRASAD | Completed | 48888 | 13992 | 2015-10-05 | 2016-08-08
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993678477 — MISROD MEDH BANDHAN BHEEMRAJ/RAMNARAYAN | Deleted | 48888 | 0 | 2015-10-05
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993678479 — MISROD MEDH BANDHAN HARISH/JAGDISHPRASAD | Completed | 48888 | 18126 | 2015-10-05 | 2016-08-08
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993678482 — MISROD MEDH BANDHAN DAVKI BAI /MAHESH | Closed | 48888 | 0 | 2015-04-14
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993681471 — मिसरोद मेढ बंधान रामाधार पूनमचंद | Completed | 48888 | 19080 | 2015-10-19 | 2016-08-08
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993681478 — मिसरोद मेढ बंधान दुर्गाप्रसाद शिवदीन | Completed | 48888 | 32913 | 2015-10-26 | 2016-08-08
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993681480 — मिसरोद मेढ बंधान परसराम रामनारायण | Closed | 48888 | 0 | 2015-10-16
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993681482 — मिसरोद मेढ बंधान शीला बाई छगनलाल | Closed | 48888 | 0 | 2015-10-16
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732003048/IF/9993681507 — मिसरोद मेढ बंधान अजेन्‍द्र श्रीकशिन | Closed | 48888 | 0 | 2015-04-14
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/1910296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4121252 | Completed | 15660 | 15660 | 2018-09-10 | 2018-12-18
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/1916217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4135704 | Completed | 15660 | 15138 | 2018-09-10 | 2018-12-04
HOSHANGABAD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/1918048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4840278 | Completed | 15660 | 15660 | 2018-08-20 | 2019-01-10
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/262690 — Construction of IAY House -IAY REG. NO. MP2806708 | Completed | 15030 | 15150 | 2017-01-23 | 2018-02-12
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3652496 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114848247 | Completed | 18360 | 18360 | 2022-06-01 | 2022-11-15
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3652518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115021185 | Completed | 18360 | 18156 | 2022-06-01 | 2022-11-15
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3652768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117022767 | Completed | 18360 | 18360 | 2022-06-01 | 2022-11-15
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/3652904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118094247 | Ongoing | 27000 | 18225 | 2024-10-09
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3652990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118539299 | Completed | 18360 | 18275 | 2022-06-01 | 2023-05-20
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3653021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118741536 | Completed | 18360 | 18360 | 2022-06-01 | 2022-12-06
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3727180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118590391 | Completed | 18360 | 18360 | 2022-06-01 | 2022-12-06
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3730423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118608061 | Completed | 18360 | 18360 | 2022-06-01 | 2022-12-23
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/3742316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118746902 | Completed | 18360 | 18360 | 2022-06-01 | 2022-12-06
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/40785 — Construction of IAY House -IAY REG. NO. MP-32-003-048-001/143 | Completed | 14310 | 14838 | 2015-12-14 | 2017-01-30
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/40786 — Construction of IAY House -IAY REG. NO. MP-32-003-048-001/90 | Completed | 14310 | 14742 | 2015-12-14 | 2016-10-18
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4314995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116236506 | Completed | 18360 | 18360 | 2022-08-24 | 2022-11-15
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4320436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118748861 | Completed | 18360 | 18360 | 2022-08-31 | 2022-11-15
HOSHANGABAD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4320461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118766494 | Completed | 18360 | 18360 | 2022-08-31 | 2022-11-15
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4701449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118313650 | Completed | 21870 | 21627 | 2024-11-13 | 2025-03-15
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4743928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114844572 | Completed | 21870 | 21627 | 2024-12-04 | 2025-03-15
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4758120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118837723 | Completed | 21870 | 21627 | 2024-12-04 | 2025-03-15
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4758136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118580893 | Completed | 21870 | 21627 | 2024-11-27 | 2025-03-15
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4884098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118588033 | Completed | 23490 | 21870 | 2025-01-22 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4885006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114828072 | Completed | 23490 | 22005 | 2025-01-22 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4892218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116226850 | Physically Completed | 23490 | 21519 | 2025-02-26 | 2026-01-10
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/4995777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114834941 | Completed | 23490 | 23184 | 2025-03-19 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5000129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116878315 | Physically Completed | 23490 | 23103 | 2025-03-19 | 2026-01-02
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5003616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118844342 | Completed | 23490 | 21753 | 2025-03-19 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5003876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118285219 | Completed | 23490 | 22275 | 2025-03-19 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5003993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118593439 | Completed | 23490 | 23103 | 2025-03-19 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5004252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118365948 | Ongoing | 27000 | 20700 | 2025-03-26
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5008758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118828246 | Physically Completed | 23490 | 21753 | 2025-03-19 | 2026-04-05
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5008763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118830240 | Completed | 23490 | 23058 | 2025-03-19 | 2026-05-27
HOSHANGABAD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5008798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118842134 | Completed | 23490 | 22275 | 2025-03-19 | 2026-05-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5155088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118308626 | Completed | 23490 | 23229 | 2025-05-07 | 2026-05-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5163881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118823606 | Physically Completed | 23490 | 23229 | 2025-05-21 | 2026-05-03
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5167075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122065244 | Completed | 23490 | 23229 | 2025-05-14 | 2026-05-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5167371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114838148 | Completed | 23490 | 23229 | 2025-07-31 | 2026-05-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5168234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149714608 | Ongoing | 27000 | 20097 | 2026-01-14
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5172405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115022810 | Completed | 23490 | 23490 | 2025-05-21 | 2026-04-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5174454 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118776701 | Completed | 23490 | 23229 | 2025-06-11 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5180371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115019330 | Completed | 23490 | 23229 | 2025-09-10 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5206051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP132449852 | Physically Completed | 23490 | 23490 | 2025-07-02 | 2026-03-22
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5221096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118586195 | Completed | 23490 | 23490 | 2025-05-21 | 2026-04-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5221392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118338008 | Completed | 23490 | 23229 | 2025-05-07 | 2026-05-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5223745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118113571 | Physically Completed | 23490 | 23229 | 2025-08-13 | 2026-01-02
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5223977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118353796 | Physically Completed | 23490 | 23229 | 2025-08-06 | 2026-01-02
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5226726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118577400 | Completed | 23490 | 23229 | 2025-09-17 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5231366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118744870 | Completed | 23490 | 23229 | 2025-04-23 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5238588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142808576 | Completed | 23490 | 23229 | 2025-06-11 | 2026-05-27
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5238943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118368856 | Ongoing | 27000 | 23100 | 2025-03-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5239133 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118116765 | Physically Completed | 23490 | 23229 | 2025-08-27 | 2026-01-02
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5239888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118309862 | Completed | 23490 | 23229 | 2025-05-07 | 2026-05-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5261369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122061905 | Completed | 23490 | 23229 | 2025-05-21 | 2026-05-27
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/53758 — Construction of IAY House -IAY REG. NO. MP-32-003-048-001/132 | Completed | 14310 | 14646 | 2016-01-04 | 2016-10-18
HOSHANGABAD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/53760 — Construction of IAY House -IAY REG. NO. MP-32-003-048-001/133 | Completed | 14310 | 11832 | 2016-01-04 | 2018-09-17
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5456897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118350758 | Physically Completed | 23490 | 23229 | 2025-08-27 | 2026-06-07
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5457622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118846191 | Ongoing | 27000 | 23229 | 2025-08-06
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5457768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118158677 | Completed | 23490 | 23490 | 2025-07-16 | 2026-04-24
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5457966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118600391 | Ongoing | 27000 | 23229 | 2025-08-06
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5458667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116234279 | Ongoing | 27000 | 23229 | 2025-08-27
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5458844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150099613 | Ongoing | 27000 | 20097 | 2025-10-08
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5461015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149677080 | Completed | 23490 | 23229 | 2025-11-12 | 2026-08-12
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5461549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118371227 | Physically Completed | 23490 | 23229 | 2025-08-27 | 2026-02-18
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5461747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118298533 | Ongoing | 27000 | 18270 | 2025-08-20
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5465031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150873660 | Approved | 27000 | 0 | 2025-04-10
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5465683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118595050 | Completed | 23490 | 23229 | 2025-08-27 | 2026-05-27
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5620281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141827992 | Ongoing | 27000 | 25062 | 2026-05-20
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5620310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118150844 | Ongoing | 27000 | 4200 | 2025-03-21
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5687449 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115013927 | Ongoing | 27000 | 20097 | 2026-01-28
HOSHANGABAD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/5687923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115006880 | Physically Completed | 23490 | 23229 | 2025-09-17 | 2026-06-07
HOSHANGABAD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732003048/IF/IAY/5862562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116225085 | Ongoing | 27000 | 24789 | 2026-04-08
HOSHANGABAD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/587084 — Construction of IAY House -IAY REG. NO. MP3223151 | Completed | 15030 | 15120 | 2017-02-20 | 2018-02-12
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/678824 — Construction of IAY House -IAY REG. NO. MP3223345 | Completed | 15030 | 15480 | 2017-05-15 | 2018-06-15
HOSHANGABAD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732003048/IF/IAY/959225 — Construction of IAY House -IAY REG. NO. MP3267503 | Completed | 15480 | 8256 | 2017-05-15 | 2019-07-29
HOSHANGABAD | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003048/LD/22012034295811 — मिसरौद शांति धाम निर्माण | Completed | 180000 | 176220.48 | 2016-12-26 | 2019-06-29
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732003048/LD/22012034507467 — Misrod - Purani panchayat bhavan ground samtalikaran kary | Closed | 0 | 0 | 2020-04-14
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1732003048/PG/22012034366424 — MISROD ME KHEL MAIDAN NIRMAN | Closed | 190066 | 0 | 2017-10-02
HOSHANGABAD | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732003048/RC/11 — मिसरौद अर्थ वर्क एवं ग्रेवल रोड | Completed | 456000 | 220968 | 2008-09-30 | 2012-03-15
HOSHANGABAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034158401 — मिसरौद (पंच परमेश्‍वर) प्रकाश भंडरी के घर के सामने | Completed | 74652 | 73352 | 2013-01-03 | 2013-03-20
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034166007 — Misrod C.C. Road Kallu Patva Ke Ghar se Temla Pahuch Marg Tak | Completed | 70102 | 69326 | 2013-05-13 | 2013-09-22
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034171469 — मिसरौद राजेश पेमनारायण के घर से रामभरोस मिसत्री के घर तक सी०सी० रोड व नाली | Completed | 21917 | 21568 | 2013-06-17 | 2013-09-22
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034197342 — मिसरौद सुबोध पटैल के घर से पुलिया के उपर तक सी.सी. | Completed | 74043 | 66776 | 2014-01-06 | 2014-04-30
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034202348 — मिसरौद पुलिया से सुबोध पटैल के घर तक सी.सी. रोड नि | Completed | 24730 | 23616 | 2014-02-03 | 2014-04-30
HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034290781 — मिसरौद पंच.पर. दिनेश मासाब के घर से जितेन्‍द्र गौर के घर तक सी.सी. रोड निर्माण | Completed | 48489 | 47329 | 2015-11-30 | 2016-08-08
HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034303165 — c.c.road pappu malvi ke dukan se dinesh gour ki dukan tak | Deleted | 0 | 0 | 2016-01-26
HOSHANGABAD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034303166 — c.c.road vanvari lohar ke makan se chakki chouk tak | Deleted | 0 | 0 | 2016-01-26
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034314029 — मिसरौद सांसद निधि श्‍याम यादव के मकान से नदी की ओर सी.सी. रोड निर्माण | Completed | 84615 | 83700 | 2016-08-01 | 2017-01-30
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034323302 — मिसरोद कललू पटवा के घर से चक्‍की चौक तक सी सी रोड निर्माण | Closed | 0 | 0 | 2017-04-14
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034325377 — मिसरौद राधेश्‍याम गौर के घ्‍ार से गोविंद गौर के घर तक नाली निर्माण | Completed | 3176 | 3173 | 2017-02-13 | 2017-10-10
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034327582 — SADAN GOUR K GHAR SE MAIN ROAD TAK CC ROAD | Completed | 28080 | 28056 | 2017-02-20 | 2017-10-10
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034327936 — GRAM MISROD SADAN GOUR KE GHAR SE MAIN ROAD TAK CC ROAD | Deleted | 28080 | 0 | 2016-10-02
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732003048/RC/22012034331925 — मिसरौद सुदूूूर ग्राम संपर्क मिसरौद से मोफाडा पहुंच मार्ग | Completed | 1450685 | 4796 | 2017-03-20 | 2018-05-15
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034337330 — MISROD MEGHSHYAM ADIVASI KE GHAR SE BHURIYA BAI KHE GHAR TAK DONO AUR NALI NIRMAN | Completed | 11550 | 11352 | 2017-05-08 | 2017-10-12
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034337595 — मिसरोद गणेश मालवीय के घर से चक्‍कीतक नाली ि‍निर्माण कार्य | Completed | 4909 | 4816 | 2017-05-22 | 2017-10-12
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034340644 — MISROD RAMNATH CHOUDHARY KE GHAR SE HEMANT YADAV KE GHAR TAK C.C.. ROAD NIRMAN | Completed | 13680 | 13416 | 2017-06-05 | 2017-10-12
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034342796 — MISROD RAMNATH CHODHRY KE GHAR SE RAMBHAROSH MALVIYA KE GHAR TAK NALI NIRMAN WORK | Completed | 12590 | 12556 | 2017-06-26 | 2017-10-10
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034350430 — राकेश गौर के घर से चकी तक एक तरफ नाली एवं सी सी रोड निर्माण | Deleted | 0 | 0 | 2016-10-02
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034350433 — राकेश गौर के घर से चकी तक एक तरफ नाली एवं सी सी रोड निर्माण | Completed | 50130 | 50052 | 2017-08-28 | 2017-10-12
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034375033 — MISROD RAGHUNANDAN KE GHAR SE SUSHIL GOUR KE GHAR TAK C.C. RAOD NIRMAN | Closed | 0 | 0 | 2016-10-02
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1732003048/RC/22012034375053 — MISROD SUDUR SAMPARK LAKHAN GOUR KE GHAR SE RAMBHAROSH YADAV KE KHET TAK | Closed | 0 | 0 | 2017-10-02
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034433530 — Mishrod - Mukhya Marg mishrod se Harijan colony ki or c.c.road nirman | Completed | 12430 | 11484 | 2018-12-31 | 2019-03-27
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034433534 — Mishrod - Mukesh Khare ke makan se Shyam Prajapati ke makan tak c.c.road nirman | Completed | 43987 | 43848 | 2018-12-31 | 2019-04-30
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034437863 — Omprakash gour ke ghar se rajesh yadav ke ghar tak c.c.road | Deleted | 0 | 0 | 2018-10-02
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034437865 — Rajesh gour ke ghar se Ramkishan gour ke ghar tak c.c.road | Deleted | 0 | 0 | 2018-10-02
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034437866 — Mishrilal sahu ke ghar se rajesh korku ke ghar tak c.c.road | Deleted | 0 | 0 | 2018-10-02
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034444529 — Prakash gour ke makan se gangaram ke makan tak c.c.road | Completed | 23383 | 22176 | 2019-06-03 | 2019-07-23
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034444531 — Mishrilal sahu ke ghar se rajesh korku ke ghar tak c.c.road | Completed | 30911 | 30276 | 2019-02-18 | 2019-05-10
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034481358 — Mishrod - Shala parisar pahunch hetu jhurkiya nale pr puliya road nirman | Completed | 16356 | 14674 | 2020-01-27 | 2021-02-24
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034481360 — Mishrod - Anganwadi ke samne v jhurkiya nale se shala parisar tak c.c.road | Completed | 17968 | 17952 | 2019-12-23 | 2020-04-01
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003048/RC/22012034536165 — MISROAD MANDIR PURA DINESH KE MAKAN SE SHALAKRAM KE MAKAN TAK C C ROAD (BAIRING COTE) | Completed | 23380 | 23180 | 2020-09-01 | 2020-09-28
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003048/RC/22012034536166 — MISROD RAJU PATELE SE ZURKIYA PULIYA TAK C C ROAD (BAIRING COTE) | Completed | 13242 | 13110 | 2020-09-14 | 2020-10-12
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034542094 — MISROD ZORKI PULIYA PAR CEMENT CONCRIT KARYA | Completed | 6171 | 6080 | 2020-10-05 | 2021-02-24
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Cement Concrete Roads for Comm / Repair and maintenance of Cement Concrete Roads for Community | Repair & maint of Road | 1732003048/RC/22012034542102 — MISROD CHAKKI CHOUK SE SHAILENDRA GOUR KE GHAR & NEW PULIYA TAK C C ROAD (BARING COTE) | Completed | 41955 | 41800 | 2020-10-12 | 2020-11-17
HOSHANGABAD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034551701 — MISROD RAJESJ GOUR KE MAKAN SE BHAGIRATH GOUR KE GHAR TAK PAKKI NALI NIRMAN | Completed | 15454 | 15200 | 2020-12-14 | 2021-02-24
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/22012034665533 — Mishrod - Amit gour ke ghar se Ashok patel ke ghar tak ccroad nirman | Completed | 10107 | 10104 | 2023-10-07 | 2023-12-11
HOSHANGABAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/46 — मिसरौद (पंच परमेश्‍वर) सुबोध पटैल के घर से चक्‍की तक नाली निर्माण | Completed | 96396 | 52718 | 2012-05-14 | 2012-10-30
HOSHANGABAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/66 — मिसरौद (पंच परमेश्‍वर) सी.सी. रोड एवं एक तरफ नाली निर्माण सोसायटी से नानकराम के घर तक | Completed | 50170 | 43536 | 2012-10-26 | 2012-12-05
HOSHANGABAD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732003048/RC/67 — मिसरौद (पंच परमेश्‍वर) सी.सी. रोड एवं एक तरफ नाली निर्माण मिसरौद टेमला रोड से शैलेन्‍द्र गौर के घर | Completed | 50170 | 49767 | 2012-10-20 | 2012-12-05
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034213738 — MISROD TOILET SANTOSH GANESH GULABBAI CHETRAM SULO | Completed | 27000 | 20832 | 2014-03-05 | 2015-05-20
HOSHANGABAD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034248747 — मिसरोद 5 शौचालय श्रीराम माखन रामक़ष्‍ण क्षमा दुलीच | Completed | 27000 | 22946 | 2014-07-07 | 2015-03-22
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034329367 — RAJESND S/O SHAKAR LAL SOCHALAYE NIRMAN | Completed | 12000 | 10845 | 2017-03-20 | 2018-07-30
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034330623 — संतोष/हजारीलाल सोचलाय निर्माण मिसरोद | Completed | 12000 | 11877 | 2017-03-20 | 2017-10-20
HOSHANGABAD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034330635 — कालूराम पटवा/दरमु पटवा सोचालय निर्माण | Completed | 12000 | 11877 | 2017-03-20 | 2017-10-20
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034334838 — रामनाथ/रामशकर सोचालय निर्माण मिसरोद | Completed | 12000 | 11937 | 2017-04-10 | 2019-09-20
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034334848 — रामकिशोर/रामभरोस यादव सोचलाय निर्माण | Completed | 12000 | 11937 | 2017-04-10 | 2018-07-25
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034345454 — जयराम/कमलकिशोर सोचलाए निर्माण मिसरोद | Completed | 12000 | 11937 | 2017-06-05 | 2018-05-25
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034350272 — मिसरोद छगनलाल/नर्मदा प्रसाद गौर सोचलाय निर्माण वर्क | Completed | 12000 | 10905 | 2017-06-05 | 2018-06-25
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034350980 — मिसरोद कमलेश/रामनाथ सोचालय निर्माण वर्क | Completed | 12000 | 11765 | 2017-06-12 | 2018-06-15
HOSHANGABAD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732003048/RS/22012034351349 — मिसरोद गीता/हरिप्रसाद सोचलाय निर्माण | Deleted | 12000 | 0 | 2017-06-07
HOSHANGABAD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034439897 — Mishrod - Community Nadep Nirman | Closed | 17127.37 | 0 | 2019-01-26
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034441796 — Nadep Nirman - Kallu Patwa ke ghar ke paas | Closed | 17184.72 | 0 | 2019-05-26
HOSHANGABAD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034441797 — Nadep Nirman - SreeRam Choudhary ke ghar ke paas | Closed | 17184.72 | 0 | 2019-05-26
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732003048/RS/22012034509352 — Mishrod - Community Toilet construction (CSC) Village-Mishrod - Bas Stand per | Completed | 72833 | 36330 | 2021-04-06 | 2023-01-15
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Berkeley Compost Pit for Community / Construction of Berkeley Compost Pit for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517541 — SLWM - Conv. - Segrigation shed Nirman - Mishrod | Completed | 21277 | 22209 | 2022-03-22 | 2022-06-17
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & Maint of Compost Pit for Community / Repair and Maintenance of Compost Pit for Community | Repaire and Maint of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517898 — SLWM - 2 work - Bhu Nadep (Khad Gadda) - Community | Closed | 6089.18 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517899 — SLWM - 50 work - Bhu Nadep (Khad Gadda) - Gharelu | Closed | 16776.84 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517900 — SLWM - 2 work - Community nadep - Mishrod | Closed | 30186.46 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517901 — SLWM - 15 work - Ghrelu Nadep - Compost Structure for Groups | Closed | 167856.61 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517902 — SLWM - 2 work - Vermi Compost - Community | Closed | 47790.75 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Vermi Compost structure for Groups / Construction of Vermi Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1732003048/RS/22012034517903 — SLWM - 15 work - Vermi Compost - Gharelu | Closed | 0 | 0 | 2021-04-14
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003048/RS/22012034703818 — Misrod - Nathuram yadav ke ghar se bhagirath ke ghar tak nali nirman | Completed | 4501 | 4494 | 2023-10-04 | 2023-12-11
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003048/RS/22012034703820 — Misrod - sanju gour ke ghar se sunil gour ke ghar tak nali nirman | Completed | 5063 | 5040 | 2023-10-04 | 2023-12-11
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003048/RS/22012035118326 — MISROD RCC NALI NIRMAN SHRAVAN SONKIYA KE GHAR SE RAJESH KUSHWAH KE GHAR TAK | Closed | 22174 | 0 | 2023-04-14
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732003048/RS/22012035118330 — MISROD BHAGIRATH KE GHAR SE SANTOSH KE GHAR TAK C C NALI | Closed | 26339 | 0 | 2023-04-14
HOSHANGABAD | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732003048/SK/844 — Bharat Nirman Rajeev Gandhi Sewa Kendra,MISROD | Completed | 1000000 | 986174.2 | 2013-09-23 | 2017-01-30
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003048/WC/22012034511446 — Mishrod - Stop dam nirman - nadi per | Closed | 0 | 0 | 2019-05-26
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003048/WC/22012034511447 — Mishrod - Stop dam nirman - nadi per | Deleted | 0 | 0 | 2019-05-26
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034525556 — Mishrod-aanganwadi bhavan me water harvesting work | Closed | 0 | 0 | 2020-01-26
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034525557 — Mishrod-panchayat bhavan me water harvesting work | Closed | 0 | 0 | 2020-01-26
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034525558 — Mishrod-school bhavan me water harvesting work | Closed | 0 | 0 | 2020-01-26
HOSHANGABAD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034525559 — Mishrod-Hatt Bazar me water harvesting work | Closed | 0 | 0 | 2020-01-26
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/22012034545164 — Misrod - Bhagirath ke ghar se handpump tak nali | Closed | 0 | 0 | 2020-04-14
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/22012034545166 — Misrod - Govind ke ghar se Kailash ke ghar tak nali | Closed | 0 | 0 | 2020-04-14
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/22012034545167 — Misrod - Anil ke ghar se sony ji ke ghar tak nali | Closed | 0 | 0 | 2020-04-14
HOSHANGABAD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/22012034545168 — Misrod - Rameshver gour ke ghar se sony ji ke ghar tak nali | Closed | 0 | 0 | 2020-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1732003048/WC/22012034663766 — CTR - Mishrod Talab Sudradikaran kary | Closed | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732003048/WC/22012034668679 — CTR - 7 Work misrod - Rain water harvesting | Closed | 192678.9 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732003048/WC/22012034668804 — CTR - 10 work Misrod -Sock pit nirman | Ongoing | 135702.29 | 17370 | 2021-10-05
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003048/WC/22012034687255 — CTR - Misrod - Khet Talab Hari om ke khet me | Closed | 110516.06 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003048/WC/22012034687273 — CTR - Mishrod - Jhukriya Nala Sudradikaran Kary | Deleted | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003048/WC/22012034693329 — CTR-SLWM-Conv.- 1 nos. Jal Shudhdhikaran Tank Nirman at Village - Mishrod | Closed | 7015 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034693503 — CTR-SLWM-Conv.- 29 nos. Sock Pit Nirman (Community), At village - Misrod | Deleted | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034693504 — CTR-SLWM-Conv.- 29 nos. Sock Pit Nirman (Community), At village - Misrod | Completed | 181830 | 82900.92 | 2021-11-23 | 2026-04-26
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012034693507 — CTR-SLWM-Conv.- 6 nos. Magic Pit Nirman (Community), At village - Misrod | Closed | 68826 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003048/WC/22012034880066 — Mishrod - Jivan prajapati ke ghar se jhurkiya nale tak nali nirman | Completed | 86158 | 86672 | 2021-11-30 | 2022-04-26
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003048/WC/22012034912392 — Mishrod - Talab Jirnodhdhar kary | Closed | 0 | 0 | 2021-04-14
HOSHANGABAD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003048/WC/22012034912393 — Mishrod - Talab Jirnodhdhar kary | Closed | 0 | 0 | 2021-04-14
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1732003048/WC/22012034944537 — मिसरौद अम़त सरोवर अन्‍तर्गत लामदा नदी पर ओ पी गौर के खेत के पास स्‍टापडेम निर्माण | Completed | 212000 | 170861 | 2022-04-20 | 2026-04-01
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003048/WC/22012034986357 — Misrod - talaiya ki gad nikalne ka kary | Closed | 0 | 0 | 2022-05-14
HOSHANGABAD | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732003048/WC/22012034986358 — Misrod - talaiya ki gad nikalne ka kary | Closed | 79951 | 0 | 2022-05-14
HOSHANGABAD | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003048/WC/22012035147847 — Misrod - Shravan sonkiya ke ghar se rajesh kushwah ke ghar tak rcc nali nirman | Closed | 22174 | 0 | 2023-04-01
HOSHANGABAD | 2024-2025 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1732003048/WC/22012035147850 — Misrod - Bhagirath ke ghar se santosh ke ghar tak rcc nali nirman | Completed | 26339 | 26339.04 | 2024-07-12 | 2025-05-04
HOSHANGABAD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732003048/WC/22012035205158 — MISROD LICHPIT NIRMAN SANTOSH VISHWAKARMA KE PASWALE HANDPUMP | Approved | 16132 | 0 | 2024-04-14
HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732003048/WC/22012035288442 — MISROD SHALIKRAM VERMA KE GHAR KOOP RICHARG PIT | Completed | 17105 | 5741 | 2025-04-29 | 2026-04-26
HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1732003048/WC/22012035312166 — CTR-JGSA-154/28 Govt HS school Parisar ke Kup ke pash recharge Pit | Approved | 17843 | 0 | 2025-04-14
HOSHANGABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/671 — मिसरौद सोक्‍ता गड्रडा सोसायटी के पास | Completed | 6815 | 6270 | 2011-06-30 | 2012-07-23
HOSHANGABAD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/672 — मिसरौद सोक्‍ता गड्रडा शाला प्रांगण में | Completed | 6815 | 6315 | 2011-06-22 | 2012-07-23
HOSHANGABAD | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1732003048/WC/9993628356 — मिसरौद सोकपिट निर्माण बसस्‍टेण्‍ड पर श्‍ाासकीय हेण्‍डपंप के पास | Deleted | 6950 | 0 | 2013-01-26
HOSHANGABAD | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732003048/WC/VB/YD/22012035335668 — Roof top rain wat. har. str. in gov Building Mishrod | Approved | 0 | 0 | 2026-04-14
HOSHANGABAD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1732003048/WH/22012034944351 — CTR JGSA MISROD TALAB SAF SAFAI AVAM SOUNDRIYKARAN | Completed | 49615.6 | 12528 | 2025-05-28 | 2026-04-27