## Work List
Exported on: 2026-10-21 10:31:08
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: NASIRABAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1732004012/IF/22012035524057 — JGSA Dug well rechage Hargovind kevat GP Nashirabad | Approved | 36926.74 | 0 | 2025-04-14
MAKHAN NAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1732004043/DP/22012034407496 — Virchharopan Ganeta nala kinare | Ongoing | 335000 | 0 | 2018-12-03
MAKHAN NAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Agro Forestry Block Plantation for Community | Plantation | 1732004043/DP/22012034435638 — Virchharopan Dev Satal | Ongoing | 335000 | 0 | 2019-01-16
MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1732004043/DP/22012034625118 — Plantation rod kinare narmada path Reva Shri school se dhana tola narmda nadi tak gp Nasirabad | Ongoing | 453563.17 | 0 | 2024-07-21
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1732004043/IC/22012034891103 — JGSA Form pond construction Radheshyam/gangaram keer | New | 0 | 0 | 2025-04-14
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004043/IF/22012035412416 — JGSA Form pond nirmaan Murlidhar /Chandan singh GP Bagalkhedi | Approved | 0 | 0 | 2025-04-14
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004043/IF/22012035497407 — JGSA Form pond nirmaan Anita /vishnu prasad GP Nashirabad | Approved | 147621.16 | 0 | 2025-04-14
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732004043/IF/22012035522249 — JGSA Dug well recharge Choti bai/Kapoor van gp n ashirabad | Approved | 0 | 0 | 2025-05-14
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732004043/IF/22012035522268 — JGSA Dug well recharge FOOLVAN/Gajravan GP NASHIRABAD | Approved | 0 | 0 | 2025-05-14
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1732004043/IF/22012035522288 — JGSA Dug well recharge Hargovind kevat GP Nahirabad | Approved | 0 | 0 | 2025-05-14
MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1732004043/IF/22012035524059 — JGSA Dug well rechage Choti bai Gp Nasheerabad | Approved | 0 | 0 | 2025-04-14
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1732004043/IF/22012035553166 — JGSA Form pond nirmaan anita bai/Vishnu ahirwar GP Nashirabad | Ongoing | 396198.38 | 0 | 2025-06-29
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732004043/IF/22012035637605 — Ek Bagiya maa ke naam Geeta yadav Nasirabad | New | 0 | 0 | 2025-04-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732004043/IF/22012035637614 — Ek Bagiya maa ke naam Geeta yadav Nasirabad | Ongoing | 269387.37 | 18600 | 2026-01-08
MAKHAN NAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/1900368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2132046 | Approved | 27000 | 0 | 2018-07-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/4550206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113457644 | Ongoing | 27000 | 0 | 2024-11-09
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/4992652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113881283 | Approved | 27000 | 0 | 2025-02-13
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/4992679 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113887500 | Ongoing | 27000 | 0 | 2025-03-20
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5094724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409615 | Ongoing | 27000 | 0 | 2025-03-20
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5094725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409900 | Ongoing | 27000 | 0 | 2025-03-21
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5094726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410405 | Ongoing | 27000 | 0 | 2025-03-25
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5374612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409676 | Approved | 27000 | 0 | 2025-03-27
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5465976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409148 | Ongoing | 27000 | 0 | 2025-06-16
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5902622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117738083 | Ongoing | 27000 | 18900 | 2026-08-12
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5903120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410113 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5903924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413074 | Ongoing | 27000 | 22500 | 2026-06-16
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5904271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410271 | Ongoing | 27000 | 21000 | 2026-06-02
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5904916 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113888049 | Ongoing | 27000 | 20700 | 2026-08-05
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5905996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141412936 | Physically Completed | 27000 | 16800 | 2026-05-25 | 2026-09-27
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5907306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802565 | Physically Completed | 27000 | 18300 | 2026-05-25 | 2026-10-11
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5907431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456526 | Physically Completed | 27000 | 20400 | 2026-06-02 | 2026-10-11
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5907517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117743269 | Ongoing | 27000 | 24600 | 2026-06-16
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5907892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413536 | Physically Completed | 23490 | 2100 | 2026-05-25 | 2026-08-16
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5907936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456053 | Ongoing | 27000 | 16800 | 2026-06-02
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5909919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141301572 | Physically Completed | 23490 | 8400 | 2026-05-25 | 2026-08-16
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5909938 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409632 | Ongoing | 27000 | 20400 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5910062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456933 | Ongoing | 27000 | 23100 | 2026-07-29
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5912285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413828 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5913471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141300335 | Ongoing | 27000 | 20400 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5914240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117740987 | Ongoing | 27000 | 4200 | 2026-08-22
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5914272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113834815 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5914791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141412864 | Ongoing | 27000 | 18600 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5915753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802690 | Ongoing | 27000 | 16800 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5916556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456309 | Physically Completed | 27000 | 20700 | 2026-06-02 | 2026-10-04
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5917046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117740267 | Ongoing | 27000 | 18900 | 2026-08-12
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5917179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141414088 | Ongoing | 27000 | 9900 | 2026-08-22
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5917490 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113459589 | Ongoing | 27000 | 20700 | 2026-08-05
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5918229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106113029 | Ongoing | 27000 | 0 | 2026-10-03
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5919135 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456632 | Physically Completed | 27000 | 18300 | 2026-05-25 | 2026-10-18
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5919322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141414015 | Ongoing | 27000 | 5700 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5919372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117737224 | Ongoing | 27000 | 18900 | 2026-08-12
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5919918 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410251 | Physically Completed | 27000 | 16800 | 2026-05-25 | 2026-09-27
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5920117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413571 | Ongoing | 27000 | 25200 | 2026-07-20
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5920245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113881960 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5920480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802537 | Ongoing | 27000 | 21000 | 2026-07-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5921338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456463 | Physically Completed | 27000 | 14100 | 2026-06-02 | 2026-10-11
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5922027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413626 | Ongoing | 27000 | 18300 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5924035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413289 | Physically Completed | 27000 | 20400 | 2026-06-02 | 2026-10-18
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5924675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409574 | Ongoing | 27000 | 14100 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5925006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117988727 | Ongoing | 27000 | 21000 | 2026-08-05
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5925607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117741703 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5925982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141408991 | Ongoing | 27000 | 22800 | 2026-07-29
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5928119 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113664684 | Physically Completed | 27000 | 20400 | 2026-06-02 | 2026-10-11
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5928662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113459402 | Physically Completed | 27000 | 18300 | 2026-05-25 | 2026-10-18
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5929020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113457264 | Ongoing | 27000 | 18300 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5929132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456379 | Physically Completed | 27000 | 18600 | 2026-05-25 | 2026-10-04
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5930350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410029 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5930518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141412881 | Ongoing | 27000 | 0 | 2026-09-29
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/5930900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410301 | Ongoing | 27000 | 18900 | 2026-05-25
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6125858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141300912 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6138341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117741359 | Ongoing | 27000 | 9900 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6147393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113665028 | Physically Completed | 27000 | 25200 | 2026-07-06 | 2026-10-18
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6148300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119093460 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6149355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409792 | Ongoing | 27000 | 21000 | 2026-06-16
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6149356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409861 | Ongoing | 27000 | 9900 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6149357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410186 | Ongoing | 27000 | 5700 | 2026-08-13
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6149358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410333 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6159857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413016 | Ongoing | 27000 | 26700 | 2026-07-06
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6159858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413052 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6159859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413167 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6159860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413489 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6168184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117737935 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6168605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146423738 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6168716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113882294 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6168899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141298802 | Ongoing | 27000 | 4200 | 2026-08-22
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6170884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150376948 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6178067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413102 | Ongoing | 27000 | 25200 | 2026-07-06
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6180925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413788 | Ongoing | 27000 | 18900 | 2026-08-12
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6183618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410150 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6183809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117741223 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6188898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413329 | Ongoing | 27000 | 8400 | 2026-08-05
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6201117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456708 | Ongoing | 27000 | 16800 | 2026-08-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6202295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456161 | Ongoing | 27000 | 6300 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6207292 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117743354 | Ongoing | 27000 | 16200 | 2026-08-13
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6216773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456791 | Ongoing | 27000 | 21000 | 2026-07-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6216932 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802704 | Ongoing | 27000 | 5700 | 2026-08-13
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6251697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802585 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6254696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117741596 | Approved | 27000 | 0 | 2026-04-22
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141298070 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141301328 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410493 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141412955 | Approved | 27000 | 0 | 2026-03-30
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141412982 | Approved | 27000 | 0 | 2026-03-30
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413244 | Approved | 27000 | 0 | 2026-03-30
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272790 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413452 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413690 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6272792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413913 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6287113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119085633 | Approved | 27000 | 0 | 2026-03-30
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6306756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117740603 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6306903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150377002 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6321034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117739487 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6321214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410002 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6321232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410433 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6321601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113664885 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6321657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141409081 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6354694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141412848 | Approved | 27000 | 0 | 2026-03-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6354967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117740787 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6355430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141410067 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6377028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141413138 | Approved | 27000 | 0 | 2026-03-06
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6387928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456087 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/6387975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113456011 | Approved | 27000 | 0 | 2026-01-19
MAKHAN NAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732004043/IF/IAY/981087 — Construction of IAY House -IAY REG. NO. MP3925153 | Approved | 27000 | 0 | 2017-04-01
MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732004043/RC/22012034828303 — C c road va nali nirman yaswant yadav ke ghar se Ashok kevat ke ghar ki or | Ongoing | 44000 | 0 | 2024-10-10
MAKHAN NAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1732004043/WC/22012034561204 — check dam nirman bakud nadi per nasirabad | Ongoing | 476992.06 | 0 | 2021-05-05
MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1732004043/WC/22012035206078 — Trench construction work pwd road se timedi tak Nasheerabad | Ongoing | 218189.88 | 0 | 2024-06-29
MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732004043/WC/22012035206105 — Sokhta gadda nirman sab station bhatwadi G p Nasheerabad | New | 0 | 0 | 2024-06-08
MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732004043/WC/22012035206113 — Sokhta gadda nirman sab station bhatwadi G p Nasheerabad | Approved | 0 | 0 | 2024-06-08
MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1732004043/WC/22012035206123 — Sokhta gadda nirman panchayat bhavan parisar G p Nasheerabad | Approved | 0 | 0 | 2024-06-08
MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1732004043/WC/22012035282059 — JGSA Pokhar nirman panchayat bhavan ke pass GP Nashirabad | Approved | 0 | 0 | 2025-04-14
MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1732004043/WH/22012034944114 — JGSA ROOF WATER HARVESTING PS SALA BHAVAN BHATWADI | Approved | 0 | 0 | 2025-04-14