## Work List
Exported on: 2026-09-15 22:20:23
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: SUKKARWADA FARM
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
MAKHAN NAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1732004064/AV/22012034663975 — Khel medan sukkarwada form school | New | 0 | 0 | 2025-01-26
MAKHAN NAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1732004064/DP/22012034612224 — Vichharopan Samsanghat ke pass | Ongoing | 427106.07 | 0 | 2024-01-09
MAKHAN NAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1732004064/DP/22012034627153 — Vraksharopan handpump ke pas se khedpati mandir pahuch marg | Ongoing | 453563.17 | 0 | 2024-10-12
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732004064/IF/22012035083301 — पशु शेड निर्माण कार्य हित ग्राही तनु यादव/मनोज | Ongoing | 69030.56 | 0 | 2026-02-17
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732004064/IF/22012035588195 — PMAY Awash Mukesh Yadav / Ramkaran MP116779781 | Ongoing | 23400 | 0 | 2025-09-01
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732004064/IF/22012035588298 — PMAY Awash Raghuveer / Mohansingh MP146254073 | Ongoing | 23400 | 0 | 2025-08-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732004064/IF/22012035593351 — PMAY Awash Dileep singh /Jhrisha MP114142838 | Ongoing | 23400 | 0 | 2025-09-26
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732004064/IF/22012035642012 — EK BAGIYA MAA KE NAME SANGITA YADAV/ DASHRATH SINGH GP SUKKARWADAFARM | New | 0 | 0 | 2025-04-04
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732004064/IF/22012035642459 — EK BAGIYA MAA K NAME SUNITA BAI /DASHRATH YADAV GP SUKKARWADAFARM | New | 0 | 0 | 2025-04-04
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732004064/IF/22012035643237 — EK BAGIYA MAA KEE NAME SUNITA BAI /DASHRATH YADAV GP SUKKARWADAFARM | New | 0 | 0 | 2025-04-01
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4578019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118091521 | Ongoing | 27000 | 0 | 2025-01-29
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4581269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118366782 | Physically Completed | 23490 | 0 | 2025-03-25 | 2026-08-06
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4581339 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119382500 | Ongoing | 27000 | 0 | 2025-02-07
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4619120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126741001 | Ongoing | 27000 | 0 | 2025-02-15
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4753327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118164375 | Ongoing | 27000 | 0 | 2025-03-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4755369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118044211 | Approved | 27000 | 0 | 2024-09-18
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4755526 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118078082 | Physically Completed | 23490 | 0 | 2025-02-07 | 2026-07-26
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4757029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119382741 | Physically Completed | 23490 | 0 | 2025-02-07 | 2026-08-06
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4758221 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118595241 | Physically Completed | 23490 | 0 | 2026-03-07 | 2026-07-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/4762153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121593562 | Ongoing | 27000 | 0 | 2025-03-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5823535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126741343 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5823763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114964464 | Approved | 27000 | 0 | 2025-02-24
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5823967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118607689 | Approved | 27000 | 0 | 2025-02-26
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5824044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119384724 | Ongoing | 27000 | 4200 | 2026-04-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5824219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118117067 | Approved | 27000 | 0 | 2025-02-26
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5824278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115030172 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5824556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119916311 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115028656 | Approved | 27000 | 0 | 2025-04-27
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114980220 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118784726 | Approved | 27000 | 0 | 2025-02-24
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117927691 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119932322 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119642464 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119642945 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825923 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116254632 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5825937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119958795 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118595905 | Ongoing | 27000 | 0 | 2026-04-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118603532 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118611906 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826228 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116247960 | Approved | 27000 | 0 | 2025-03-27
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119382947 | Physically Completed | 23490 | 0 | 2026-03-15 | 2026-08-16
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119380560 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5826697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119378448 | Ongoing | 27000 | 2100 | 2026-07-10
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5827360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116450120 | Approved | 27000 | 0 | 2025-03-27
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5827926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119378076 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5827928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119379293 | Physically Completed | 23490 | 0 | 2025-02-23 | 2026-08-09
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5827929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119382270 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5827930 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119383965 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5828213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118765683 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5828239 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116509750 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5828403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116779781 | Approved | 27000 | 0 | 2025-02-26
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5828522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119978628 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5828551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114538239 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5843771 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115030460 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5844009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120052825 | Approved | 27000 | 0 | 2025-02-23
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5844067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118171583 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5844205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126740363 | Approved | 27000 | 0 | 2025-03-12
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5844514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118554937 | Ongoing | 27000 | 0 | 2026-02-04
MAKHAN NAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5845283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116927307 | Approved | 27000 | 0 | 2025-03-05
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/5845865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118335150 | Physically Completed | 23490 | 1800 | 2026-03-06 | 2026-08-09
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6123607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115030208 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6124011 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120591169 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6145596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115028768 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6148291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119081729 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6159299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116918722 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6159898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116243595 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6162877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116228335 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6163515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116238880 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732004064/IF/IAY/6172635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122433388 | Approved | 27000 | 0 | 2026-02-16
MAKHAN NAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1732004064/WC/22012035280630 — JSGA Roof water harwesting Mangal baban kali mandir GP sukaarwada form | Ongoing | 27853.08 | 0 | 2025-05-16