## Work List
Exported on: 2026-10-21 12:51:36
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: THIKARI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SOHAGPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Goat Shelter for Community / Construction of Goat Shelter for Community | Goat Shelter | 1732005058/AV/22012034640746 — shantidham nirman kary gram panchayt thikari | Ongoing | 226381.46 | 0 | 2023-12-28
SOHAGPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Along the coast Line Plantation of Forestry Trees for Community | Plantation | 1732005058/DP/22012034586383 — Vasuda vandan plantation gp thikri | Ongoing | 55847.4 | 0 | 2023-12-28
SOHAGPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1732005058/IF/22012035246827 — वृक्षारोपण कार्य किरण /कैलाश शाहू के खेत में | New | 0 | 0 | 2024-07-08
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4566586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116471275 | Ongoing | 27000 | 0 | 2025-01-01
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4575300 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117590214 | Ongoing | 27000 | 0 | 2024-11-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4580184 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118142582 | Ongoing | 27000 | 0 | 2024-12-04
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4609940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125523431 | Ongoing | 27000 | 0 | 2025-06-17
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4619091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126734942 | Ongoing | 27000 | 0 | 2025-01-22
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4694562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116273551 | Ongoing | 27000 | 0 | 2025-01-01
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4709348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125334100 | Ongoing | 27000 | 0 | 2025-02-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4742438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113705652 | Ongoing | 27000 | 0 | 2024-12-04
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4753212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118133027 | Ongoing | 27000 | 0 | 2025-01-22
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4753218 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118134491 | Ongoing | 27000 | 0 | 2025-07-29
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4773060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124965058 | Ongoing | 27000 | 0 | 2025-01-01
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4879010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126455266 | Ongoing | 27000 | 0 | 2025-01-03
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4993879 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113706748 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4994107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113731575 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4994775 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114954697 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4997629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114969502 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4997756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115893603 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4997829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115911088 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4997982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116294614 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4997992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116296766 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4998004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116299465 | Ongoing | 27000 | 0 | 2025-05-12
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4998005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116299526 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/4998098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116517505 | Physically Completed | 27000 | 0 | 2025-03-19 | 2026-10-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5000884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116327034 | Ongoing | 27000 | 0 | 2025-03-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5001719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117271718 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5001721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117272541 | Ongoing | 27000 | 2100 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5002262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115942269 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5002892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118117908 | Ongoing | 27000 | 2100 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5003542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117422621 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5003555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117426204 | Ongoing | 27000 | 0 | 2025-03-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5003568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117427669 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5004686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118123943 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5004747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118139162 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5004784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118146092 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5004888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118180423 | Approved | 27000 | 0 | 2025-02-21
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5005282 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117876775 | Ongoing | 27000 | 0 | 2025-06-23
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5005585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118784500 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5005689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118820513 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5016010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125051905 | Ongoing | 27000 | 0 | 2026-04-23
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5017356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125316824 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5020983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126456955 | Ongoing | 27000 | 0 | 2025-04-27
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5020990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126458073 | Ongoing | 27000 | 0 | 2025-07-29
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5021122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126481426 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5021299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126733409 | Approved | 27000 | 0 | 2025-02-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5021302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126734504 | Approved | 27000 | 0 | 2025-02-26
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5021304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126734769 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5021317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736366 | Ongoing | 27000 | 0 | 2025-03-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5021321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126737681 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5082448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118304570 | Ongoing | 27000 | 0 | 2025-03-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5082466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118309218 | Ongoing | 27000 | 0 | 2025-03-18
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5083883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126880422 | Ongoing | 27000 | 0 | 2025-04-27
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5099036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146941582 | Ongoing | 27000 | 0 | 2025-03-26
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5147178 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126452312 | Physically Completed | 27000 | 0 | 2025-04-27 | 2026-10-04
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5151737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126733237 | Approved | 27000 | 0 | 2025-02-21
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5193335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118128585 | Approved | 27000 | 0 | 2025-02-21
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5194204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117265834 | Ongoing | 27000 | 4200 | 2025-04-27
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5221302 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146943736 | Ongoing | 27000 | 0 | 2025-05-12
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5246139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117262903 | Ongoing | 27000 | 0 | 2025-05-19
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5252432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736629 | Ongoing | 27000 | 0 | 2025-04-27
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5261433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126755177 | Approved | 27000 | 0 | 2025-03-13
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5263692 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126737133 | Ongoing | 27000 | 4200 | 2026-01-30
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5265168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118148642 | Ongoing | 27000 | 0 | 2025-04-27
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5271397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116525365 | Ongoing | 27000 | 0 | 2026-01-23
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5271851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736161 | Ongoing | 27000 | 0 | 2025-04-27
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5297064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118827645 | Ongoing | 27000 | 0 | 2025-05-19
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5297359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113733948 | Ongoing | 27000 | 0 | 2025-06-17
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5314247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119840662 | Ongoing | 27000 | 0 | 2025-05-04
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5317977 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126464041 | Ongoing | 27000 | 0 | 2025-05-19
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5319920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117808906 | Approved | 27000 | 0 | 2025-02-26
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5322694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129954850 | Ongoing | 27000 | 0 | 2025-05-19
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5323854 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116477875 | Physically Completed | 27000 | 0 | 2025-04-27 | 2026-09-06
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5329350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118127067 | Ongoing | 27000 | 0 | 2025-04-13
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5459164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113721420 | Ongoing | 27000 | 0 | 2025-06-24
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5462440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126462659 | Ongoing | 27000 | 0 | 2025-09-11
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5463248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119547559 | Ongoing | 27000 | 0 | 2025-05-04
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5528909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116499227 | Ongoing | 27000 | 0 | 2025-05-19
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5615272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117849628 | Ongoing | 27000 | 0 | 2025-06-17
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5619802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126445784 | Ongoing | 27000 | 4200 | 2026-01-23
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5678316 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126480476 | Physically Completed | 27000 | 3900 | 2026-01-30 | 2026-09-27
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5678566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124955210 | Ongoing | 27000 | 0 | 2025-08-11
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5678640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118125806 | Approved | 27000 | 0 | 2025-02-21
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5687473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126735087 | Ongoing | 27000 | 0 | 2026-01-30
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5687476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118129572 | Approved | 27000 | 0 | 2025-02-21
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5687551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117415005 | Ongoing | 27000 | 0 | 2025-12-30
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5687552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115900711 | Approved | 27000 | 0 | 2025-02-26
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5687675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126736823 | Ongoing | 27000 | 0 | 2026-02-26
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5687821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118781505 | Ongoing | 27000 | 0 | 2025-08-11
SOHAGPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5716655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126454099 | Approved | 27000 | 0 | 2025-02-26
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5815535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113718421 | Ongoing | 27000 | 0 | 2025-09-27
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5937758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126737432 | Approved | 27000 | 0 | 2026-02-19
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5941036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126735569 | Ongoing | 27000 | 0 | 2026-04-07
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/5941761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115908020 | Physically Completed | 27000 | 0 | 2026-06-22 | 2026-10-18
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6076960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117908539 | Ongoing | 27000 | 5400 | 2026-07-08
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6076981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117917166 | Approved | 27000 | 0 | 2026-02-24
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6079173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119547553 | Ongoing | 27000 | 0 | 2026-08-17
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6087910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126447638 | Ongoing | 27000 | 5400 | 2026-07-16
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6087949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126461114 | Approved | 27000 | 0 | 2026-02-19
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6088767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126735260 | Approved | 27000 | 0 | 2026-02-24
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6088770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126735745 | Approved | 27000 | 0 | 2026-02-24
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6124354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126466198 | Approved | 27000 | 0 | 2026-02-12
SOHAGPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6248406 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106397864 | Approved | 27000 | 0 | 2026-04-15
SOHAGPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/6255532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117806351 | Approved | 27000 | 0 | 2026-02-24
SOHAGPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/880611 — Construction of IAY House -IAY REG. NO. MP1871406 | Approved | 27000 | 0 | 2017-04-01
SOHAGPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/883947 — Construction of IAY House -IAY REG. NO. MP1916971 | Approved | 27000 | 0 | 2017-04-01
SOHAGPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/969652 — Construction of IAY House -IAY REG. NO. MP3541359 | Approved | 27000 | 0 | 2017-04-01
SOHAGPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732005058/IF/IAY/971487 — Construction of IAY House -IAY REG. NO. MP3590742 | Approved | 27000 | 0 | 2017-04-01
SOHAGPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1732005058/RC/22012034681804 — सीसी रोड मरम्मत कार्य नेटू कुम्हार के घर से दशरथ कहार के घर तक ग्राम ठीकरी | Ongoing | 24000 | 0 | 2024-03-10
SOHAGPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732005058/RS/22012035125576 — आर सी सी नाली निर्माण कार्य रामगोपाल सोनी के घर से कमोद सिंह के घर तक ग्राम ठीकरी | Ongoing | 28000 | 0 | 2024-03-10
SOHAGPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1732005058/RS/22012035125577 — आर सीसी नाली निर्माण कार्य डालचंद के मकान से मेहरवान के मकान तक ग्राम ठीकरी | Ongoing | 33000 | 0 | 2024-03-13
SOHAGPUR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732005058/RS/VB/YD/22012035140633 — Construction of Soak Pit for 1 | Approved | 0 | 0 | 2026-04-14
SOHAGPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plntation-Biodrainage-fields-Comm / Bio-drainage Plantation for Community | Plantation | 1732005058/WC/22012035155871 — bad niyantran nala gahrikaran saf safai jagdeesh patel ke khet se madho ke khet tak thikari | Ongoing | 113176.14 | 0 | 2024-01-19
SOHAGPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boundary Line Plantation of Forestry-Community / Avenue Plantation for Community | Plantation | 1732005058/WC/22012035155872 — khanti khuda kary shshkiya bhoomi par thikari se ranigohan marg thikari | Ongoing | 57189.16 | 0 | 2024-01-19