## Work List
Exported on: 2026-10-14 13:43:11
Filters applied:
Data source: VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: KHIDIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PIPARIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1732006019/IF/22012035380768 — shok pit khedapati mandir ke pass semrirandheer | New | 0 | 0 | 2025-04-14
PIPARIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1732006019/IF/22012035443652 — Dugwell nirman jamna kushwah ke khet me kuaa ke pass semrirandheer | New | 0 | 0 | 2025-04-15
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732006019/IF/22012035596871 — Ek Bagiya maa ke naam sangeeta thakur / mahendra thakur semrirandheer | Ongoing | 269386.03 | 0 | 2025-09-19
PIPARIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/3781555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130638791 | Approved | 27000 | 0 | 2022-04-26
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/3840749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811111 | Completed | 27000 | 0 | 2024-10-11 | 2026-09-18
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/4635573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130636541 | Ongoing | 27000 | 0 | 2024-11-08
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5002471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811315 | Ongoing | 27000 | 0 | 2025-04-11
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5002473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811359 | Ongoing | 27000 | 0 | 2025-04-11
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5162237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118817502 | Ongoing | 27000 | 0 | 2025-04-11
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5187007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125061718 | Ongoing | 27000 | 0 | 2025-07-25
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5210418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117809721 | Ongoing | 27000 | 0 | 2025-04-11
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5275836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130635972 | Ongoing | 27000 | 0 | 2025-07-25
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5305025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130648242 | Approved | 27000 | 0 | 2025-03-27
PIPARIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/542045 — Construction of IAY House -IAY REG. NO. MP3124285 | Ongoing | 27000 | 0 | 2019-11-11
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5668268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119640501 | Ongoing | 27000 | 0 | 2025-07-18
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5904134 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113960092 | Completed | 23490 | 0 | 2026-04-03 | 2026-08-06
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5905403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130636020 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5906075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146448549 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5906076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130840270 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5907425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125804394 | Ongoing | 27000 | 21900 | 2026-07-03
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5908897 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121682364 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5909226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117810968 | Ongoing | 27000 | 14100 | 2026-07-31
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5910294 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118819249 | Ongoing | 27000 | 3600 | 2026-04-17
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5911912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130648478 | Approved | 27000 | 0 | 2026-02-16
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5912652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125358297 | Ongoing | 27000 | 10200 | 2026-08-28
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5914205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130645043 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5916343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125052964 | Ongoing | 27000 | 0 | 2026-04-03
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5916833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130837260 | Approved | 27000 | 0 | 2026-02-16
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5916905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130670998 | Approved | 27000 | 0 | 2026-02-16
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5918743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811164 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5918793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122135212 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5919709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130638521 | Ongoing | 27000 | 15600 | 2026-05-29
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5919724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118346798 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5920431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125807639 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5922170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127158169 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5922788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811220 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5923303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125808212 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5923669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811546 | Ongoing | 27000 | 0 | 2026-06-12
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5923722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130663608 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5923799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811440 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5924132 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113959308 | Ongoing | 27000 | 3600 | 2026-04-03
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5925051 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119631132 | Ongoing | 27000 | 20400 | 2026-06-12
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5925276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130639809 | Ongoing | 27000 | 0 | 2026-10-09
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5925356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130836825 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5925799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130835711 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5925910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130638062 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5926156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125359385 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5927317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113858294 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5927622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130648733 | Approved | 27000 | 0 | 2026-02-16
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5928191 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121687127 | Ongoing | 27000 | 12000 | 2026-05-29
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5929618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130641662 | Approved | 27000 | 0 | 2026-02-16
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5929878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119630983 | Ongoing | 27000 | 20400 | 2026-06-12
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5930043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118818363 | Approved | 27000 | 0 | 2026-02-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5931256 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130637008 | Ongoing | 27000 | 0 | 2026-10-09
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/5931754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119630737 | Ongoing | 27000 | 6900 | 2026-04-17
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6118710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117811485 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6131991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124203112 | Approved | 27000 | 0 | 2026-03-06
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6146556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130639006 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6150994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130655061 | Approved | 27000 | 0 | 2026-03-06
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6161893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125053711 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6161894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130841128 | Approved | 27000 | 0 | 2026-03-06
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6161900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130653228 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6161905 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130642880 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6173874 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130835194 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6174660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130647161 | Approved | 27000 | 0 | 2026-03-02
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6373372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125357542 | Approved | 27000 | 0 | 2026-06-24
PIPARIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/6373551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124206531 | Approved | 27000 | 0 | 2026-06-24
PIPARIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/679739 — Construction of IAY House -IAY REG. NO. MP3376223 | Ongoing | 27000 | 0 | 2019-11-11
PIPARIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1732006019/IF/IAY/682489 — Construction of IAY House -IAY REG. NO. MP3777698 | Ongoing | 27000 | 0 | 2019-11-18
PIPARIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plug for Community | Boulder Check/Gully Plug | 1732006019/WC/22012035210961 — NALA UPCHAR ALOK KE KHET SE ASHOK KE KHET TAK SEMRIRANDHEER | Approved | 0 | 0 | 2024-06-09