## Work List
Exported on: 2026-09-09 07:28:12
Filters applied:
Data source: MGNREGA + VBGRAMG
District: NARMADAPURAM
Block: All
Panchayat: BHAMORI KALA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732006042/AV/22012034467302 — Soak pit NalJail Boor ke Side me | Completed | 13427.22 | 9504 | 2019-09-14 | 2019-10-04
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732006042/AV/22012034467307 — SOAK PIT PRIMARY SCHOOL HAND PUMP KE SIDE ME | Completed | 13427.22 | 9504 | 2019-10-01 | 2019-10-21
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732006042/AV/22012034467310 — SOAK FIT NALJAL WATER TANK KE SIDE ME | Completed | 13427.22 | 9504 | 2019-10-19 | 2019-11-05
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732006042/AV/22012034467311 — SOAK FIT MATA MANDIR HAND PUMP KE SIDE ME | Completed | 13427.22 | 9504 | 2019-11-03 | 2019-12-08
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732006042/AV/22012034467312 — SOAK FIT HARIJAN MOHALLA HAND PUMP KE SIDE ME | Completed | 13427.22 | 9504 | 2019-11-25 | 2019-12-05
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1732006042/AV/22012034467313 — SOAK FIT HANUMAN MANDIR HAND PUMP KE SIDE ME | Completed | 13427.22 | 9504 | 2019-11-10 | 2020-03-08
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1732006042/AV/22012034504323 — Boundary wall primary school | Completed | 40500 | 40656 | 2019-12-06 | 2020-03-14
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1732006042/AV/22012034507343 — Aganwadi bhavan nirman | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732006042/AV/22012034509609 — Sokfit Naljal Hand pump ke pass | Completed | 14283.77 | 10260 | 2020-05-18 | 2020-08-19
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732006042/AV/22012034509612 — Sokfit Harijan Mohalla | Completed | 14283.77 | 10070 | 2020-06-15 | 2020-08-19
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732006042/AV/22012034509614 — Sokfit Main Road Hand pump ke pass | Deleted | 0 | 0 | 2020-04-14
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732006042/AV/22012034509803 — Sokfit Primary School Hand pump ke pass | Completed | 14283.77 | 10070 | 2020-06-15 | 2020-08-19
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732006042/DP/22012034544233 — maa ki bagiya school me gram kumhawad gp bamohrikala | Closed | 0 | 0 | 2021-09-02
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732006042/DP/22012034544234 — maa ki bagiya school me gram bamohrikala | Closed | 19332.58 | 0 | 2021-09-02
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732006042/DP/22012034544235 — maa ki bagiya school me gram bamohrikala | Closed | 0 | 0 | 2021-09-02
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1732006042/DP/22012034544236 — maa ki bagiya school me gram kumhawad gp bamohrikala | Completed | 29000.28 | 10884 | 2022-03-21 | 2024-06-08
PIPARIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1732006042/DP/22012034594895 — Vasudha Vandan Govt middle School | Ongoing | 55847.4 | 8676 | 2024-07-20
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Works for Flood Control and Protection | 1732006042/FP/22012034368810 — मच्छवाई नाला सफाई | Completed | 211695.6 | 184110 | 2021-01-01 | 2021-07-10
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of sub-minor Canal for Community / Repair and Maintenance of sub-minor Canal for Community | Repair & Maint of Canal | 1732006042/IC/22012034388465 — नहर सफाई कार्य | Completed | 108315.7 | 92340 | 2020-11-23 | 2020-12-18
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Repair & Maint of sub-minor Canal for Community / Repair and Maintenance of sub-minor Canal for Community | Repair & Maint of Canal | 1732006042/IC/22012034390392 — नहर साफ सफ़ाई | Completed | 55818 | 41688 | 2022-01-04 | 2022-04-27
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1732006042/IF/22012034341003 — PLANTATION KUMHAWAD | Completed | 534460 | 22292 | 2017-05-20 | 2020-07-15
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732006042/IF/22012034479063 — मेढ वंधान चेन सिंह / भूरा कतिया | Completed | 28877.69 | 20064 | 2019-06-07 | 2019-06-25
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1732006042/IF/22012034479067 — मेड वंधान रामस्वरूप / हल्के कतिया | Completed | 30666.52 | 23232 | 2019-06-07 | 2019-07-04
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Pebble graded Bund for Individuals / Construction of Pebble graded Bund for Individuals | Construction of Bund | 1732006042/IF/22012034479070 — मेड बंधान उमेश / नन्हे भैय्या कुमहावड़ | Completed | 28430.47 | 31680 | 2019-06-07 | 2019-07-02
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732006042/IF/22012034479072 — मेड बंधान राजकुमार / करन सिंह कुमहावड़ | Completed | 28877.69 | 21120 | 2019-06-07 | 2019-06-24
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732006042/IF/22012034479226 — मेड बंधान विनोद / बारेवीर कुमहावड़ | Completed | 29772.1 | 22176 | 2019-06-07 | 2019-07-03
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1732006042/IF/22012034479227 — मेढ़ बंधान भान सिंह / छोटा अहिरवार कुमहावड | Completed | 28877.69 | 22176 | 2019-06-07 | 2019-07-03
PIPARIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732006042/IF/22012034532044 — KHET TALAB NIRMAN BAMHORIKALA | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732006042/IF/22012034567461 — बकरी पालन हेतु शेड का निर्माण हितग्राही माया बाई अहिरवार | Completed | 46636.05 | 40870 | 2020-06-15 | 2022-12-12
PIPARIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1732006042/IF/22012034567479 — बकरी पालन हेतु शेड का निर्माण हितग्राही शांता बाई अहिरवार | Completed | 46636.05 | 40171.75 | 2020-06-15 | 2021-09-11
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1732006042/IF/22012034631342 — निजी खेत मे फलउद्यान छोटेवीर रघुवंशी | Completed | 144900 | 58010 | 2020-11-30 | 2024-06-12
PIPARIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1732006042/IF/22012034842254 — सोकफिट रामस्वरूप कतिया | Completed | 21965.3 | 15486 | 2021-08-27 | 2022-12-12
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732006042/IF/22012035238502 — खेत समतली करण रामस्वरूप कतिया | Completed | 54462.08 | 44955 | 2024-07-17 | 2025-01-14
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732006042/IF/22012035238743 — खेत समतलीकरन राधेश्याम रघुवंशी | Approved | 0 | 0 | 2024-06-21
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1732006042/IF/22012035238757 — खेत समतलीकरन अशोक रघुवंशी | Approved | 0 | 0 | 2024-06-21
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732006042/IF/22012035271542 — Khet Talab Nirman bhagvat sin gp bhamorikala gh | Completed | 166162.45 | 107712 | 2024-12-04 | 2026-03-30
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1732006042/IF/22012035346042 — Khet Talab Pohap Singh Bhamorikala | Approved | 97532.4 | 0 | 2025-04-14
PIPARIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1732006042/IF/22012035551711 — JGSA-Dugwell Recharge work Shiv Mandir ke pass | Completed | 25899.46 | 15660 | 2025-05-27 | 2026-03-25
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732006042/IF/22012035582071 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120015957 | Physically Completed | 23490 | 10440 | 2025-08-05 | 2026-06-30
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732006042/IF/22012035582073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120000541 | Physically Completed | 23490 | 23229 | 2025-08-05 | 2026-06-30
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732006042/IF/22012035582075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149478643 | Completed | 23490 | 23490 | 2025-08-05 | 2026-01-16
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732006042/IF/22012035582077 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120402777 | Completed | 23490 | 23490 | 2025-08-22 | 2026-01-16
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1732006042/IF/22012035582098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP120782427 | Physically Completed | 23490 | 21141 | 2025-11-28 | 2026-06-30
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1732006042/IF/22012035596554 — Ek Bagiya Maa Ke Naam Kirshana Bai Ahirwar/ Chain Singh Ahirwar | Ongoing | 269386.03 | 261 | 2025-09-19
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993666465 — Cattle shed kanchadi lal | Completed | 107283 | 105756.49 | 2015-06-16 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993666496 — Cattle shed Lakhan Lal/Shankar lal | Completed | 107283 | 105446.99 | 2015-06-16 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1732006042/IF/9993666570 — MED BANDHAN BHURA/SAVLEVENI | Completed | 95570 | 9540 | 2015-10-20 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993667207 — CATTLE SHED JASVANT SINGH/BURELAL | Completed | 107283 | 75320 | 2015-06-22 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668106 — CATTLE SHED RAMRATAN/GOVINDI | Completed | 107283 | 107280.99 | 2015-07-10 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668112 — cattle shed Pholsingh /govindi ahirwar | Completed | 107283 | 108747.99 | 2015-06-30 | 2015-11-17
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668147 — Cattle shed Dhansingh/Amira Ahirwar | Completed | 107283 | 107997.29 | 2015-06-29 | 2015-11-17
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668153 — Cattle shed Shankar/chore Lal | Completed | 107283 | 105767.99 | 2015-07-10 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668157 — Cattle shed NARAYAN Singh/Halku Raghuwanshi | Completed | 107284 | 108759.89 | 2015-06-30 | 2015-11-17
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668161 — Cattle shed Parmu/Bhaiya Kal katiya | Completed | 107283 | 105767.99 | 2015-07-07 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668163 — Cattle shed Laxman Singh/Tulshi Ram Raghuwansbi | Completed | 107283 | 106948.89 | 2015-06-30 | 2015-11-17
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1732006042/IF/9993668167 — Cattle shed Ramratan/Shahib Singh | Completed | 107283 | 106234.99 | 2015-07-10 | 2017-11-03
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993678461 — Medhvandhan vishan/jugraj | Completed | 32856 | 29574 | 2015-10-06 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993678562 — med bandhan santosh / babu lal | Completed | 19557 | 13356 | 2015-10-06 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993678563 — MED BANDHAN KANCHADI / BABU LAL | Completed | 41798 | 44838 | 2015-10-13 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993678565 — MED BANDHAN SUSHEELA / KOMAL SINGH | Completed | 20418 | 21942 | 2015-10-13 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993686449 — MED BANDHAN KAMOD/BHIYA LAL KATIYA | Completed | 28340 | 24486 | 2015-11-10 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993686462 — MED BANDHAN PARVATI/KAMOD KATIYA | Completed | 28340 | 25758 | 2015-11-10 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993687231 — MED BANDHAN PARMU/ BHAIYA LAL KATIYA | Completed | 24584 | 14310 | 2015-11-10 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993688216 — MED VANDHAN HANUMET/ HALKU | Completed | 28340 | 12402 | 2015-11-18 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993688225 — MED VANDHAN CHARAN SINGH/PANNA LAL | Completed | 39676 | 26712 | 2015-11-18 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1732006042/IF/9993688242 — MED VANDHAN BURIYA BAI / DHANRAJ | Completed | 44510 | 34344 | 2015-11-18 | 2016-01-18
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/9993700146 — IAY CHEN SINGH / BURA KATIYA | Deleted | 14310 | 0 | 2015-12-29
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/112073 — Construction of IAY House -IAY REG. NO. MP-32-006-042-001/4 | Completed | 14310 | 14454 | 2016-01-20 | 2017-11-15
PIPARIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/112074 — Construction of IAY House -IAY REG. NO. MP-32-006-042-001/43 | Completed | 14310 | 14806 | 2016-01-20 | 2017-11-15
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/1365544 — Construction of IAY House -IAY REG. NO. MP3867973 | Completed | 15480 | 14616 | 2018-05-30 | 2018-08-27
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/1634868 — Construction of IAY House -IAY REG. NO. MP2614468 | Completed | 15660 | 15660 | 2018-07-25 | 2018-10-07
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/1635584 — Construction of IAY House -IAY REG. NO. MP2694562 | Completed | 15660 | 14616 | 2018-05-14 | 2018-08-27
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/1724239 — Construction of IAY House -IAY REG. NO. MP3910962 | Completed | 15660 | 15660 | 2018-06-07 | 2018-10-07
PIPARIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/2147859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5209939 | Completed | 15840 | 15916 | 2019-07-18 | 2020-06-16
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/233653 — Construction of IAY House -IAY REG. NO. MP1377283 | Completed | 15030 | 15030 | 2017-01-24 | 2018-01-22
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/253510 — Construction of IAY House -IAY REG. NO. MP2043181 | Completed | 15030 | 15060 | 2017-01-24 | 2017-11-15
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/260068 — Construction of IAY House -IAY REG. NO. MP2375295 | Completed | 15030 | 15090 | 2017-01-24 | 2018-01-22
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/260916 — Construction of IAY House -IAY REG. NO. MP2489417 | Completed | 15030 | 15120 | 2017-01-24 | 2018-01-22
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/261653 — Construction of IAY House -IAY REG. NO. MP2618327 | Completed | 15030 | 15030 | 2017-01-24 | 2017-11-15
PIPARIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/3652057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125776349 | Completed | 18360 | 18122 | 2022-10-01 | 2023-06-26
PIPARIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/3661208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114969097 | Completed | 18360 | 17850 | 2022-06-04 | 2023-06-13
PIPARIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4186285 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144488161 | Completed | 18360 | 18360 | 2022-07-18 | 2023-01-30
PIPARIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4186593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148591994 | Completed | 18360 | 6120 | 2022-07-18 | 2024-06-12
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4558334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114944214 | Completed | 21870 | 21870 | 2024-09-25 | 2025-02-14
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4691471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114968967 | Completed | 21870 | 21870 | 2024-10-09 | 2025-02-14
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4854898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142883 | Completed | 21870 | 21870 | 2025-01-24 | 2025-03-12
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4990061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106142846 | Completed | 23490 | 23121 | 2025-03-21 | 2025-09-17
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/4997626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114968999 | Ongoing | 27000 | 19809 | 2025-04-09
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5007070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120393358 | Completed | 23490 | 23382 | 2025-03-21 | 2026-01-16
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5007074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120399040 | Completed | 23490 | 23337 | 2025-03-21 | 2026-06-10
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5007084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120406620 | Completed | 23490 | 23382 | 2025-03-21 | 2026-01-16
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5007830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119988160 | Completed | 23490 | 23382 | 2025-03-21 | 2026-05-21
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5007875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120006737 | Completed | 23490 | 23490 | 2025-04-16 | 2026-06-10
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5007884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120011772 | Completed | 23490 | 23382 | 2025-03-21 | 2026-06-10
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5009857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120784532 | Completed | 23490 | 23490 | 2025-04-02 | 2026-01-16
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5014469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124214804 | Completed | 23490 | 18162 | 2025-03-21 | 2026-06-29
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5014472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124215340 | Completed | 23490 | 23382 | 2025-03-21 | 2026-01-16
PIPARIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5017450 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124810703 | Completed | 23490 | 23490 | 2025-06-27 | 2026-01-16
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5102414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148608740 | Completed | 23490 | 23382 | 2025-03-21 | 2026-02-25
PIPARIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/5104497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149478629 | Completed | 23490 | 23382 | 2025-03-21 | 2026-06-04
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/520072 — Construction of IAY House -IAY REG. NO. MP2555324 | Completed | 15030 | 15390 | 2017-03-20 | 2017-11-15
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/659733 — Construction of IAY House -IAY REG. NO. MP1257050 | Completed | 15030 | 15308 | 2017-05-06 | 2018-02-07
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/665654 — Construction of IAY House -IAY REG. NO. MP2016590 | Completed | 15030 | 15308 | 2017-05-06 | 2018-02-07
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/665756 — Construction of IAY House -IAY REG. NO. MP2023316 | Completed | 15030 | 15768 | 2018-05-30 | 2019-09-11
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/665970 — Construction of IAY House -IAY REG. NO. MP2035762 | Completed | 15030 | 14616 | 2018-05-30 | 2018-08-27
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/673314 — Construction of IAY House -IAY REG. NO. MP2594796 | Completed | 15030 | 15480 | 2017-05-06 | 2018-01-12
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/673680 — Construction of IAY House -IAY REG. NO. MP2614445 | Completed | 15030 | 15480 | 2017-05-06 | 2018-02-07
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/674245 — Construction of IAY House -IAY REG. NO. MP2686462 | Approved | 27000 | 0 | 2017-03-15
PIPARIYA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/682290 — Construction of IAY House -IAY REG. NO. MP3734061 | Approved | 27000 | 0 | 2017-03-15
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/682331 — Construction of IAY House -IAY REG. NO. MP3744553 | Completed | 15030 | 15308 | 2017-05-06 | 2018-02-13
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/682377 — Construction of IAY House -IAY REG. NO. MP3754727 | Completed | 15030 | 15136 | 2017-05-06 | 2018-03-09
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/683087 — Construction of IAY House -IAY REG. NO. MP3908935 | Completed | 15030 | 14620 | 2017-05-16 | 2018-08-27
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/683089 — Construction of IAY House -IAY REG. NO. MP3909195 | Completed | 15030 | 15522 | 2017-05-06 | 2018-05-18
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/932958 — Construction of IAY House -IAY REG. NO. MP2672037 | Completed | 15480 | 15308 | 2017-05-26 | 2018-02-13
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/933096 — Construction of IAY House -IAY REG. NO. MP2675377 | Completed | 15480 | 15308 | 2017-05-26 | 2018-02-13
PIPARIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/933963 — Construction of IAY House -IAY REG. NO. MP2694546 | Completed | 15480 | 15480 | 2017-05-26 | 2018-02-07
PIPARIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1732006042/IF/IAY/980694 — Construction of IAY House -IAY REG. NO. MP3909982 | Completed | 15480 | 14616 | 2018-06-07 | 2018-08-27
PIPARIYA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034262756 — शांतिधाम निर्माण BHAMORIKALA | Deleted | 451806 | 0 | 2016-04-01
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1732006042/LD/22012034265702 — शांतिधाम निर्माण KUMHAWAD | Completed | 180000 | 160794.73 | 2017-03-21 | 2019-02-15
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1732006042/LD/22012034296320 — Shanti dham Bhamorikala | Completed | 180000 | 171228.93 | 2016-12-28 | 2019-01-15
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1732006042/LD/22012034527346 — trench work bhamorikala | Closed | 148238.74 | 0 | 2020-10-02
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1732006042/LD/22012034528991 — खेत समतली करण रामस्वरूप कतिया | Closed | 0 | 0 | 2020-08-15
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Level Bench Terrace Terrace for Comm / Construction of Level Bench Terrace for Community | Terracing | 1732006042/LD/22012034528992 — खेत समतलीकरण नर्मदा प्रसाद कतिया | Closed | 0 | 0 | 2020-08-15
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034542481 — खेत समतलीकरण कमल सिंह मालवीय ग्राम कुम्हावड़ | Completed | 62901.4 | 52440 | 2021-03-04 | 2021-07-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034546366 — खेतसमतलीकरण उमेश कुमार कुम्हाबड़ | Closed | 41635.12 | 0 | 2021-04-01
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034546370 — खेत समतली करण भानसिंह अहिरवार कुम्हावड़ | Completed | 64200 | 52110 | 2021-04-08 | 2021-07-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034546373 — खेतसमतलीकरण रामसरूप पठारीया बम्होरीकला | Completed | 67047.09 | 54426 | 2021-04-08 | 2021-07-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034555671 — खेतसमतलीकरण चेन सिंह कतिया बम्होरीकला | Completed | 51059.23 | 35898 | 2021-05-18 | 2021-09-11
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034555672 — खेत समतलीकरण बेनी प्रसाद कतिया बमोरी कला | Completed | 48282.74 | 26634 | 2021-06-15 | 2021-08-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034555791 — खेत समतलीकरण फूल सिंह कतिया बमोरी कला | Completed | 56088.68 | 48636 | 2021-05-18 | 2021-08-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034555793 — खेत समतलीकरण नर्मदा प्रसाद कतिया बमोरी कला | Completed | 49600.41 | 39372 | 2021-06-15 | 2021-08-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034555795 — खेत समतलीकरण कनछेदी कतिया बमोरी कला | Completed | 41576.8 | 27792 | 2021-06-15 | 2021-08-10
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/22012034562497 — खेत समतलीकरण कमल सिंह रघुवंशी कुम्हावड़ | Completed | 56753.39 | 47478 | 2021-06-13 | 2021-08-10
PIPARIYA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1732006042/LD/3799429274 — खेल मैदान स्कूल परिसर- कुम्माबड | Completed | 244546 | 8686.32 | 2014-02-25 | 2014-11-07
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1732006042/PG/9425895702 — खेल मेदान BHAMORIKALA | Completed | 186600 | 2176 | 2017-03-21 | 2017-04-20
PIPARIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/183 — पं प मेनरोड से मंदि‍र की ओर सी सी रोड | Completed | 178000 | 116117 | 2012-05-28 | 2012-07-04
PIPARIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/216 — बम्‍होरी मार्ग पुलि‍या नि‍माण | Completed | 178018 | 164683.57 | 2012-08-11 | 2014-06-11
PIPARIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034162530 — pp main road se sashkiya bhavan ki or | Completed | 97623 | 49152 | 2013-01-16 | 2013-12-30
PIPARIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034186811 — वि‍घायक नि‍धी स्‍कुल से मुख्‍य मार्ग की ओर सी.सी र | Completed | 61303 | 49370 | 2013-10-08 | 2014-05-28
PIPARIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034187191 — पंचपरमेंश्‍वर स्‍कूल की पुलि‍या से बगीचे की ओर सीं | Completed | 89375 | 70735 | 2013-10-08 | 2014-11-07
PIPARIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034206475 — पंचपरमेश्वर मुन्नीलाल के घर से राममंदिर की ओर सी.स | Completed | 101523 | 64988.4 | 2014-02-25 | 2014-05-28
PIPARIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034207245 — पंचपरमेंश्‍वर स्‍कूल से प्रह्लाद रघुवंशी के मकान क | Completed | 81000 | 68530 | 2014-02-25 | 2014-11-07
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034296737 — C.C. ROAD CC ROAD SE RAJKUMAR KE GHAR KI AUR | Completed | 85789 | 72510 | 2016-01-28 | 2016-12-23
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034296741 — C.C ROAD SCHOOL ROAD SE RAKESH KE GHAR KI AUR | Completed | 45880 | 57753 | 2016-01-19 | 2016-12-23
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034322579 — c c road nali nirman | Closed | 0 | 0 | 2017-01-26
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1732006042/RC/22012034329344 — 14 वित चैन सिंग कतिया के घर के पीछे से हल्के भिया के घर की और | Completed | 28954 | 18276 | 2017-03-10 | 2017-12-22
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034329353 — 14 वित चैन सिंग कतिया के घर के सामने से महेंद्र कतीय के घर की और | Completed | 26426 | 35070 | 2017-03-03 | 2017-12-22
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1732006042/RC/22012034347200 — 14 वित सीसी रोड और नाली निर्माण हरिजन मोहलाल हॅंड पंप से गोरी शंकर के घर की ओर | Completed | 28320 | 28896 | 2017-07-28 | 2017-12-22
PIPARIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034374737 — C C ROAD | Closed | 0 | 0 | 2016-10-02
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034398381 — CC रोड एवं नाली निर्माण मेन रोड से बचचन सिंग के घर की ओर | Completed | 18200 | 15840 | 2019-08-29 | 2019-10-25
PIPARIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034398397 — सीसी रोड एवं नाली निर्माण निर्मित सीसी रोड से राधेलाल रघुवंशी के घर की ओर | Completed | 49200 | 38628 | 2019-01-10 | 2019-02-08
PIPARIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034398399 — सीसी रोड मैंन रोड से उमेश रघुवंशी के घर की ओर | Closed | 7650 | 0 | 2018-08-15
PIPARIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034435034 — CC ROAD | Closed | 49200 | 0 | 2018-08-15
PIPARIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034441658 — सी सी रोड नली निर्माण | Closed | 0 | 0 | 2019-01-26
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034469486 — CC ROAD AUR NALI NIRMAN RADHELAL KE GHAR SE PANCHAYAT BHAVAN HOKAR SHANTI DHAM KI AUR | Completed | 73800 | 58080 | 2019-07-09 | 2019-09-02
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034469488 — CC ROAD CHEN SINGH KE GHAR SE PANCHAYAT BHAVAN KI AUR | Closed | 24900 | 0 | 2019-04-14
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034516608 — CC ROAD SHANTI DHAM SE RIVER KI AUR | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034516610 — CC ROAD PRAKESH RAGHUWANSHI KE GHAR SE RAMESHWAR RAGHUWANSHI KE GHAR KI AUR | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034516612 — CC ROAD RADHESYAM RAGHUWANSHI KE GHAR SE CHEN SINGH KE GHAR KI AUR | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034516656 — Sudoor sadak | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034516671 — CC RAOD NIRMAN RADHESHYAM KE GHAR SE MAIN ROAD TAK | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034559469 — सीसी रोड एवं नाली निर्माण निर्मित सीसी रोड से रामा जी कटिया के घर तक | Completed | 39000 | 33060 | 2021-02-10 | 2021-03-17
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034559473 — सीसी रोड एवं नाली निर्माण भैया लाल के घर के पीछे से हरिजन मोहल्ला तक | Completed | 28000 | 28500 | 2021-02-10 | 2021-03-14
PIPARIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034582873 — सीसी रोड मकरन सिंग रघुवंशी के घर से खेंमचंद रघुवंशी के घर की ओर | Completed | 28179 | 25377 | 2021-09-08 | 2021-11-22
PIPARIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034583258 — नाली निर्माण धनराज के घर से नाले की ओर | Completed | 25476 | 24643 | 2021-11-26 | 2022-12-12
PIPARIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1732006042/RC/22012034628008 — आर . सी . सी नाली निर्माण हर् दौल दादा जी से बगीचा की ओर | Closed | 33000 | 0 | 2022-10-02
PIPARIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034642549 — c c road nirman Hardol Dada se bagicha ki Aur | Completed | 20000 | 19227 | 2023-07-19 | 2024-06-08
PIPARIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034670599 — c c road nirman hanuman mandir se ram janki mandir tak | Completed | 39000 | 37774 | 2023-12-13 | 2024-06-08
PIPARIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1732006042/RC/22012034681385 — सीसी रोड निर्माण पदम सिंह रघुवंशी के घर से सुनील रघुवंशी के घर की ओर | Completed | 16000 | 15810 | 2024-03-15 | 2025-01-14
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284417 — NBA GORA BAI / RICHA | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284448 — NBA Harkishan / Pahalad singh | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284480 — NBA AMAN SINGH / SHANKAR SINGH RAGHUWANSHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284505 — SBM PRASOTAM / AMAN SINGH | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284508 — SBM HAR NARAYAN /SHATAN SINGH | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284510 — SBM HARBHAJAN/ABHYA RAM HARIJAN | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284513 — SBM DEEN DAYAL / SITA RAM RAGHUWANSHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284519 — SBM ASHOK / GANESH RAGHUWANSHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284585 — SBM KHEM CHAND / SITA RAM RAGHUWANSHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284591 — SBM PADAM / KISHORI RAGHUWNASHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284595 — SBM MUNSI VASHKAR | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284598 — SBM MAHESH / SHANKAR RAGHUWANSHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284602 — SBM RAMRATAN / GOVINDI AHIRWAR | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284603 — SBM MOHAN / BHAGIRATH RAGHUWANSHI | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284605 — SBM JASVANT / RAMMU AHIRWAR | Completed | 3289 | 3180 | 2015-09-24 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284607 — SBM HARI RAM / CHOTA AHIRWAR | Completed | 3289 | 3180 | 2015-10-06 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284610 — SBM VINOD / khem chand Raghuwanshi | Completed | 3289 | 3180 | 2015-10-06 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284612 — SBM CHOTU VANSKAR | Completed | 3289 | 3180 | 2015-10-05 | 2016-01-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284614 — SBM CHEN SINGH / GOVINDI AHIRWAR | Completed | 3289 | 3180 | 2015-10-06 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284617 — SBM RAJESH / ABHYA RAM AHIRWAR | Completed | 3289 | 3180 | 2015-10-20 | 2015-11-17
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284950 — SBM VANI PRASAD KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034284965 — SBM CHEN SINGH KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285512 — SBM KERA KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285516 — SBM Dashiya KATIYA | Completed | 3289 | 2862 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285519 — SBM SANTOSH KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285522 — SBM Rataniya Bai KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285534 — SBM Nandkishor KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285541 — SBM Ramsvarup KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285545 — SBM Narvada Prasad KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285549 — SBM RAM JI KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285555 — SBM Malkhe Singh katiya | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285560 — SBM Lakshman Singh | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285563 — SBM HANUMAT SINGH KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285568 — SBM PARMU SINGH KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285571 — SBM KAMOD KATIYA | Completed | 3289 | 3180 | 2015-09-29 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285575 — SBM DAMODAR KATIYA | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285577 — SBM JASMAN KATIYA | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285579 — SBM CHEN SINGH KAITIYA | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285584 — SBM RAM KISHAN KATIYA | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034285589 — SBM Salakram Raghuwansi | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034286310 — SBM LAKHAN LAL RAGHUWANSHI | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034286318 — SBM HARPRASAD RAGHUWANSHI | Completed | 3289 | 2862 | 2015-10-06 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034286322 — SBM JASMAN / BURA RAGHUWANSHI | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034286326 — SBM SIYA RAM /KESHAR SINGH RAGHUWANSHI | Completed | 3289 | 3180 | 2015-10-06 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289386 — SBM RAKESH /SHANKAR RAGHUWANSHI | Completed | 3289 | 2862 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289387 — SBM NAND RAM /GOKAL AHIRWAR | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289388 — SMB KAMAL/ SHANKAR RAGHUWANSHI | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289389 — SBM KASTURI BAI AHIRWAR | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289390 — SBM GULAB/NANU MALVIYA | Completed | 3289 | 3180 | 2015-10-20 | 2015-11-17
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289428 — SBM TIKA RAM / DHAR DAS MAV\LVIYA | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289430 — SBM BAL KISHAN / HARI SINGH SARATHE | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289432 — SBM PHOOL SINGH /DHARAM DAS MALVIYA | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289436 — SBM DHAN SINGH/ AMIRA AHIRWAR | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289449 — SBM HARPRASAD RAGHUWANSHI KUMHAWAD | Completed | 3289 | 3180 | 2015-10-20 | 2015-12-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289453 — SBM NANAK RAM / GOKAL HAIRWAR | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289456 — SBM BHAN SINGH / JAGDIESH RAGHUWANSHI | Deleted | 3289 | 0 | 2015-10-19
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289457 — SBM PADAM / SUNDER RAGHUWANSHI KUMHAWAD | Deleted | 0 | 0 | 2015-08-15
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289460 — SBM LEELADHAR RAGHUWANSHI KUMHAWAD | Completed | 3289 | 3180 | 2015-10-20 | 2015-10-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034289461 — SBM BUTI RAGHUWANSHI KUHAWAD | Completed | 3289 | 3180 | 2015-11-03 | 2016-01-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034291162 — SBM AJAB SINGH/SAHAB SINGH RAGHUWANSHI | Completed | 3289 | 3180 | 2015-11-03 | 2016-01-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034291164 — SBM RAM NATH /SAHAB SINGH | Completed | 3289 | 3180 | 2015-11-03 | 2016-01-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034291165 — SBM RAMRATAN / SAHAB SINGH | Completed | 3289 | 3180 | 2015-11-03 | 2016-01-28
PIPARIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034291240 — SBM SAROOP SINGH / KOMAL SINGH RAGHUWANSHI | Deleted | 3289 | 0 | 2015-10-19
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034372865 — SBM HARNAM / RAMESH RAGHUWANSHI BHAMORIKALA | Completed | 11440 | 10752 | 2017-09-30 | 2018-08-12
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034372868 — SBM ABHINASH/ RAGHUVEER RAGHUWANSHI | Completed | 11440 | 10752 | 2017-09-30 | 2018-08-14
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034372873 — SBM ATAR SINGH / PRATHVI SINGH RAGHUWANSHI | Completed | 11440 | 10741.78 | 2017-09-30 | 2018-12-28
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034372877 — SBM SIYA RAM / KESHAR RAGHUWANSHI | Completed | 11440 | 2752 | 2017-09-30 | 2017-10-24
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034372879 — SBM RAM CHARAN /DAMMU RAGHUWANSHI | Completed | 11440 | 10752 | 2017-09-30 | 2018-08-14
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034376670 — SBM DEVENDRA/ RRANVEER RAGHUWANSHI | Completed | 11440 | 10752 | 2017-09-30 | 2018-08-14
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034376675 — SBM PARSHOTTAM / PAHLAD SINGH RAGHUWANSHI | Completed | 11440 | 10752 | 2017-09-30 | 2018-08-14
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034376678 — SBM PRADEEP / RAMESH RAGHUWANSHI | Completed | 11440 | 10064 | 2017-09-30 | 2018-08-14
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034376682 — SBM GENDA LAL / MAKRAN RAGHUWANSHI | Completed | 11440 | 10752 | 2017-09-30 | 2018-08-14
PIPARIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1732006042/RS/22012034376685 — SBM PHOOLSING / DHARM DAS MALVIYA | Completed | 11440 | 2752 | 2017-09-30 | 2017-10-11
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1732006042/RS/22012034496995 — samudayik swchta parishar prthmik shala bhavan ke pas bamohorikala | Completed | 43700 | 43320 | 2020-09-27 | 2025-01-14
PIPARIYA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012034511542 — कच्ची नाली निर्माण स्कूल के पीछे से बगीचा की ओर ग्राम कुमावड़ | Completed | 72461.52 | 50952 | 2021-04-01 | 2021-07-10
PIPARIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012034671739 — nahar safai karya bamhorikala | Closed | 0 | 0 | 2022-10-02
PIPARIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012034671773 — nahar safai karya bamhorikala | Closed | 0 | 0 | 2022-10-02
PIPARIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012034671775 — nahar safai karya bamhorikala | Closed | 0 | 0 | 2022-10-02
PIPARIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012034671890 — nahar safai karya bamhorikala | Completed | 74549.6 | 63648 | 2022-10-28 | 2023-03-30
PIPARIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012035121252 — कच्ची नाली निर्माण हरिराम अहिरवार के घर से पुलिया की ओर | Closed | 0 | 0 | 2023-10-21
PIPARIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012035121255 — कच्ची नाली निर्माण हरिराम अहिरवार के घर से पलिया की ओर | Completed | 41636.1 | 31743 | 2024-01-07 | 2025-01-14
PIPARIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1732006042/RS/22012035136092 — Rcc nali nirman naljalpump house se nale ki or | Completed | 10000 | 9990 | 2025-02-19 | 2025-05-19
PIPARIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1732006042/SK/147 — Bharat Nirman Rajeev Gandhi Sewa Kendra,BHAMORI KALA | Completed | 452000 | 441222.16 | 2013-07-02 | 2015-10-03
PIPARIYA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1732006042/WC/22012034395366 — jal evam mrda sanrachn shaskiy bhumi me | Closed | 13059.9 | 0 | 2018-04-14
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732006042/WC/22012034510327 — khet talab ramkishan | Closed | 101996.79 | 0 | 2019-10-15
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732006042/WC/22012034510329 — khet talab Meharvan Raghuwanshi | Completed | 101996.79 | 76788 | 2019-12-30 | 2020-07-03
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732006042/WC/22012034524313 — Khet Talab | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1732006042/WC/22012034524314 — Khet talab | Closed | 0 | 0 | 2020-01-26
PIPARIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1732006042/WC/22012034529318 — KHET TALAB ATAR SINGH RAGHUWANSHI | Completed | 101997.1 | 45996 | 2020-03-13 | 2020-11-25
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1732006042/WC/22012034548676 — शासकिय भूमि लघु तालाब | Closed | 332572.21 | 0 | 2020-04-14
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1732006042/WC/22012034550172 — Talab Nirman Choti hai Raghuwanshi | Completed | 108814.67 | 78850 | 2020-05-16 | 2020-07-08
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1732006042/WC/22012034551912 — Khet Talab Bachaan Singh | Completed | 108814.67 | 78660 | 2020-05-28 | 2020-07-23
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1732006042/WC/22012034551916 — Khet Talab Santosh Raghuwanshi | Completed | 108814.67 | 78850 | 2020-05-27 | 2020-07-03
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1732006042/WC/22012034551919 — Khet talab Heera Lal Raghuwanshi | Closed | 0 | 0 | 2020-04-26
PIPARIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1732006042/WC/22012034589328 — नाला सफाई ग्राम बॅम्होरी कला | Completed | 150274.9 | 124260 | 2020-10-12 | 2021-01-06
PIPARIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1732006042/WC/22012034598871 — नाला सफाई स्कूल के पीछे से नदी की ओर बॅम्होरी कला | Completed | 232942 | 204060 | 2020-12-10 | 2025-05-04
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732006042/WC/22012034689487 — CTR Rain water harvesting swachhta parisar bamhorikala | Completed | 19171.81 | 15486 | 2021-06-13 | 2022-02-27
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732006042/WC/22012034689491 — CTR rain water harvesting anganwadi bhawan bamhorikala | Completed | 19171.81 | 15486 | 2021-06-13 | 2022-02-27
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1732006042/WC/22012034689495 — CTR rain water harvesting panchyt bhawan bamhorikala | Completed | 19171.81 | 15486 | 2021-06-13 | 2022-02-27
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732006042/WC/22012034690092 — CTR rain water harvesting panchayat bhavan bhamorikala | Closed | 0 | 0 | 2021-04-14
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1732006042/WC/22012034690107 — CTR rain water harvesting aganwadi bhavan bhamorikala | Closed | 0 | 0 | 2021-04-14
PIPARIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1732006042/WC/22012034809031 — CTR water harvesting primary school | Closed | 26654.26 | 0 | 2021-08-15
PIPARIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1732006042/WC/28 — नि‍रमलनि‍र कुप नि‍रमान बामोरीकला | Completed | 147000 | 5500 | 2009-02-05 | 2014-11-05